## readme demo
[10 empty] | Proposal #: | 1945.02 |  |  |  | Start Date | 45838
[10 empty] | Job #: | Nitron 2500T
Change #:
[10 empty] | Description: | Nitron 2500T (Rev #2)
[10 empty] | Owner: | Linde
[10 empty] | Location: | Sherman, Texas | [8 empty] | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 6 | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
[10 empty] | Date: | June 23, 2025
[10 empty] | Estimate Basis |  |  |  |  | Progress (These values calculate automatically) |  |  |  |  | WE | 2025-07-06 |  |  |  |  | WE | 2025-07-13 |  |  |  |  | WE | 2025-07-20 |  |  |  |  | WE | 2025-07-27 |  |  |  |  | WE | 2025-08-03 |  |  |  |  | WE | 2025-08-10 |  |  |  |  | WE | 2025-08-17 |  |  |  |  | Weekly Quantitities Complete | [6 empty] | Weekly Earned MH
Filter | WBS | PHASE | SIZE | FLC | LINE / DESCRIP | SPEC | INSUL | INSL. SIZE | SHT | QTY | UNIT | CRAFT | WELD | TOTAL | QTY COMPLETE | QTY REMAINING | MH EARNED | MH REMAINING TO EARN | % COMPLETE | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17
W | 10000 | WBS |  |  | MOBILIZE | [6 empty] | 78 | 10 | 88 |  |  | 88 | 0 | 100%
P | 10000 | 10001 |  |  | EQUIPMENT SETUP | [6 empty] | 13 | 0 | 13 |  |  | 13 | 0 | 100%
D | 10000 | 10001 |  |  | TOOLS |  |  |  |  | 1 | EA | 5 | 0 | 5 | 1 | 0 | 5 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | bar: WE M
D | 10000 | 10001 |  |  | EQUIPMENT |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | [42 empty] | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | bar: WE M to 2025-07-06 W; WE M
P | 10000 | 10002 |  |  | TRAILER SETUP | [6 empty] | 10 | 0 | 10 |  |  | 10 | 0 | 100%
D | 10000 | 10002 |  |  | TOOL TRAILER |  |  |  |  | 1 | EA | 10 | 0 | 10 | 1 | 0 | 10 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | bar: WE M
P | 10000 | 10004 |  |  | SAFETY ORIENTATION | [6 empty] | 55 | 0 | 55 |  |  | 55 | 0 | 100%
D | 10000 | 10004 |  |  | CUSTOMER SAFETY ORIENTATION |  |  |  |  | 11 | CRAFT | 44 | 0 | 44 | 11 | 0 | 44 | 0 | 100% | WE M: 4; WE M: 3; 2025-07-13 Tu: 4 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 16 | 28 | 0 | 0 | 0 | 0 | 0
D | 10000 | 10004 |  |  | INDEMAND SAFETY ORIENTATION |  |  |  |  | 11 | CRAFT | 11 | 0 | 11 | 11 | 0 | 11 | 0 | 100% | WE M: 4; WE M: 3; 2025-07-13 Tu: 4 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0
P | 10000 | 10005 |  |  | WELDER TEST / QUALIFICATION | [6 empty] | 0 | 10 | 10 |  |  | 10 | 0 | 100%
D | 10000 | 10005 |  |  | TEST |  |  |  |  | 1 | CRAFT | 0 | 10 | 10 | 1 | 0 | 10 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
W | 30000 | WBS |  |  | CONCRETE | [6 empty] | 58.88 | 0 | 58.88 |  |  | 58.88 | 0 | 100%
P | 30000 | 30001 |  |  | CEMENTITIOUS GROUT | [6 empty] | 27.85 | 0 | 27.85 |  |  | 27.85 | 0 | 100%
D | 30000 | 30001 |  |  | BUSH HAMMER |  |  |  |  | 11 | SF | 3.85 | 0 | 3.85 | 11 | 0 | 3.85 | 0 | 100% | 2025-07-06 Th: 1; WE M: 10 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0.35 | 0 | 3.5 | 0 | 0 | 0 | 0
D | 30000 | 30001 |  |  | PREPURIFIER VESSEL A |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-27 Th: 2; 2025-07-27 F: 1; 2025-07-27 Sa: 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
D | 30000 | 30001 |  |  | PREPURIFIER VESSEL B |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-27 Th: 2; 2025-07-27 F: 1; 2025-07-27 Sa: 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
D | 30000 | 30001 |  |  | GLYCOL EXPANSION TANK |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-20 Tu: 1; 2025-07-27 F: 2; 2025-07-27 Sa: 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0
P | 30000 | 30002 |  |  | EPOXY GROUT |  |  |  | (REV #1) |  |  | 31.03 | 0 | 31.03 |  |  | 31.03 | 0 | 100%
D | 30000 | 30002 |  |  | BUSH HAMMER |  |  |  | (REV #1) | 25 | SF | 8.75 | 0 | 8.75 | 25 | 0 | 8.75 | 0 | 100% | 2025-07-06 Th: 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0
D | 30000 | 30002 |  |  | GROUT FORMING |  |  |  | (REV #1) | 46 | LF | 13.8 | 0 | 13.8 | 46 | 0 | 13.8 | 0 | 100% | 2025-07-27 Th: 45; 2025-07-27 Sa: 1 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8 | 0 | 0 | 0
D | 30000 | 30002 |  |  | MAC AND BNC |  |  |  | (REV #1) | 1.48 | CY | 5.92 | 0 | 5.92 | 1.48 | 0 | 5.92 | 0 | 100% | 2025-07-27 Sa: 1.48 | 0 | 0 | 0 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 5.92 | 0 | 0 | 0
D | 30000 | 30002 |  |  | COLD BOX |  |  |  | (REV #1) | 0.32 | CY | 1.28 | 0 | 1.28 | 0.32 | 0 | 1.28 | 0 | 100% | WE M: 0.32 | 0 | 0 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 0 | 0 | 0 | 0
D | 30000 | 30002 |  |  | TURBINE BOX |  |  |  | (REV #1) | 0.32 | CY | 1.28 | 0 | 1.28 | 0.32 | 0 | 1.28 | 0 | 100% | 2025-07-20 Tu: 0.32 | 0 | 0 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 0 | 0 | 0 | 0
W | 40000 | WBS |  |  | TOWERS/VESSELS/EQUIPMENT | [6 empty] | 983.71 | 30 | 1013.71 |  |  | 993.52 | 20.19 | 98.01%
P | 40000 | 40001 | RC-0500/RC-0700 |  | MAC & BNC | (REV #1) |  |  |  | 11.5 | TON | 39.63 | 0 | 39.63 |  |  | 39.63 | 0 | 100%
D | 40000 | 40001 | RC-0500/RC-0700 |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40001 | RC-0500/RC-0700 |  | INSTALL ANCHOR BOLTS | (REV #1) |  |  |  | 6 | EA | 12 | 0 | 12 | 6 | 0 | 12 | 0 | 100% | 2025-07-13 W: 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40001 | RC-0500/RC-0700 |  | SHIM | (REV #1) |  |  |  | 6 | EA | 9 | 0 | 9 | 6 | 0 | 9 | 0 | 100% | 2025-07-06 W: 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40001 | RC-0500/RC-0700 |  | SECURE | (REV #1) |  |  |  | 6 | EA | 6 | 0 | 6 | 6 | 0 | 6 | 0 | 100% | WE M: 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40001 | RC-0500/RC-0700 |  | CLEAN UP | (REV #1) |  |  |  | 11.5 | TON | 8.63 | 0 | 8.63 | 11.5 | 0 | 8.63 | 0 | 100% | 2025-07-13 W: 11; 2025-08-03 Sa: 0.5 | 0 | 11 | 0 | 0 | 0.5 | 0 | 0 | 0 | 8.2548 | 0 | 0 | 0.37522 | 0 | 0
P | 40000 | 40002 | SK-0550 |  | PREPURIFIER SKID | (REV #1) |  |  |  | 14.3 | TON | 98.73 | 8 | 106.73 |  |  | 106.73 | 0 | 100%
D | 40000 | 40002 | SK-0550 |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 8 | 0 | 8 | 1 | 0 | 8 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40002 | SK-0550 |  | INSTALL ANCHOR BOLTS | (REV #1) |  |  |  | 8 | EA | 32 | 0 | 32 | 8 | 0 | 32 | 0 | 100% | 2025-07-13 W: 4; 2025-07-13 Sa: 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40002 | SK-0550 |  | SHIM | (REV #1) |  |  |  | 8 | EA | 32 | 0 | 32 | 8 | 0 | 32 | 0 | 100% | 2025-07-06 W: 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40002 | SK-0550 |  | SECURE | (REV #1) |  |  |  | 8 | EA | 16 | 8 | 24 | 8 | 0 | 24 | 0 | 100% | WE M: 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40002 | SK-0550 |  | CLEAN UP | (REV #1) |  |  |  | 14.3 | TON | 10.73 | 0 | 10.73 | 14.3 | 0 | 10.73 | 0 | 100% | 2025-07-13 Sa: 10; 2025-07-27 Sa: 4.3 | 0 | 10 | 0 | 4.3 | 0 | 0 | 0 | 0 | 7.5035 | 0 | 3.2265 | 0 | 0 | 0
P | 40000 | 40003 | CB-0100 |  | COLD BOX |  |  |  |  | 18 | TON | 120.5 | 6 | 126.5 |  |  | 126.5 | 0 | 100%
D | 40000 | 40003 | CB-0100 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 8 | 0 | 8 | 1 | 0 | 8 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40003 | CB-0100 |  | SHIM |  |  |  |  | 4 | EA | 18 | 0 | 18 | 4 | 0 | 18 | 0 | 100% | 2025-07-06 W: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | SECURE |  |  |  |  | 4 | EA | 12 | 0 | 12 | 4 | 0 | 12 | 0 | 100% | 2025-07-13 Tu: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | CLEAN UP |  |  |  |  | 18 | TON | 13.5 | 0 | 13.5 | 18 | 0 | 13.5 | 0 | 100% | 2025-07-20 Tu: 8; 2025-08-03 Sa: 10 | 0 | 0 | 8 | 0 | 10 | 0 | 0 | 0 | 0 | 6 | 0 | 7.5 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | REMOVE SHIPPING SUPPORTS |  |  |  |  | 2 | EA | 12 | 6 | 18 | 2 | 0 | 18 | 0 | 100% | 2025-07-13 W: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | SD-08 SILENCER |  |  |  |  | 1 | LOT | 10 | 0 | 10 | 1 | 0 | 10 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | bar: 2025-07-20 Tu
D | 40000 | 40003 | CB-0100 |  | INSTALL ANCHOR CHAIR SPACER |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-20 Tu: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | INSTALL POLY FILM |  |  |  |  | 500 | SF | 25 | 0 | 25 | 500 | 0 | 25 | 0 | 100% | 2025-08-03 Sa: 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
D | 40000 | 40003 | CB-0100 |  | INSTALL ACTUATORS |  |  |  |  | 3 | EA | 18 | 0 | 18 | 3 | 0 | 18 | 0 | 100% | 2025-08-03 Sa: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
P | 40000 | 40004 | HV-0360 |  | DRAIN VAPROIZER |  |  |  |  | 1.2 | TON | 30.9 | 0 | 30.9 |  |  | 30.9 | 0 | 100%
D | 40000 | 40004 | HV-0360 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Th
D | 40000 | 40004 | HV-0360 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 16 | 0 | 16 | 4 | 0 | 16 | 0 | 100% | 2025-08-03 Sa: 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0
D | 40000 | 40004 | HV-0360 |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 W: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40004 | HV-0360 |  | SECURE |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 Tu: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40004 | HV-0360 |  | CLEAN UP |  |  |  |  | 1.2 | TON | 0.9 | 0 | 0.9 | 1.2 | 0 | 0.9 | 0 | 100% | 2025-08-03 Sa: 1.2 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0
P | 40000 | 40005 | AV-0550 |  | PREPURIFIER VESSEL |  |  |  |  | 13.5 | TON | 60.13 | 0 | 60.13 |  |  | 60.13 | 0 | 100%
D | 40000 | 40005 | AV-0550 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 6 | 0 | 6 | 1 | 0 | 6 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40005 | AV-0550 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 8 | EA | 16 | 0 | 16 | 8 | 0 | 16 | 0 | 100% | 2025-07-27 Sa: 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
D | 40000 | 40005 | AV-0550 |  | SHIM |  |  |  |  | 8 | EA | 20 | 0 | 20 | 8 | 0 | 20 | 0 | 100% | 2025-07-06 W: 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40005 | AV-0550 |  | SECURE |  |  |  |  | 8 | EA | 8 | 0 | 8 | 8 | 0 | 8 | 0 | 100% | 2025-07-13 Tu: 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40005 | AV-0550 |  | CLEAN UP |  |  |  |  | 13.5 | TON | 10.13 | 0 | 10.13 | 13.5 | 0 | 10.13 | 0 | 100% | 2025-07-13 F: 13.5 | 0 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10.13 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40006 | AV-0560 |  | PREPURIFIER VESSEL |  |  |  |  | 13.5 | TON | 60.13 | 0 | 60.13 |  |  | 60.13 | 0 | 100%
D | 40000 | 40006 | AV-0560 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 6 | 0 | 6 | 1 | 0 | 6 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40006 | AV-0560 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 8 | EA | 16 | 0 | 16 | 8 | 0 | 16 | 0 | 100% | 2025-07-27 Sa: 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
D | 40000 | 40006 | AV-0560 |  | SHIM |  |  |  |  | 8 | EA | 20 | 0 | 20 | 8 | 0 | 20 | 0 | 100% | 2025-07-06 W: 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40006 | AV-0560 |  | SECURE |  |  |  |  | 8 | EA | 8 | 0 | 8 | 8 | 0 | 8 | 0 | 100% | 2025-07-13 Tu: 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40006 | AV-0560 |  | CLEAN UP |  |  |  |  | 13.5 | TON | 10.13 | 0 | 10.13 | 13.5 | 0 | 10.13 | 0 | 100% | 2025-07-13 F: 5; 2025-08-03 Sa: 8.5 | 0 | 5 | 0 | 0 | 8.5 | 0 | 0 | 0 | 3.7519 | 0 | 0 | 6.3781 | 0 | 0
P | 40000 | 40007 | AS-0560 |  | BLOWDOWN SILENCER | (REV #1) |  |  |  | 1.5 | TON | 24.13 | 0 | 24.13 |  |  | 24.13 | 0 | 100%
D | 40000 | 40007 | AS-0560 |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40007 | AS-0560 |  | SHIM | (REV #1) |  |  |  | 2 | EA | 3 | 0 | 3 | 2 | 0 | 3 | 0 | 100% | 2025-07-06 W: 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40007 | AS-0560 |  | SECURE | (REV #1) |  |  |  | 2 | EA | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 100% | 2025-07-20 F: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
D | 40000 | 40007 | AS-0560 |  | INSTALL HANGERS, STRUCTURAL STEEL | (REV #1) |  |  |  | 0.5 | TON | 10 | 0 | 10 | 0.5 | 0 | 10 | 0 | 100% | 2025-07-13 Sa: 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40007 | AS-0560 |  | CLEAN UP | (REV #1) |  |  |  | 1.5 | TON | 1.13 | 0 | 1.13 | 1.5 | 0 | 1.13 | 0 | 100% | 2025-08-03 Sa: 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.13 | 0 | 0
D | 40000 | 40007 | AS-0560 |  | INSTALL DRAIN MUFFLER ASSEMBLY | (REV #1) |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | bar: 2025-08-03 Sa
P | 40000 | 40008 | RP-0830 |  | GLYCOL PUMP SKID |  |  |  |  | 5 | TON | 46.75 | 4 | 50.75 |  |  | 50.75 | 0 | 100%
D | 40000 | 40008 | RP-0830 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40008 | RP-0830 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 16 | 0 | 16 | 4 | 0 | 16 | 0 | 100% | 2025-07-13 Sa: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40008 | RP-0830 |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 W: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40008 | RP-0830 |  | SECURE |  |  |  |  | 4 | EA | 8 | 4 | 12 | 4 | 0 | 12 | 0 | 100% | WE M: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40008 | RP-0830 |  | PRECISION ALIGNMENT |  |  |  |  | 1 | EA | 3 | 0 | 3 | 1 | 0 | 3 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | bar: 2025-07-27 Sa
D | 40000 | 40008 | RP-0830 |  | LUBRICATION |  |  |  |  | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | bar: 2025-07-27 Sa
D | 40000 | 40008 | RP-0830 |  | WEEKLY ROTATION |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-27 Sa: 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
D | 40000 | 40008 | RP-0830 |  | CLEAN UP |  |  |  |  | 5 | TON | 3.75 | 0 | 3.75 | 5 | 0 | 3.75 | 0 | 100% | 2025-08-03 Sa: 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 0 | 0
P | 40000 | 40009 | AF-0500 |  | AIR SUCTION FILTER HOUSE | (REV #1) |  |  |  | 0.25 | TON | 42.19 | 0 | 42.19 |  |  | 42 | 0.19 | 99.55%
D | 40000 | 40009 | AF-0500 |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40009 | AF-0500 |  | INSTALL ANCHOR BOLTS | (REV #1) |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-27 Sa: 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
D | 40000 | 40009 | AF-0500 |  | SHIM | (REV #1) |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 Th: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40009 | AF-0500 |  | SECURE | (REV #1) |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 F: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40009 | AF-0500 |  | ASSEMBLE COMPONENTS | (REV #1) |  |  |  | 2 | EA | 20 | 0 | 20 | 2 | 0 | 20 | 0 | 100% | 2025-07-13 F: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40009 | AF-0500 |  | CLEAN UP | (REV #1) |  |  |  | 0.25 | TON | 0.19 | 0 | 0.19 | 0 | 0.25 | 0 | 0.19 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40010 | AS-0500 |  | MAC VENT SILENCER |  |  |  |  | 1.5 | TON | 10.13 | 0 | 10.13 |  |  | 10.13 | 0 | 100%
D | 40000 | 40010 | AS-0500 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Th
D | 40000 | 40010 | AS-0500 |  | SHIM |  |  |  |  | 2 | EA | 3 | 0 | 3 | 2 | 0 | 3 | 0 | 100% | 2025-07-06 Th: 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40010 | AS-0500 |  | SECURE |  |  |  |  | 2 | EA | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 100% | 2025-07-13 F: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40010 | AS-0500 |  | CLEAN UP |  |  |  |  | 1.5 | TON | 1.13 | 0 | 1.13 | 1.5 | 0 | 1.13 | 0 | 100% | 2025-07-13 F: 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.13 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40011 | TO-0803 |  | GLYCOL EXPANSION TANK |  |  |  |  | 2.5 | TON | 31.88 | 0 | 31.88 |  |  | 31.88 | 0 | 100%
D | 40000 | 40011 | TO-0803 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40011 | TO-0803 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 16 | 0 | 16 | 4 | 0 | 16 | 0 | 100% | 2025-07-13 W: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40011 | TO-0803 |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 Th: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40011 | TO-0803 |  | SECURE |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 W: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40011 | TO-0803 |  | CLEAN UP |  |  |  |  | 2.5 | TON | 1.88 | 0 | 1.88 | 2.5 | 0 | 1.88 | 0 | 100% | 2025-07-13 F: 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40012 | HO-0801 |  | FIN FAN COOLER (MAC/BNC) | (REV #1) |  |  |  | 13.5 | TON | 157.13 | 0 | 157.13 |  |  | 157.13 | 0 | 100%
D | 40000 | 40012 | HO-0801 |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 6 | 0 | 6 | 1 | 0 | 6 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 Tu
D | 40000 | 40012 | HO-0801 |  | INSTALL ANCHOR BOLTS | (REV #1) |  |  |  | 32 | EA | 64 | 0 | 64 | 32 | 0 | 64 | 0 | 100% | 2025-07-13 Sa: 32 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40012 | HO-0801 |  | SHIM | (REV #1) |  |  |  | 8 | EA | 20 | 0 | 20 | 8 | 0 | 20 | 0 | 100% | 2025-07-06 Th: 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40012 | HO-0801 |  | SECURE | (REV #1) |  |  |  | 32 | EA | 32 | 0 | 32 | 32 | 0 | 32 | 0 | 100% | 2025-07-13 Tu: 32 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40012 | HO-0801 |  | INSTALL HANGERS, STRUCTURAL STEEL | (REV #1) |  |  |  | 1 | TON | 25 | 0 | 25 | 1 | 0 | 25 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 W
D | 40000 | 40012 | HO-0801 |  | CLEAN UP | (REV #1) |  |  |  | 13.5 | TON | 10.13 | 0 | 10.13 | 13.5 | 0 | 10.13 | 0 | 100% | 2025-07-13 F: 13.5 | 0 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10.13 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40013 | RC-0205 |  | TURBINE DUCT |  |  |  |  | 10 | TON | 131.5 | 12 | 143.5 |  |  | 123.5 | 20 | 86.06%
D | 40000 | 40013 | RC-0205 |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40013 | RC-0205 |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-13 Sa: 2; WE M: 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 Th: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | SECURE |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 Sa: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | CLEAN UP |  |  |  |  | 10 | TON | 7.5 | 0 | 7.5 | 10 | 0 | 7.5 | 0 | 100% | 2025-07-20 Tu: 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | REMOVE SHIPPING SUPPORTS |  |  |  |  | 2 | LOT | 8 | 0 | 8 | 2 | 0 | 8 | 0 | 100% | 2025-07-13 Sa: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | REMOVE SHIPPING SECURING DEVICE FROM MANWAY |  |  |  |  | 1 | LOT | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 W
D | 40000 | 40013 | RC-0205 |  | SHIP LOOSE TURBINE INSTALL |  |  |  |  | 1 | LOT | 30 | 0 | 30 | 0.5 | 0.5 | 15 | 15 | 50% | 2025-07-13 Sa: 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | INSTALL AF-200 AIR FILTER |  |  |  |  | 1 | LOT | 10 | 0 | 10 | 0.5 | 0.5 | 5 | 5 | 50% | 2025-07-13 Sa: 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | REMOVE SHIPPING WEDGES |  |  |  |  | 4 | EA | 12 | 12 | 24 | 4 | 0 | 24 | 0 | 100% | WE M: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | 6 - INSTALL EXPANSION JOINT |  |  |  |  | 2 | EA | 20 | 0 | 20 | 2 | 0 | 20 | 0 | 100% | 2025-07-13 W: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | 4 - INSTALL EXPANSION JOINT |  |  |  |  | 2 | EA | 16 | 0 | 16 | 2 | 0 | 16 | 0 | 100% | 2025-07-13 W: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40013 | RC-0205 |  | INSTALL ANCHOR CHAIR SPACERS |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 Sa: 2; WE M: 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
P | 40000 | 40014 |  |  | STORAGE UNIT |  |  |  |  | 4 | TON | 7 | 0 | 7 |  |  | 7 | 0 | 100%
D | 40000 | 40014 |  |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40014 |  |  | CLEAN UP |  |  |  |  | 4 | TON | 3 | 0 | 3 | 4 | 0 | 3 | 0 | 100% | 2025-07-13 Tu: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40015 |  |  | CONTROL ROOM | (REV #1) |  |  |  | 21.5 | TON | 20.13 | 0 | 20.13 |  |  | 20.13 | 0 | 100%
D | 40000 | 40015 |  |  | LAYOUT / VERIFY | (REV #1) |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40015 |  |  | CLEAN UP | (REV #1) |  |  |  | 21.5 | TON | 16.13 | 0 | 16.13 | 21.5 | 0 | 16.13 | 0 | 100% | 2025-07-13 Tu: 15; 2025-07-13 W: 6; WE M: 0.5 | 0 | 21 | 0.5 | 0 | 0 | 0 | 0 | 0 | 15.7549 | 0.37512 | 0 | 0 | 0 | 0
P | 40000 | 40016 |  |  | TRANSFORMER |  |  |  |  | 5.8 | TON | 26.35 | 0 | 26.35 |  |  | 26.35 | 0 | 100%
D | 40000 | 40016 |  |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40016 |  |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | 2025-07-13 W: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40016 |  |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 Th: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40016 |  |  | SECURE |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 W: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40016 |  |  | CLEAN UP |  |  |  |  | 5.8 | TON | 4.35 | 0 | 4.35 | 5.8 | 0 | 4.35 | 0 | 100% | 2025-07-20 Tu: 5.8 | 0 | 0 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35 | 0 | 0 | 0 | 0
P | 40000 | 40017 |  |  | SWITCHGEAR |  |  |  |  | 4 | TON | 25 | 0 | 25 |  |  | 25 | 0 | 100%
D | 40000 | 40017 |  |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40017 |  |  | INSTALL ANCHOR BOLTS |  |  |  |  | 4 | EA | 8 | 0 | 8 | 4 | 0 | 8 | 0 | 100% | WE M: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
D | 40000 | 40017 |  |  | SHIM |  |  |  |  | 4 | EA | 6 | 0 | 6 | 4 | 0 | 6 | 0 | 100% | 2025-07-06 Th: 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40017 |  |  | SECURE |  |  |  |  | 4 | EA | 4 | 0 | 4 | 4 | 0 | 4 | 0 | 100% | 2025-07-13 Tu: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 40000 | 40017 |  |  | CLEAN UP |  |  |  |  | 4 | TON | 3 | 0 | 3 | 4 | 0 | 3 | 0 | 100% | 2025-07-20 Tu: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
P | 40000 | 40018 |  |  | MCC ROOM |  |  |  |  | 10 | TON | 11.5 | 0 | 11.5 |  |  | 11.5 | 0 | 100%
D | 40000 | 40018 |  |  | LAYOUT / VERIFY |  |  |  |  | 1 | EA | 4 | 0 | 4 | 1 | 0 | 4 | 0 | 100% | [42 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-06 W
D | 40000 | 40018 |  |  | CLEAN UP |  |  |  |  | 10 | TON | 7.5 | 0 | 7.5 | 10 | 0 | 7.5 | 0 | 100% | 2025-07-13 Th: 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0
P | 40000 | 40019 |  |  | Uncrate Offload Receive | [6 empty] | 40 | 0 | 40 |  |  | 40 | 0 | 100%
D | 40000 | 40019 |  |  | Uncrate Offload Receive - 2 days |  |  |  |  | 4 |  | 40 | 0 | 40 | 4 | 0 | 40 | 0 | 100% | WE M: 1; 2025-07-13 Tu: 1; 2025-07-13 Th: 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0
W | 60000 | WBS |  |  | STRUCTURAL | [6 empty] | 127.5 | 0 | 127.5 |  |  | 127.5 | 0 | 100%
P | 60000 | 60001 |  |  | FPS-01A | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60001 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 W
D | 60000 | 60001 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60002 |  |  | FPS-01B | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60002 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60002 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60003 |  |  | FPS-02 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60003 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60003 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60004 |  |  | FPS-03 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60004 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60004 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60005 |  |  | FPS-04 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60005 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60005 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60006 |  |  | FPS-05 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60006 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60006 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60007 |  |  | FPS-06 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60007 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60007 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60008 |  |  | FPS-07 | [6 empty] | 7.5 | 0 | 7.5 |  |  | 7.5 | 0 | 100%
D | 60000 | 60008 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 1 | EA | 6.5 | 0 | 6.5 | 1 | 0 | 6.5 | 0 | 100% | [42 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th
D | 60000 | 60008 |  |  | INSTALL ANCHORS |  |  |  |  | 4 | EA | 1 | 0 | 1 | 4 | 0 | 1 | 0 | 100% | 2025-07-13 Th: 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60009 |  |  | FPS-08 | [6 empty] | 15 | 0 | 15 |  |  | 15 | 0 | 100%
D | 60000 | 60009 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 2 | EA | 13 | 0 | 13 | 2 | 0 | 13 | 0 | 100% | [42 empty] | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th; 2025-07-13 Sa
D | 60000 | 60009 |  |  | INSTALL ANCHORS |  |  |  |  | 8 | EA | 2 | 0 | 2 | 8 | 0 | 2 | 0 | 100% | 2025-07-13 Th: 4; 2025-07-13 Sa: 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60010 |  |  | FPS-09 | [6 empty] | 15 | 0 | 15 |  |  | 15 | 0 | 100%
D | 60000 | 60010 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 2 | EA | 13 | 0 | 13 | 2 | 0 | 13 | 0 | 100% | 2025-07-13 F: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0
D | 60000 | 60010 |  |  | INSTALL ANCHORS |  |  |  |  | 8 | EA | 2 | 0 | 2 | 8 | 0 | 2 | 0 | 100% | 2025-07-13 F: 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
P | 60000 | 60011 |  |  | FPS-10 | [6 empty] | 37.5 | 0 | 37.5 |  |  | 37.5 | 0 | 100%
D | 60000 | 60011 |  |  | FIELD SUPPORT - POST (≤10) |  |  |  |  | 5 | EA | 32.5 | 0 | 32.5 | 5 | 0 | 32.5 | 0 | 100% | 2025-07-13 F: 1; 2025-07-13 Sa: 2; 2025-07-20 Th: 2 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 19.5 | 13 | 0 | 0 | 0 | 0
D | 60000 | 60011 |  |  | INSTALL ANCHORS |  |  |  |  | 20 | EA | 5 | 0 | 5 | 20 | 0 | 5 | 0 | 100% | 2025-07-13 F: 4; 2025-07-13 Sa: 8; 2025-07-20 Th: 8 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
W | 70000 | WBS |  |  | AG PIPING | [6 empty] | 836.5 | 241.57 | 1078.07 |  |  | 783.205 | 294.865 | 72.65%
P | 70000 | 70001 |  |  | AGL0500A | CS150B |  |  | (REV #1) | 9 | LF | 25.49 | 0 | 25.49 |  |  | 25.49 | 0 | 100%
D | 70000 | 70001 |  |  | HE - 14 | CS150B |  |  | (REV #1) | 3 | LF | 1.92 | 0 | 1.92 | 3 | 0 | 1.92 | 0 | 100% | 2025-07-27 W: 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 0 | 0 | 0
D | 70000 | 70001 |  |  | HE - 12 | CS150B |  |  | (REV #1) | 6 | LF | 3.12 | 0 | 3.12 | 6 | 0 | 3.12 | 0 | 100% | 2025-07-27 W: 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3.12 | 0 | 0 | 0
D | 70000 | 70001 |  |  | V - 14 | CS150B |  |  | (REV #1) | 1 | EA | 5 | 0 | 5 | 1 | 0 | 5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | bar: 2025-07-27 W
D | 70000 | 70001 |  |  | BU - 14 (REV1) | CS150B |  |  | (REV #1) | 1 | EA | 3.75 | 0 | 3.75 | 1 | 0 | 3.75 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 0 | 0 | 0 | bar: 2025-07-27 W
D | 70000 | 70001 |  |  | BU - 12 | CS150B |  |  | (REV #1) | 1 | EA | 3.5 | 0 | 3.5 | 1 | 0 | 3.5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | bar: 2025-07-27 W
D | 70000 | 70001 |  |  | THRD - ≤.75 | CS150B |  |  | (REV #1) | 1 | EA | 0.2 | 0 | 0.2 | 1 | 0 | 0.2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | bar: 2025-07-27 W
D | 70000 | 70001 |  |  | UBOLT - 12-18 | CS150B |  |  | (REV #1) | 2 | EA | 8 | 0 | 8 | 2 | 0 | 8 | 0 | 100% | 2025-07-27 W: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
P | 70000 | 70002 |  |  | AGM0500A | CS150B |  |  |  | 16 | LF | 15.33 | 2.65 | 17.98 |  |  | 17.98 | 0 | 100%
D | 70000 | 70002 |  |  | HE - 6 | CS150B |  |  |  | 1 | LF | 0.28 | 0 | 0.28 | 1 | 0 | 0.28 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70002 |  |  | HE - 4 | CS150B |  |  |  | 15 | LF | 3.75 | 0 | 3.75 | 15 | 0 | 3.75 | 0 | 100% | 2025-07-20 Sa: 10; WE M: 2.5; 2025-07-27 Sa: 2.5 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 0 | 0
D | 70000 | 70002 |  |  | FW - 4 | CS150B |  |  |  | 1 | EA | 2.3 | 2.65 | 4.95 | 1 | 0 | 4.95 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4.95 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70002 |  |  | V - 4 | CS150B |  |  |  | 1 | EA | 1.75 | 0 | 1.75 | 1 | 0 | 1.75 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70002 |  |  | BU - 6 | CS150B |  |  |  | 1 | EA | 1.5 | 0 | 1.5 | 1 | 0 | 1.5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70002 |  |  | BU - 4 | CS150B |  |  |  | 3 | EA | 3.75 | 0 | 3.75 | 3 | 0 | 3.75 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1.25 | 1.25 | 1.25 | 0 | 0 | bar: 2025-07-20 Sa to WE M; 2025-08-03 Sa
D | 70000 | 70002 |  |  | UBOLT - ≤4 | CS150B |  |  |  | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | bar: 2025-08-03 Sa
P | 70000 | 70003 |  |  | AGV0500A | CS150B |  |  |  | 7 | LF | 9.11 | 4.37 | 13.48 |  |  | 13.48 | 0 | 100%
D | 70000 | 70003 |  |  | HE - 3 | CS150B |  |  |  | 7 | LF | 1.61 | 0 | 1.61 | 7 | 0 | 1.61 | 0 | 100% | 2025-07-27 Th: 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1.61 | 0 | 0 | 0
D | 70000 | 70003 |  |  | FW - 6 | CS150B |  |  |  | 1 | EA | 5 | 4.37 | 9.37 | 1 | 0 | 9.37 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9.37 | 0 | 0 | 0 | bar: 2025-07-27 Th
D | 70000 | 70003 |  |  | BU - 6 | CS150B |  |  |  | 1 | EA | 1.5 | 0 | 1.5 | 1 | 0 | 1.5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | bar: 2025-07-27 Th
D | 70000 | 70003 |  |  | BU - 3 | CS150B |  |  |  | 1 | EA | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | bar: 2025-07-27 Sa
P | 70000 | 70004 |  |  | GWF0830B | CS150B |  |  |  | 36 | LF | 18.55 | 2.3 | 20.85 |  |  | 20.85 | 0 | 100%
D | 70000 | 70004 |  |  | HE - 4 | CS150B |  |  |  | 1 | LF | 0.25 | 0 | 0.25 | 1 | 0 | 0.25 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | bar: 2025-07-27 Sa
D | 70000 | 70004 |  |  | HE - 3 | CS150B |  |  |  | 35 | LF | 8.05 | 0 | 8.05 | 35 | 0 | 8.05 | 0 | 100% | 2025-07-27 Sa: 30; 2025-08-03 Th: 5 | 0 | 0 | 0 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 6.9 | 1.15 | 0 | 0
D | 70000 | 70004 |  |  | FW - 3 | CS150B |  |  |  | 1 | EA | 2 | 2.3 | 4.3 | 1 | 0 | 4.3 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2.15 | 2.15 | 0 | 0
D | 70000 | 70004 |  |  | BU - 4 | CS150B |  |  |  | 1 | EA | 1.25 | 0 | 1.25 | 1 | 0 | 1.25 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.625 | 0.625 | 0 | 0
D | 70000 | 70004 |  |  | BU - 3 | CS150B |  |  |  | 1 | EA | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0
D | 70000 | 70004 |  |  | UBOLT - ≤4 | CS150B |  |  |  | 3 | EA | 6 | 0 | 6 | 3 | 0 | 6 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Th: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0
P | 70000 | 70005 |  |  | GWR0500-001 | CS150B |  |  |  | 3 | LF | 6.25 | 0 | 6.25 |  |  | 6.25 | 0 | 100%
D | 70000 | 70005 |  |  | HE - 4 | CS150B |  |  |  | 3 | LF | 0.75 | 0 | 0.75 | 3 | 0 | 0.75 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Sa: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.25 | 0 | 0
D | 70000 | 70005 |  |  | V - 4 | CS150B |  |  |  | 1 | EA | 1.75 | 0 | 1.75 | 1 | 0 | 1.75 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Sa: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.875 | 0.875 | 0 | 0
D | 70000 | 70005 |  |  | BU - 4 | CS150B |  |  |  | 3 | EA | 3.75 | 0 | 3.75 | 3 | 0 | 3.75 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Sa: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 0
P | 70000 | 70006 |  |  | GWR0500-002 | CS150B |  |  |  | 32 | LF | 21.4 | 2.65 | 24.05 |  |  | 16.875 | 7.175 | 70.17%
D | 70000 | 70006 |  |  | HE - 4 | CS150B |  |  |  | 32 | LF | 8 | 0 | 8 | 30 | 2 | 7.5 | 0.5 | 93.75% | 2025-07-27 Sa: 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0
D | 70000 | 70006 |  |  | FW - 4 | CS150B |  |  |  | 1 | EA | 2.3 | 2.65 | 4.95 | 0.5 | 0.5 | 2.475 | 2.475 | 50% | 2025-07-27 Sa: 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2.475 | 0 | 0 | 0
D | 70000 | 70006 |  |  | V - 4 | CS150B |  |  |  | 1 | EA | 1.75 | 0 | 1.75 | 0.5 | 0.5 | 0.875 | 0.875 | 50% | 2025-07-27 Sa: 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.875 | 0 | 0 | 0
D | 70000 | 70006 |  |  | V - ≤2 | CS150B |  |  |  | 3 | EA | 1.5 | 0 | 1.5 | 2 | 1 | 1 | 0.5 | 66.67% | 2025-07-27 Sa: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
D | 70000 | 70006 |  |  | BU - 4 | CS150B |  |  |  | 1 | EA | 1.25 | 0 | 1.25 | 0.5 | 0.5 | 0.625 | 0.625 | 50% | 2025-07-27 Sa: 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.625 | 0 | 0 | 0
D | 70000 | 70006 |  |  | THRD - ≤.75 | CS150B |  |  |  | 3 | EA | 0.6 | 0 | 0.6 | 2 | 1 | 0.4 | 0.2 | 66.67% | 2025-07-27 Sa: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0
D | 70000 | 70006 |  |  | UBOLT - ≤4 | CS150B |  |  |  | 3 | EA | 6 | 0 | 6 | 2 | 1 | 4 | 2 | 66.67% | 2025-07-27 Sa: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
P | 70000 | 70007 |  |  | GWR0500-003 | CS150B |  |  |  | 15 | LF | 11.65 | 2.65 | 14.3 |  |  | 14.3 | 0 | 100%
D | 70000 | 70007 |  |  | HE - 4 | CS150B |  |  |  | 15 | LF | 3.75 | 0 | 3.75 | 15 | 0 | 3.75 | 0 | 100% | 2025-07-27 Sa: 10; 2025-08-03 Th: 5 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 0
D | 70000 | 70007 |  |  | FW - 4 | CS150B |  |  |  | 1 | EA | 2.3 | 2.65 | 4.95 | 1 | 0 | 4.95 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2.475 | 2.475 | 0 | 0
D | 70000 | 70007 |  |  | V - ≤2 | CS150B |  |  |  | 1 | EA | 0.5 | 0 | 0.5 | 1 | 0 | 0.5 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0 | 0
D | 70000 | 70007 |  |  | BU - 4 | CS150B |  |  |  | 2 | EA | 2.5 | 0 | 2.5 | 2 | 0 | 2.5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1.25 | 1.25 | 0 | 0 | bar: 2025-07-27 Sa; 2025-08-03 Th
D | 70000 | 70007 |  |  | THRD - ≤.75 | CS150B |  |  |  | 3 | EA | 0.6 | 0 | 0.6 | 3 | 0 | 0.6 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Th: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.2 | 0 | 0
D | 70000 | 70007 |  |  | UBOLT - ≤4 | CS150B |  |  |  | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
P | 70000 | 70008 |  |  | GWR0801B | CS150B |  |  |  | 10 | LF | 7.35 | 0 | 7.35 |  |  | 7.35 | 0 | 100%
D | 70000 | 70008 |  |  | HE - 4 | CS150B |  |  |  | 10 | LF | 2.5 | 0 | 2.5 | 10 | 0 | 2.5 | 0 | 100% | 2025-07-27 Sa: 8; 2025-08-03 Th: 2 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0.5 | 0 | 0
D | 70000 | 70008 |  |  | V - ≤2 | CS150B |  |  |  | 1 | EA | 0.5 | 0 | 0.5 | 1 | 0 | 0.5 | 0 | 100% | 2025-07-27 Sa: 0.5; 2025-08-03 Th: 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0 | 0
D | 70000 | 70008 |  |  | BU - 4 | CS150B |  |  |  | 3 | EA | 3.75 | 0 | 3.75 | 3 | 0 | 3.75 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Th: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1.25 | 0 | 0
D | 70000 | 70008 |  |  | THRD - ≤.75 | CS150B |  |  |  | 3 | EA | 0.6 | 0 | 0.6 | 3 | 0 | 0.6 | 0 | 100% | 2025-07-27 Sa: 2; 2025-08-03 Th: 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.2 | 0 | 0
P | 70000 | 70009 |  |  | NGM0101E | SS150B |  |  | (REV #1) | 35 | LF | 23.75 | 2.75 | 26.5 |  |  | 26.5 | 0 | 100%
D | 70000 | 70009 |  |  | HE - 4 | SS150B |  |  | (REV #1) | 35 | LF | 8.75 | 0 | 8.75 | 35 | 0 | 8.75 | 0 | 100% | 2025-07-20 F: 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 0 | 0 | 0 | 0
D | 70000 | 70009 |  |  | FW - 4 | SS150B |  |  | (REV #1) | 1 | EA | 2.5 | 2.75 | 5.25 | 1 | 0 | 5.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | bar: 2025-07-20 F
D | 70000 | 70009 |  |  | V - 4 | SS150B |  |  | (REV #1) | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | bar: 2025-07-20 F
D | 70000 | 70009 |  |  | BU - 4 | SS150B |  |  | (REV #1) | 3 | EA | 4.5 | 0 | 4.5 | 3 | 0 | 4.5 | 0 | 100% | 2025-07-20 F: 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0
D | 70000 | 70009 |  |  | UBOLT - ≤4 | SS150B |  |  | (REV #1) | 3 | EA | 6 | 0 | 6 | 3 | 0 | 6 | 0 | 100% | WE M: 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
P | 70000 | 70010 |  |  | NGM0700D-001 | SS150B |  |  | (REV #1) | 105 | LF | 46.75 | 5.5 | 52.25 |  |  | 52.25 | 0 | 100%
D | 70000 | 70010 |  |  | HE - 4 | SS150B |  |  | (REV #1) | 105 | LF | 26.25 | 0 | 26.25 | 105 | 0 | 26.25 | 0 | 100% | 2025-07-13 Th: 10; 2025-07-20 Th: 75; 2025-07-20 F: 20 | 0 | 10 | 95 | 0 | 0 | 0 | 0 | 0 | 2.5 | 23.75 | 0 | 0 | 0 | 0
D | 70000 | 70010 |  |  | FW - 4 | SS150B |  |  | (REV #1) | 2 | EA | 5 | 5.5 | 10.5 | 2 | 0 | 10.5 | 0 | 100% | 2025-07-20 Th: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 0 | 0 | 0 | 0
D | 70000 | 70010 |  |  | BU - 4 | SS150B |  |  | (REV #1) | 1 | EA | 1.5 | 0 | 1.5 | 1 | 0 | 1.5 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | bar: 2025-07-20 F
D | 70000 | 70010 |  |  | UBOLT - ≤4 | SS150B |  |  | (REV #1) | 7 | EA | 14 | 0 | 14 | 7 | 0 | 14 | 0 | 100% | 2025-07-20 Th: 4; 2025-07-20 F: 2; WE M: 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 0 | 0 | 0
P | 70000 | 70011 |  |  | NGM0700D-002 | SS150B |  |  | (REV #1) | 10 | LF | 8.5 | 2.75 | 11.25 |  |  | 11.25 | 0 | 100%
D | 70000 | 70011 |  |  | HE - 4 | SS150B |  |  | (REV #1) | 10 | LF | 2.5 | 0 | 2.5 | 10 | 0 | 2.5 | 0 | 100% | 2025-07-13 Th: 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70011 |  |  | FW - 4 | SS150B |  |  | (REV #1) | 1 | EA | 2.5 | 2.75 | 5.25 | 1 | 0 | 5.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | bar: 2025-07-20 F
D | 70000 | 70011 |  |  | BU - 4 | SS150B |  |  | (REV #1) | 1 | EA | 1.5 | 0 | 1.5 | 1 | 0 | 1.5 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | bar: 2025-07-20 F
D | 70000 | 70011 |  |  | UBOLT - ≤4 | SS150B |  |  | (REV #1) | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | bar: WE M
P | 70000 | 70012 |  |  | NGM0700E | SS150B |  |  | (REV #1) | 30 | LF | 22.5 | 2.75 | 25.25 |  |  | 25.25 | 0 | 100%
D | 70000 | 70012 |  |  | HE - 4 | SS150B |  |  | (REV #1) | 30 | LF | 7.5 | 0 | 7.5 | 30 | 0 | 7.5 | 0 | 100% | 2025-07-13 Th: 10; 2025-07-20 Th: 15; WE M: 5 | 0 | 10 | 15 | 5 | 0 | 0 | 0 | 0 | 2.5 | 3.75 | 1.25 | 0 | 0 | 0
D | 70000 | 70012 |  |  | FW - 4 | SS150B |  |  | (REV #1) | 1 | EA | 2.5 | 2.75 | 5.25 | 1 | 0 | 5.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | bar: 2025-07-20 Th
D | 70000 | 70012 |  |  | V - 4 | SS150B |  |  | (REV #1) | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | bar: 2025-07-20 Th
D | 70000 | 70012 |  |  | BU - 4 | SS150B |  |  | (REV #1) | 3 | EA | 4.5 | 0 | 4.5 | 3 | 0 | 4.5 | 0 | 100% | 2025-07-20 Th: 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0
D | 70000 | 70012 |  |  | UBOLT - ≤4 | SS150B |  |  | (REV #1) | 3 | EA | 6 | 0 | 6 | 3 | 0 | 6 | 0 | 100% | 2025-07-20 Th: 2; WE M: 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0
P | 70000 | 70013 |  |  | NLM1740A-001 | SS150B | GS-115 | 8" | (REV #1) | 35 | LF | 14.55 | 0.8 | 15.35 |  |  | 15.35 | 0 | 100%
D | 70000 | 70013 |  |  | HE - ≤2 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 35 | LF | 7 | 0 | 7 | 35 | 0 | 7 | 0 | 100% | 2025-07-20 Th: 25; WE M: 10 | 0 | 0 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0
D | 70000 | 70013 |  |  | FSW - 1 | SS150B | GS-115 | 8" | (REV #1) | 1 | EA | 0.8 | 0.8 | 1.6 | 1 | 0 | 1.6 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70013 |  |  | BU - ≤2 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 1 | EA | 0.75 | 0 | 0.75 | 1 | 0 | 0.75 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70013 |  |  | UBOLT - 6-10 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 2 | EA | 6 | 0 | 6 | 2 | 0 | 6 | 0 | 100% | 2025-08-03 Th: 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
P | 70000 | 70014 |  |  | NLM1740A-002 | SS150B | GS-115 | 8" | (REV #1) | 16 | LF | 11.7 | 0.8 | 12.5 |  |  | 12.5 | 0 | 100%
D | 70000 | 70014 |  |  | HE - ≤2 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 16 | LF | 3.2 | 0 | 3.2 | 16 | 0 | 3.2 | 0 | 100% | WE M: 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0 | 0 | 0
D | 70000 | 70014 |  |  | FSW - 1 | SS150B | GS-115 | 8" | (REV #1) | 1 | EA | 0.8 | 0.8 | 1.6 | 1 | 0 | 1.6 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70014 |  |  | V - ≤2 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 3 | EA | 3 | 0 | 3 | 3 | 0 | 3 | 0 | 100% | WE M: 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
D | 70000 | 70014 |  |  | BU - ≤2 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 2 | EA | 1.5 | 0 | 1.5 | 2 | 0 | 1.5 | 0 | 100% | WE M: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
D | 70000 | 70014 |  |  | THRD - ≤.75 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 1 | EA | 0.2 | 0 | 0.2 | 1 | 0 | 0.2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70014 |  |  | UBOLT - 6-10 (REV1) | SS150B | GS-115 | 8" | (REV #1) | 1 | EA | 3 | 0 | 3 | 1 | 0 | 3 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | bar: 2025-08-03 Th
P | 70000 | 70015 |  |  | NLM1740A-003 | SS150B | GS-115 | 8" |  | 5 | LF | 7.25 | 0 | 7.25 |  |  | 7.25 | 0 | 100%
D | 70000 | 70015 |  |  | HE - ≤2 | SS150B | GS-115 | 8" |  | 5 | LF | 1 | 0 | 1 | 5 | 0 | 1 | 0 | 100% | WE M: 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
D | 70000 | 70015 |  |  | V - ≤2 | SS150B | GS-115 | 8" |  | 1 | EA | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70015 |  |  | BU - ≤2 | SS150B | GS-115 | 8" |  | 3 | EA | 2.25 | 0 | 2.25 | 3 | 0 | 2.25 | 0 | 100% | WE M: 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
D | 70000 | 70015 |  |  | UBOLT - 6-10 | SS150B | GS-115 | 8" |  | 1 | EA | 3 | 0 | 3 | 1 | 0 | 3 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | bar: 2025-08-03 Th
P | 70000 | 70016 |  |  | INNER CONNECT - VESSEL 0560 |  |  |  |  | 40 | LF | 27.85 | 0 | 27.85 |  |  | 27.65 | 0.2 | 99.28%
D | 70000 | 70016 |  |  | HE - 10 |  |  |  |  | 30 | LF | 12.9 | 0 | 12.9 | 30 | 0 | 12.9 | 0 | 100% | 2025-07-20 W: 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9 | 0 | 0 | 0 | 0
D | 70000 | 70016 |  |  | HE - ≤2 |  |  |  |  | 10 | LF | 2 | 0 | 2 | 10 | 0 | 2 | 0 | 100% | 2025-07-20 W: 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
D | 70000 | 70016 |  |  | BU - 10 |  |  |  |  | 4 | EA | 11 | 0 | 11 | 4 | 0 | 11 | 0 | 100% | 2025-07-20 W: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0
D | 70000 | 70016 |  |  | BU - ≤2 |  |  |  |  | 1 | EA | 0.75 | 0 | 0.75 | 1 | 0 | 0.75 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | bar: 2025-07-20 W
D | 70000 | 70016 |  |  | THRD - ≤.75 |  |  |  |  | 6 | EA | 1.2 | 0 | 1.2 | 5 | 1 | 1 | 0.2 | 83.33% | 2025-07-20 W: 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
P | 70000 | 70017 |  |  | INNER CONNECT - VESSEL 0550 |  |  |  |  | 40 | LF | 27.85 | 0 | 27.85 |  |  | 27.85 | 0 | 100%
D | 70000 | 70017 |  |  | HE - 10 |  |  |  |  | 30 | LF | 12.9 | 0 | 12.9 | 30 | 0 | 12.9 | 0 | 100% | 2025-07-20 W: 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9 | 0 | 0 | 0 | 0
D | 70000 | 70017 |  |  | HE - ≤2 |  |  |  |  | 10 | LF | 2 | 0 | 2 | 10 | 0 | 2 | 0 | 100% | 2025-07-20 W: 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
D | 70000 | 70017 |  |  | BU - 10 |  |  |  |  | 4 | EA | 11 | 0 | 11 | 4 | 0 | 11 | 0 | 100% | 2025-07-20 W: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0
D | 70000 | 70017 |  |  | BU - ≤2 |  |  |  |  | 1 | EA | 0.75 | 0 | 0.75 | 1 | 0 | 0.75 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | bar: 2025-07-20 W
D | 70000 | 70017 |  |  | THRD - ≤.75 |  |  |  |  | 6 | EA | 1.2 | 0 | 1.2 | 6 | 0 | 1.2 | 0 | 100% | 2025-07-20 W: 5; 2025-08-03 Th: 1 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.2 | 0 | 0
P | 70000 | 70018 |  |  | INNER CONNECT - COLD BOX |  |  |  |  | 20 | LF | 52.05 | 10.8 | 62.85 |  |  | 62.85 | 0 | 100%
D | 70000 | 70018 |  |  | HE - ≤2 |  |  |  |  | 20 | LF | 4 | 0 | 4 | 20 | 0 | 4 | 0 | 100% | 2025-07-13 Th: 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | FSW - 2 |  |  |  |  | 9 | EA | 10.8 | 10.8 | 21.6 | 9 | 0 | 21.6 | 0 | 100% | 2025-07-20 Sa: 4; 2025-07-27 Tu: 5 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 9.6 | 12 | 0 | 0 | 0
D | 70000 | 70018 |  |  | V - 10 |  |  |  |  | 4 | EA | 14 | 0 | 14 | 4 | 0 | 14 | 0 | 100% | WE M: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | V - 8 |  |  |  |  | 2 | EA | 5.5 | 0 | 5.5 | 2 | 0 | 5.5 | 0 | 100% | WE M: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | V - 6 |  |  |  |  | 1 | EA | 2.25 | 0 | 2.25 | 1 | 0 | 2.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0 | 0 | bar: WE M
D | 70000 | 70018 |  |  | BU - 10 |  |  |  |  | 2 | EA | 5.5 | 0 | 5.5 | 2 | 0 | 5.5 | 0 | 100% | WE M: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | BU - 8 |  |  |  |  | 2 | EA | 4 | 0 | 4 | 2 | 0 | 4 | 0 | 100% | WE M: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | BU - 6 |  |  |  |  | 2 | EA | 3 | 0 | 3 | 2 | 0 | 3 | 0 | 100% | WE M: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
D | 70000 | 70018 |  |  | BU - ≤2 |  |  |  |  | 4 | EA | 3 | 0 | 3 | 4 | 0 | 3 | 0 | 100% | 2025-07-20 Sa: 2; 2025-08-03 Th: 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 0 | 0
P | 70000 | 70019 |  |  | INNER CONNECT - FILTER HOUSE |  |  |  |  | 10 | LF | 12.81 | 0 | 12.81 |  |  | 12.81 | 0 | 100%
D | 70000 | 70019 |  |  | HE - 14 |  |  |  |  | 3 | LF | 1.92 | 0 | 1.92 | 3 | 0 | 1.92 | 0 | 100% | 2025-08-03 Tu: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 0 | 0
D | 70000 | 70019 |  |  | HE - 12 |  |  |  |  | 7 | LF | 3.64 | 0 | 3.64 | 7 | 0 | 3.64 | 0 | 100% | 2025-08-03 Tu: 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 3.64 | 0 | 0
D | 70000 | 70019 |  |  | BU - 14 |  |  |  |  | 1 | EA | 3.75 | 0 | 3.75 | 1 | 0 | 3.75 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 0 | 0 | bar: 2025-08-03 Tu
D | 70000 | 70019 |  |  | BU - 12 |  |  |  |  | 1 | EA | 3.5 | 0 | 3.5 | 1 | 0 | 3.5 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | bar: 2025-08-03 Tu
P | 70000 | 70020 |  |  | INNER CONNECT - AIR FILTER |  |  |  |  | 10 | LF | 8.05 | 0 | 8.05 |  |  | 8.05 | 0 | 100%
D | 70000 | 70020 |  |  | HE - 6 |  |  |  |  | 10 | LF | 2.8 | 0 | 2.8 | 10 | 0 | 2.8 | 0 | 100% | 2025-07-20 Sa: 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 0 | 0 | 0
D | 70000 | 70020 |  |  | V - 6 |  |  |  |  | 1 | EA | 2.25 | 0 | 2.25 | 1 | 0 | 2.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0 | 0 | bar: 2025-07-20 Sa
D | 70000 | 70020 |  |  | BU - 6 |  |  |  |  | 2 | EA | 3 | 0 | 3 | 2 | 0 | 3 | 0 | 100% | 2025-07-20 Sa: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
P | 70000 | 70021 |  |  | INNER CONNECT - TURBINE |  |  |  |  | 50 | LF | 51.55 | 0 | 51.55 |  |  | 30.2 | 21.35 | 58.58%
D | 70000 | 70021 |  |  | HE - 6 |  |  |  |  | 20 | LF | 5.6 | 0 | 5.6 | 15 | 5 | 4.2 | 1.4 | 75% | 2025-07-13 Th: 10; 2025-07-20 W: 5 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 2.8 | 1.4 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | HE - ≤2 |  |  |  |  | 30 | LF | 6 | 0 | 6 | 10 | 20 | 2 | 4 | 33.33% | 2025-07-13 Th: 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | V - 6 |  |  |  |  | 1 | EA | 2.25 | 0 | 2.25 | 1 | 0 | 2.25 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0 | 0 | bar: 2025-07-20 W
D | 70000 | 70021 |  |  | V - 4 |  |  |  |  | 1 | EA | 1.75 | 0 | 1.75 | 1 | 0 | 1.75 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | bar: 2025-07-20 W
D | 70000 | 70021 |  |  | V - ≤2 |  |  |  |  | 6 | EA | 3 | 0 | 3 | 0 | 6 | 0 | 3 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | BU - 6 |  |  |  |  | 5 | EA | 7.5 | 0 | 7.5 | 5 | 0 | 7.5 | 0 | 100% | 2025-07-20 W: 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | BU - 4 |  |  |  |  | 2 | EA | 2.5 | 0 | 2.5 | 2 | 0 | 2.5 | 0 | 100% | 2025-07-20 W: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | BU - ≤2 |  |  |  |  | 1 | EA | 0.75 | 0 | 0.75 | 0 | 1 | 0 | 0.75 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | THRD - ≤.75 |  |  |  |  | 61 | EA | 12.2 | 0 | 12.2 | 0 | 61 | 0 | 12.2 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 70021 |  |  | UBOLT - 6-10 |  |  |  |  | 2 | EA | 6 | 0 | 6 | 2 | 0 | 6 | 0 | 100% | [42 empty] | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | bar: 2025-07-13 Th; 2025-07-20 W
D | 70000 | 70021 |  |  | UBOLT - ≤4 |  |  |  |  | 2 | EA | 4 | 0 | 4 | 2 | 0 | 4 | 0 | 100% | 2025-07-13 Th: 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
P | 70000 | 70022 |  |  | NG0205A |  |  |  | (REV #1) | 20 | LF | 7 | 0 | 7 |  |  | 7 | 0 | 100%
D | 70000 | 70022 |  |  | HE - ≤2 |  |  |  | (REV #1) | 20 | LF | 4 | 0 | 4 | 20 | 0 | 4 | 0 | 100% | 2025-08-03 Th: 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
D | 70000 | 70022 |  |  | BU - ≤2 |  |  |  | (REV #1) | 4 | EA | 3 | 0 | 3 | 4 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
P | 70000 | 70023 |  |  | NGM0700C - PREPURIFIER SKID |  |  |  | (REV #1) | 5 | LF | 11.75 | 0 | 11.75 |  |  | 11.75 | 0 | 100%
D | 70000 | 70023 |  |  | HE - 4 |  |  |  | (REV #1) | 5 | LF | 1.25 | 0 | 1.25 | 5 | 0 | 1.25 | 0 | 100% | 2025-07-20 Sa: 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 0
D | 70000 | 70023 |  |  | V - 4 |  |  |  | (REV #1) | 2 | EA | 3.5 | 0 | 3.5 | 2 | 0 | 3.5 | 0 | 100% | 2025-07-20 Sa: 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0
D | 70000 | 70023 |  |  | BU - 4 |  |  |  | (REV #1) | 4 | EA | 5 | 0 | 5 | 4 | 0 | 5 | 0 | 100% | 2025-07-20 Sa: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
D | 70000 | 70023 |  |  | UBOLT - ≤4 |  |  |  | (REV #1) | 1 | EA | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | bar: 2025-08-03 Tu
P | 70000 | 70024 |  |  | INNER CONNECT - KLL0330B |  |  |  | (REV #1) | 15 | LF | 8 | 0 | 8 |  |  | 8 | 0 | 100%
D | 70000 | 70024 |  |  | HE - ≤2 |  |  |  | (REV #1) | 15 | LF | 3 | 0 | 3 | 15 | 0 | 3 | 0 | 100% | 2025-08-03 Tu: 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 70000 | 70024 |  |  | V - ≤2 |  |  |  | (REV #1) | 2 | EA | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 100% | 2025-08-03 Tu: 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
D | 70000 | 70024 |  |  | BU - ≤2 |  |  |  | (REV #1) | 4 | EA | 3 | 0 | 3 | 4 | 0 | 3 | 0 | 100% | 2025-08-03 Tu: 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
P | 70000 | 70025 |  |  | MAC DRAIN LINES |  |  |  | (REV #2) | 10 | LF | 5.6 | 0 | 5.6 |  |  | 5.6 | 0 | 100%
D | 70000 | 70025 |  |  | HE - ≤2 |  |  |  | (REV #2) | 10 | LF | 2.3 | 0 | 2.3 | 10 | 0 | 2.3 | 0 | 100% | 2025-07-20 W: 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 0 | 0 | 0
D | 70000 | 70025 |  |  | THRD - ≤.75 |  |  |  | (REV #2) | 6 | EA | 1.2 | 0 | 1.2 | 6 | 0 | 1.2 | 0 | 100% | 2025-07-20 W: 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0
D | 70000 | 70025 |  |  | CUT - ≤2 |  |  |  | (REV #2) | 4 | EA | 2 | 0 | 2 | 4 | 0 | 2 | 0 | 100% | 2025-07-20 W: 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
D | 70000 | 70025 |  |  | OFF - ≤2 |  |  |  | (REV #2) | 10 | LF | 0.1 | 0 | 0.1 | 10 | 0 | 0.1 | 0 | 100% | 2025-07-20 W: 9; 2025-08-03 Sa: 1 | 0 | 0 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0.09 | 0 | 0.01 | 0 | 0
P | 70000 | 70026 |  |  | KGMO33OD |  |  |  | (REV #2) | 20 | LF | 24.3 | 0.8 | 25.1 |  |  | 25.1 | 0 | 100%
D | 70000 | 70026 |  |  | HE - ≤2 |  |  |  | (REV #2) | 20 | LF | 4 | 0 | 4 | 20 | 0 | 4 | 0 | 100% | 2025-07-27 Tu: 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
D | 70000 | 70026 |  |  | FSW - 1 |  |  |  | (REV #2) | 1 | EA | 0.8 | 0.8 | 1.6 | 1 | 0 | 1.6 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | bar: 2025-07-27 Tu
D | 70000 | 70026 |  |  | V - ≤2 |  |  |  | (REV #2) | 9 | EA | 9 | 0 | 9 | 9 | 0 | 9 | 0 | 100% | 2025-07-27 Tu: 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
D | 70000 | 70026 |  |  | BU - ≤2 |  |  |  | (REV #2) | 2 | EA | 1.5 | 0 | 1.5 | 2 | 0 | 1.5 | 0 | 100% | 2025-07-27 Tu: 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
D | 70000 | 70026 |  |  | THRD - 1 |  |  |  | (REV #2) | 10 | EA | 3 | 0 | 3 | 10 | 0 | 3 | 0 | 100% | 2025-07-27 Tu: 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
D | 70000 | 70026 |  |  | UBOLT - ≤4 |  |  |  | (REV #2) | 3 | EA | 6 | 0 | 6 | 3 | 0 | 6 | 0 | 100% | 2025-07-27 Tu: 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
P | 70000 | 79989 |  |  | OFFLOAD/RECIEVE |  |  |  | (REV #1) |  |  | 96.42 | 0 | 96.42 |  |  | 96.42 | 0 | 100%
D | 70000 | 79989 |  |  | OFF - 14 |  |  |  | (REV #1) | 6 | LF | 3.12 | 0 | 3.12 | 6 | 0 | 3.12 | 0 | 100% | 2025-07-20 Sa: 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3.12 | 0 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - 12 |  |  |  | (REV #1) | 13 | LF | 5.2 | 0 | 5.2 | 13 | 0 | 5.2 | 0 | 100% | 2025-07-20 Sa: 13 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - 10 |  |  |  | (REV #1) | 60 | LF | 18 | 0 | 18 | 60 | 0 | 18 | 0 | 100% | 2025-07-20 Sa: 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - 6 |  |  |  | (REV #1) | 31 | LF | 6.2 | 0 | 6.2 | 31 | 0 | 6.2 | 0 | 100% | 2025-07-20 Sa: 31 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - 4 |  |  |  | (REV #1) | 261 | LF | 41.76 | 0 | 41.76 | 261 | 0 | 41.76 | 0 | 100% | 2025-07-13 Tu: 200; 2025-07-20 W: 50; 2025-07-27 Tu: 11 | 0 | 200 | 50 | 11 | 0 | 0 | 0 | 0 | 32 | 8 | 1.76 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - 3 |  |  |  | (REV #1) | 42 | LF | 5.04 | 0 | 5.04 | 42 | 0 | 5.04 | 0 | 100% | 2025-07-20 W: 10; 2025-07-27 Tu: 32 | 0 | 0 | 10 | 32 | 0 | 0 | 0 | 0 | 0 | 1.2 | 3.84 | 0 | 0 | 0
D | 70000 | 79989 |  |  | OFF - ≤2 |  |  |  | (REV #1) | 171 | LF | 17.1 | 0 | 17.1 | 171 | 0 | 17.1 | 0 | 100% | 2025-07-13 Tu: 100; 2025-07-20 W: 9; 2025-07-27 Tu: 62 | 0 | 100 | 9 | 62 | 0 | 0 | 0 | 0 | 10 | 0.9 | 6.2 | 0 | 0 | 0
P | 70000 | 79995 |  |  | ADDITIONAL HOURS | [6 empty] | 0 | 200 | 200 |  |  | 30 | 170 | 15%
D | 70000 | 79995 |  |  | 1 WELD - 5 WEEKS |  |  |  |  | 1 |  | 0 | 200 | 200 | 0.15 | 0.85 | 30 | 170 | 15% | 2025-07-20 Tu: 0.05; 2025-07-20 W: 0.05; 2025-08-03 Tu: 0.05 | 0 | 0 | 0.1 | 0 | 0.05 | 0 | 0 | 0 | 0 | 20 | 0 | 10 | 0 | 0
P | 70000 | 79996 |  |  | TORQUE VERIFICATION |  |  |  | (REV #1) |  |  | 67 | 0 | 67 |  |  | 47 | 20 | 70.15%
D | 70000 | 79996 |  |  | BOLT UPS |  |  |  | (REV #1) | 67 | EA | 67 | 0 | 67 | 47 | 20 | 47 | 20 | 70.15% | 2025-07-20 F: 1; 2025-07-27 Sa: 10; 2025-08-03 Sa: 36 | 0 | 0 | 1 | 10 | 36 | 0 | 0 | 0 | 0 | 1 | 10 | 36 | 0 | 0
P | 70000 | 79997 |  |  | PNEUMATIC TESTING |  |  |  | (REV #1) |  |  | 97.14 | 0 | 97.14 |  |  | 21 | 76.14 | 21.62%
D | 70000 | 79997 |  |  | PNEU - 14 |  |  |  | (REV #1) | 6 | LF | 2.1 | 0 | 2.1 | 6 | 0 | 2.1 | 0 | 100% | 2025-08-03 Sa: 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - 12 |  |  |  | (REV #1) | 13 | LF | 3.9 | 0 | 3.9 | 13 | 0 | 3.9 | 0 | 100% | 2025-08-03 Sa: 13 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - 10 |  |  |  | (REV #1) | 60 | LF | 15 | 0 | 15 | 60 | 0 | 15 | 0 | 100% | 2025-08-03 Sa: 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - 6 |  |  |  | (REV #1) | 31 | LF | 5.58 | 0 | 5.58 | 0 | 31 | 0 | 5.58 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - 4 |  |  |  | (REV #1) | 261 | LF | 41.76 | 0 | 41.76 | 0 | 261 | 0 | 41.76 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - 3 |  |  |  | (REV #1) | 42 | LF | 5.88 | 0 | 5.88 | 0 | 42 | 0 | 5.88 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 70000 | 79997 |  |  | PNEU - ≤2 |  |  |  | (REV #1) | 191 | LF | 22.92 | 0 | 22.92 | 0 | 191 | 0 | 22.92 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P | 70000 | 79998 |  |  | O2 CLEANING |  |  |  | (REV #1) |  |  | 89 | 0 | 89 |  |  | 89 | 0 | 100%
D | 70000 | 79998 |  |  | WELDS |  |  |  | (REV #1) | 22 | EA | 22 | 0 | 22 | 22 | 0 | 22 | 0 | 100% | 2025-07-20 F: 10; 2025-07-27 Sa: 5; 2025-08-03 Tu: 7 | 0 | 0 | 10 | 5 | 7 | 0 | 0 | 0 | 0 | 10 | 5 | 7 | 0 | 0
D | 70000 | 79998 |  |  | BOLTUPS |  |  |  | (REV #1) | 67 | EA | 67 | 0 | 67 | 67 | 0 | 67 | 0 | 100% | 2025-07-27 Sa: 30; 2025-08-03 Tu: 15; 2025-08-03 Th: 22 | 0 | 0 | 0 | 30 | 37 | 0 | 0 | 0 | 0 | 0 | 30 | 37 | 0 | 0
W | 90000 | WBS |  |  | INSTRUMENTS | [6 empty] | 222.35 | 20.1 | 242.45 |  |  | 210.55 | 31.9 | 86.84%
P | 90000 | 90001 |  |  | COLD BOX BULKHEAED PLATE TO SKID BULKHEAD PLATE |  |  |  | (REV #1) |  |  | 52.85 | 0 | 52.85 |  |  | 52.85 | 0 | 100%
D | 90000 | 90001 |  |  | TYPE M / L / K .028 - .049 WALL - 1/4 (CU) |  |  |  | (REV #1) | 140 | LF | 33.6 | 0 | 33.6 | 140 | 0 | 33.6 | 0 | 100% | WE M: 20; 2025-08-03 Tu: 80; 2025-08-03 W: 30; 2025-08-03 F: 10 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 33.6 | 0 | 0
D | 90000 | 90001 |  |  | INSTALL CONNECTIONS |  |  |  | (REV #1) | 14 | EA | 14 | 0 | 14 | 14 | 0 | 14 | 0 | 100% | 2025-08-03 Tu: 12; 2025-08-03 W: 2 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0
D | 90000 | 90001 |  |  | INSTALL MS-01-109 |  |  |  | (REV #1) | 35 | EA | 5.25 | 0 | 5.25 | 35 | 0 | 5.25 | 0 | 100% | 2025-08-03 Tu: 30; 2025-08-03 W: 5 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 0 | 0
P | 90000 | 90002 |  |  | G4 TO G INSTRUMENT LINE |  |  |  | (REV #1) |  |  | 12.7 | 0 | 12.7 |  |  | 12.7 | 0 | 100%
D | 90000 | 90002 |  |  | HE - ≤2 |  |  |  | (REV #1) | 10 | LF | 2 | 0 | 2 | 10 | 0 | 2 | 0 | 100% | 2025-08-03 Th: 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
D | 90000 | 90002 |  |  | BU - ≤2 |  |  |  | (REV #1) | 3 | EA | 2.25 | 0 | 2.25 | 3 | 0 | 2.25 | 0 | 100% | 2025-08-03 Th: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0
D | 90000 | 90002 |  |  | OFF - ≤2 |  |  |  | (REV #1) | 10 | LF | 1 | 0 | 1 | 10 | 0 | 1 | 0 | 100% | 2025-08-03 Th: 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
D | 90000 | 90002 |  |  | TORQUE BOLT UPS |  |  |  | (REV #1) | 3 | EA | 3 | 0 | 3 | 3 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 90000 | 90002 |  |  | PNEU - ≤2 |  |  |  | (REV #1) | 10 | LF | 1.2 | 0 | 1.2 | 10 | 0 | 1.2 | 0 | 100% | 2025-08-03 Th: 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0
D | 90000 | 90002 |  |  | O2 CLEANING BOLTUPS |  |  |  | (REV #1) | 3 | EA | 3 | 0 | 3 | 3 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 90000 | 90002 |  |  | V - ≤2 |  |  |  | (REV #1) | 1 | EA | 0.25 | 0 | 0.25 | 1 | 0 | 0.25 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | bar: 2025-08-03 F
P | 90000 | 90003 |  |  | TURBINE DUCT TUBING |  |  |  | (REV #1) |  |  | 60.2 | 1.5 | 61.7 |  |  | 29.8 | 31.9 | 48.3%
D | 90000 | 90003 |  |  | TYPE M / L / K .028 - .049 WALL - 1/4 (CU) |  |  |  | (REV #1) | 15 | LF | 3.6 | 0 | 3.6 | 5 | 10 | 1.2 | 2.4 | 33.33% | 2025-08-03 Sa: 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0
D | 90000 | 90003 |  |  | TYPE M / L / K .028 - .049 WALL - 3/8 (CU) |  |  |  | (REV #1) | 40 | LF | 12 | 0 | 12 | 10 | 30 | 3 | 9 | 25% | 2025-08-03 Sa: 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 90000 | 90003 |  |  | TYPE M / L / K .028 - .049 WALL - 1/2 (CU) |  |  |  | (REV #1) | 20 | LF | 7 | 0 | 7 | 10 | 10 | 3.5 | 3.5 | 50% | 2025-08-03 Sa: 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0
D | 90000 | 90003 |  |  | CV - 4 (INSTALL) |  |  |  | (REV #1) | 2 | EA | 16 | 0 | 16 | 1 | 1 | 8 | 8 | 50% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | bar: 2025-08-03 Sa
D | 90000 | 90003 |  |  | CV - 6 (INSTALL) |  |  |  | (REV #1) | 1 | EA | 7 | 0 | 7 | 0.5 | 0.5 | 3.5 | 3.5 | 50% | 2025-08-03 Sa: 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0
D | 90000 | 90003 |  |  | PDI - (INSTALL) |  |  |  | (REV #1) | 1 | EA | 1.5 | 1.5 | 3 | 0.5 | 0.5 | 1.5 | 1.5 | 50% | 2025-08-03 Sa: 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
D | 90000 | 90003 |  |  | INSTALL VALVE |  |  |  | (REV #1) | 8 | EA | 8 | 0 | 8 | 4 | 4 | 4 | 4 | 50% | 2025-08-03 Sa: 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
D | 90000 | 90003 |  |  | INSTALL CONNECTIONS |  |  |  | (REV #1) | 34 | EA | 5.1 | 0 | 5.1 | 34 | 0 | 5.1 | 0 | 100% | 2025-08-03 Sa: 34 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 0 | 0
P | 90000 | 90004 |  |  | X788N TO L7 |  |  |  | (REV #1) |  |  | 48 | 0 | 48 |  |  | 48 | 0 | 100%
D | 90000 | 90004 |  |  | .035 WALL - 3/8 (SS) |  |  |  | (REV #1) | 20 | LF | 5.6 | 0 | 5.6 | 20 | 0 | 5.6 | 0 | 100% | 2025-08-03 F: 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 0
D | 90000 | 90004 |  |  | .049 WALL - 1/2 (SS) |  |  |  | (REV #1) | 60 | LF | 20.4 | 0 | 20.4 | 60 | 0 | 20.4 | 0 | 100% | 2025-08-03 Tu: 40; 2025-08-03 Sa: 20 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 0
D | 90000 | 90004 |  |  | 1/2" INSTALL CONNECTIONS |  |  |  | (REV #1) | 6 | EA | 6 | 0 | 6 | 6 | 0 | 6 | 0 | 100% | 2025-08-03 Tu: 5; 2025-08-03 Sa: 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
D | 90000 | 90004 |  |  | 3/8" INSTALL CONNECTIONS |  |  |  | (REV #1) | 6 | EA | 6 | 0 | 6 | 6 | 0 | 6 | 0 | 100% | 2025-08-03 Th: 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
D | 90000 | 90004 |  |  | 1/2" BOLTUP |  |  |  | (REV #1) | 1 | EA | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 100% | [42 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | bar: 2025-08-03 Th
D | 90000 | 90004 |  |  | INSTALL VALVE |  |  |  | (REV #1) | 3 | EA | 3 | 0 | 3 | 3 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 90000 | 90004 |  |  | CREATE DOUBLE COIL |  |  |  | (REV #1) | 2 | EA | 3 | 0 | 3 | 2 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
D | 90000 | 90004 |  |  | INSTALL MS-01-109 |  |  |  | (REV #1) | 20 | EA | 3 | 0 | 3 | 20 | 0 | 3 | 0 | 100% | 2025-08-03 Th: 10; 2025-08-03 Sa: 10 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
P | 90000 | 90005 |  |  | INSTRUMENTS |  |  |  | (REV #1) |  |  | 18 | 3 | 21 |  |  | 21 | 0 | 100%
D | 90000 | 90005 |  |  | TE - (INSTALL) |  |  |  | (REV #1) | 3 | EA | 15 | 3 | 18 | 3 | 0 | 18 | 0 | 100% | 2025-07-20 Th: 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0
D | 90000 | 90005 |  |  | TI - (INSTALL) |  |  |  | (REV #1) | 1 | EA | 3 | 0 | 3 | 1 | 0 | 3 | 0 | 100% | [42 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | bar: 2025-07-20 Th
P | 90000 | 99990 |  |  | TUBING SUPPORTS |  |  |  | (REV #1) |  |  | 30.6 | 15.6 | 46.2 |  |  | 46.2 | 0 | 100%
D | 90000 | 99990 |  |  | INSTALL RACEWAY |  |  |  | (REV #1) | 100 | LF | 15 | 0 | 15 | 100 | 0 | 15 | 0 | 100% | 2025-08-03 Tu: 75; 2025-08-03 W: 25 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0
D | 90000 | 99990 |  |  | INSTALL SUPPORTS |  |  |  | (REV #1) | 26 | EA | 15.6 | 15.6 | 31.2 | 26 | 0 | 31.2 | 0 | 100% | 2025-08-03 Tu: 20; 2025-08-03 W: 6 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 31.2 | 0 | 0
W | 190000 | WBS |  |  | DEMOBILIZE | [6 empty] | 43 | 0 | 43 |  |  | 0 | 43 | 0%
P | 190000 | 190001 |  |  | SITE CLEAN UP | [6 empty] | 20 | 0 | 20 |  |  | 0 | 20 | 0%
D | 190000 | 190001 |  |  | DURING CONSTRUCTION |  |  |  |  | 2 | DAY | 20 | 0 | 20 | 0 | 2 | 0 | 20 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P | 190000 | 190002 |  |  | EQUIPMENT REMOVAL | [6 empty] | 13 | 0 | 13 |  |  | 0 | 13 | 0%
D | 190000 | 190002 |  |  | TOOLS |  |  |  |  | 1 | EA | 5 | 0 | 5 | 0 | 1 | 0 | 5 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 190000 | 190002 |  |  | EQUIPMENT |  |  |  |  | 4 | EA | 8 | 0 | 8 | 0 | 4 | 0 | 8 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P | 190000 | 190003 |  |  | TRAILER REMOVAL | [6 empty] | 10 | 0 | 10 |  |  | 0 | 10 | 0%
D | 190000 | 190003 |  |  | TOOL TRAILER |  |  |  |  | 1 | EA | 10 | 0 | 10 | 0 | 1 | 0 | 10 | 0% | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W | 200000 | WBS |  |  | SUPPORT | [6 empty] | 240 | 0 | 240 |  |  | 240 | 0 | 100%
P | 200000 | 200100 |  |  | PROJECT MANAGER | [6 empty] | 240 | 0 | 240 |  |  | 240 | 0 | 100%
D | 200000 | 200100 |  |  | WEEK (60 HRS) |  |  |  |  | 4 | WEEK | 240 | 0 | 240 | 4 | 0 | 240 | 0 | 100% | [42 empty] | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | bar: WE M; WE M; WE M; WE M
T | T | T | T | T | T | T | T | T | T | T | T | 2589.94 | 301.67 | 2891.61 |  |  | 2501.655 | 389.955 | 86.51% | [49 empty] | 373.1 | 804.835 | 498.5951 | 377.3465 | 447.7784 | 0 | 0