## Progress Tracking
[10 empty] | Proposal #: | 2021 - Rev1
Change #:
Job #:
Description:
[10 empty] | Owner: | weyerhaeuser
[10 empty] | Location: | 242 lipton industrial parkway
[10 empty] | Start Date: | 1775001600000
Scope | [9 empty] | Estimate Basis |  |  |  |  | Progress |  |  |  |  | W/E 2/14 | [5 empty] | W/E 2/21 | [5 empty] | Weekly Qty Complete |  | Weekly Earned MH
Filter | WBS | PHASE | SIZE | FLC | DESCRIPTION | SPEC | INSULATION | INSUL SIZE | SHT | QTY | UNIT | CRAFT MH | WELD MH | TOTAL MH | QTY COMP | QTY REM | MH EARNED | MH REM | % COMP | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | 2/14 | 2/21 | 2/14 | 2/21
W | 90000 |  |  |  | INSTRUMENTS
W | 80000 |  |  |  | ELECTRICAL
W | 50000 |  |  |  | PUMPS & DRIVERS
W | 150000 |  |  |  | BUILDINGS
W | 20000 |  |  |  | SITE PREPARATION
W | 130000 |  |  |  | BG PIPING
W | 110000 |  |  |  | PAINTING
P | 110000 | 110001 |  |  | COATINGS
W | 100000 |  |  |  | INSULATION
W | 120000 |  |  |  | DISMANTLING
W | 180000 |  |  |  | SPECIALTY SERVICES
W | 70000 |  |  |  | AG PIPING | [6 empty] | 7207.7 |  | 7207.7 |  |  | 1.65 | 7206.05 | [14 empty] | 4 |  | 1.65
P | 70000 | 70001 |  | 6 | PROCESS WATER/WC1 (SPECIALTY RIP SAW) | [6 empty] | 104.95 |  | 104.95 |  |  | 1.65 | 103.3 | 2% | [13 empty] | 4 |  | 1.65
D | 70000 | 70001 |  | 6 | 3/4" X 50' WATER HOSE |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 2 | 0 | 0.8 |  | 100% | [13 empty] | 2 |  | 0.8
D | 70000 | 70001 |  | 6 | FIREMAN HOSE NOZZLE |  |  |  |  | 2 | EA | 0.7 |  | 0.7 | 1 | 1 | 0.35 | 0.35 | 50% | [13 empty] | 1 |  | 0.35
D | 70000 | 70001 |  | 6 | HE - ≤2 |  |  |  |  | 160 | LF | 32 |  | 32 | 0 | 160 |  | 32
D | 70000 | 70001 |  | 6 | V - ≤2 |  |  |  |  | 3 | EA | 1.5 |  | 1.5 | 1 | 2 | 0.5 | 1 | 33% | [13 empty] | 1 |  | 0.5
D | 70000 | 70001 |  | 6 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 6 | THRD - 1 |  |  |  |  | 32 | EA | 9.6 |  | 9.6 | 0 | 32 |  | 9.6
D | 70000 | 70001 |  | 6 | CUT - ≤2 |  |  |  |  | 28 | EA | 14 |  | 14 | 0 | 28 |  | 14
D | 70000 | 70001 |  | 6 | UBOLT - ≤4 |  |  |  |  | 23 | EA | 46 |  | 46 | 0 | 23 |  | 46
P | 70000 | 79989 |  |  | OFFLOAD/RECEIVE | [6 empty] | 454.4 |  | 454.4 |  |  |  | 454.4
D | 70000 | 79989 |  |  | OFF - ≤2 |  |  |  |  | 9088 | LF | 454.4 |  | 454.4 | 0 | 9088 |  | 454.4
P | 70000 | 70001 |  | 4 | PROCESS WATER/WC1 (SANDERS) | [6 empty] | 448.6 |  | 448.6 |  |  |  | 448.6
D | 70000 | 70001 |  | 4 | FIREMAN HOSE NOZZLE |  |  |  |  | 12 | EA | 4.2 |  | 4.2 | 0 | 12 |  | 4.2
D | 70000 | 70001 |  | 4 | 3/4" X 50' WATER HOSE |  |  |  |  | 12 | EA | 4.8 |  | 4.8 | 0 | 12 |  | 4.8
D | 70000 | 70001 |  | 4 | HE - ≤2 |  |  |  |  | 448 | LF | 89.6 |  | 89.6 | 0 | 448 |  | 89.6
D | 70000 | 70001 |  | 4 | V - ≤2 |  |  |  |  | 20 | EA | 10 |  | 10 | 0 | 20 |  | 10
D | 70000 | 70001 |  | 4 | THRD - 1 |  |  |  |  | 285 | EA | 85.5 |  | 85.5 | 0 | 285 |  | 85.5
D | 70000 | 70001 |  | 4 | CUT - ≤2 |  |  |  |  | 237 | EA | 118.5 |  | 118.5 | 0 | 237 |  | 118.5
D | 70000 | 70001 |  | 4 | UBOLT - ≤4 |  |  |  |  | 68 | EA | 136 |  | 136 | 0 | 68 |  | 136
P | 70000 | 70001 |  | 1 | PROCESS WATER/WB1 (END TRIM/DUAL EDGE TRIM SAWS) | [6 empty] | 249.95 |  | 249.95 |  |  |  | 249.95
D | 70000 | 70001 |  | 1 | FIREMAN HOSE NOZZLE |  |  |  |  | 15 | EA | 5.25 |  | 5.25 | 0 | 15 |  | 5.25
D | 70000 | 70001 |  | 1 | 3/4" X 50' WATER HOSE |  |  |  |  | 15 | EA | 6 |  | 6 | 0 | 15 |  | 6
D | 70000 | 70001 |  | 1 | HE - ≤2 |  |  |  |  | 420 | LF | 84 |  | 84 | 0 | 420 |  | 84
D | 70000 | 70001 |  | 1 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 1 | THRD - 1.5 |  |  |  |  | 36 | EA | 12.6 |  | 12.6 | 0 | 36 |  | 12.6
D | 70000 | 70001 |  | 1 | THRD - 1 |  |  |  |  | 87 | EA | 26.1 |  | 26.1 | 0 | 87 |  | 26.1
D | 70000 | 70001 |  | 1 | CUT - ≤2 |  |  |  |  | 83 | EA | 41.5 |  | 41.5 | 0 | 83 |  | 41.5
D | 70000 | 70001 |  | 1 | UBOLT - ≤4 |  |  |  |  | 35 | EA | 70 |  | 70 | 0 | 35 |  | 70
P | 70000 | 70001 |  | 3 | MILL AIR (HORIZONTAL COOLER) | [6 empty] | 229.7 |  | 229.7 |  |  |  | 229.7
D | 70000 | 70001 |  | 3 | AIR WAND |  |  |  |  | 5 | EA | 1.75 |  | 1.75 | 0 | 5 |  | 1.75
D | 70000 | 70001 |  | 3 | 3/8" X 50' AIR HOSE |  |  |  |  | 5 | EA | 1.25 |  | 1.25 | 0 | 5 |  | 1.25
D | 70000 | 70001 |  | 3 | HE - ≤2 |  |  |  |  | 300 | LF | 60 |  | 60 | 0 | 300 |  | 60
D | 70000 | 70001 |  | 3 | V - ≤2 |  |  |  |  | 10 | EA | 5 |  | 5 | 0 | 10 |  | 5
D | 70000 | 70001 |  | 3 | THRD - 1.5 |  |  |  |  | 42 | EA | 14.7 |  | 14.7 | 0 | 42 |  | 14.7
D | 70000 | 70001 |  | 3 | THRD - 1 |  |  |  |  | 70 | EA | 21 |  | 21 | 0 | 70 |  | 21
D | 70000 | 70001 |  | 3 | CUT - ≤2 |  |  |  |  | 92 | EA | 46 |  | 46 | 0 | 92 |  | 46
D | 70000 | 70001 |  | 3 | UBOLT - ≤4 |  |  |  |  | 40 | EA | 80 |  | 80 | 0 | 40 |  | 80
P | 70000 | 70001 |  | 19 | PROCESS WATER/WC1 (ACCESSORY EQUIPMENT STATIONS) | [6 empty] | 336.9 |  | 336.9 |  |  |  | 336.9
D | 70000 | 70001 |  | 19 | 3/4" X 50' WATER HOSE |  |  |  |  | 6 | EA | 2.4 |  | 2.4 | 0 | 6 |  | 2.4
D | 70000 | 70001 |  | 19 | FIREMAN HOSE NOZZLE |  |  |  |  | 6 | EA | 2.1 |  | 2.1 | 0 | 6 |  | 2.1
D | 70000 | 70001 |  | 19 | HE - ≤2 |  |  |  |  | 550 | LF | 110 |  | 110 | 0 | 550 |  | 110
D | 70000 | 70001 |  | 19 | V - ≤2 |  |  |  |  | 14 | EA | 7 |  | 7 | 0 | 14 |  | 7
D | 70000 | 70001 |  | 19 | THRD - 2 |  |  |  |  | 68 | EA | 27.2 |  | 27.2 | 0 | 68 |  | 27.2
D | 70000 | 70001 |  | 19 | THRD - 1 |  |  |  |  | 84 | EA | 25.2 |  | 25.2 | 0 | 84 |  | 25.2
D | 70000 | 70001 |  | 19 | CUT - ≤2 |  |  |  |  | 102 | EA | 51 |  | 51 | 0 | 102 |  | 51
D | 70000 | 70001 |  | 19 | UBOLT - ≤4 |  |  |  |  | 56 | EA | 112 |  | 112 | 0 | 56 |  | 112
P | 70000 | 70001 |  | 7 | PROCESS WATER/WC1 (REMAN SAWS/STACKERS) | [6 empty] | 126.3 |  | 126.3 |  |  |  | 126.3
D | 70000 | 70001 |  | 7 | 3/4" WATER HOSE |  |  |  |  | 4 | EA | 1.6 |  | 1.6 | 0 | 4 |  | 1.6
D | 70000 | 70001 |  | 7 | FIREMAN HOSE NOZZLE |  |  |  |  | 4 | EA | 1.4 |  | 1.4 | 0 | 4 |  | 1.4
D | 70000 | 70001 |  | 7 | HE - ≤2 |  |  |  |  | 120 | LF | 24 |  | 24 | 0 | 120 |  | 24
D | 70000 | 70001 |  | 7 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 7 | THRD - 2 |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 7 | THRD - 1 |  |  |  |  | 80 | EA | 24 |  | 24 | 0 | 80 |  | 24
D | 70000 | 70001 |  | 7 | CUT - ≤2 |  |  |  |  | 72 | EA | 36 |  | 36 | 0 | 72 |  | 36
D | 70000 | 70001 |  | 7 | UBOLT - ≤4 |  |  |  |  | 17 | EA | 34 |  | 34 | 0 | 17 |  | 34
P | 70000 | 70001 |  | 10 | PW/WC1 TRIM SAW CONVEYORS (BL-00) | [6 empty] | 129.1 |  | 129.1 |  |  |  | 129.1
D | 70000 | 70001 |  | 10 | FIREMAN HOSE NOZZLE |  |  |  |  | 3 | EA | 1.05 |  | 1.05 | 0 | 3 |  | 1.05
D | 70000 | 70001 |  | 10 | 3/4" X 50' WATER HOSE |  |  |  |  | 3 | EA | 1.2 |  | 1.2 | 0 | 3 |  | 1.2
D | 70000 | 70001 |  | 10 | HE - ≤2 |  |  |  |  | 230 | LF | 46 |  | 46 | 0 | 230 |  | 46
D | 70000 | 70001 |  | 10 | V - ≤2 |  |  |  |  | 3 | EA | 1.5 |  | 1.5 | 0 | 3 |  | 1.5
D | 70000 | 70001 |  | 10 | THRD - 2 |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 10 | THRD - 1.5 |  |  |  |  | 39 | EA | 13.65 |  | 13.65 | 0 | 39 |  | 13.65
D | 70000 | 70001 |  | 10 | THRD - 1 |  |  |  |  | 33 | EA | 9.9 |  | 9.9 | 0 | 33 |  | 9.9
D | 70000 | 70001 |  | 10 | CUT - ≤2 |  |  |  |  | 46 | EA | 23 |  | 23 | 0 | 46 |  | 23
D | 70000 | 70001 |  | 10 | UBOLT - ≤4 |  |  |  |  | 16 | EA | 32 |  | 32 | 0 | 16 |  | 32
P | 70000 | 70001 |  | 9 | PROCESS WATER/WC1 (WRAPPERS/STAPLERS) | [6 empty] | 284.95 |  | 284.95 |  |  |  | 284.95
D | 70000 | 70001 |  | 9 | FIREMAN HOSE NOZZLE |  |  |  |  | 10 | EA | 3.5 |  | 3.5 | 0 | 10 |  | 3.5
D | 70000 | 70001 |  | 9 | 3/4" X 50' WATER HOSE |  |  |  |  | 10 | EA | 4 |  | 4 | 0 | 10 |  | 4
D | 70000 | 70001 |  | 9 | HE - ≤2 |  |  |  |  | 250 | LF | 50 |  | 50 | 0 | 250 |  | 50
D | 70000 | 70001 |  | 9 | V - ≤2 |  |  |  |  | 18 | EA | 9 |  | 9 | 0 | 18 |  | 9
D | 70000 | 70001 |  | 9 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 9 | THRD - 1 |  |  |  |  | 202 | EA | 60.6 |  | 60.6 | 0 | 202 |  | 60.6
D | 70000 | 70001 |  | 9 | CUT - ≤2 |  |  |  |  | 175 | EA | 87.5 |  | 87.5 | 0 | 175 |  | 87.5
D | 70000 | 70001 |  | 9 | UBOLT - ≤4 |  |  |  |  | 35 | EA | 70 |  | 70 | 0 | 35 |  | 70
P | 70000 | 70001 |  | 8 | PROCESS WATER/WC1 (STRAPPERS/CUT-TO-SIZE SAWS/END SEALS) | [6 empty] | 336.4 |  | 336.4 |  |  |  | 336.4
D | 70000 | 70001 |  | 8 | FIREMAN HOSE NOZZLE |  |  |  |  | 6 | EA | 2.1 |  | 2.1 | 0 | 6 |  | 2.1
D | 70000 | 70001 |  | 8 | 3/4" X 50' WATER HOSE |  |  |  |  | 6 | EA | 2.4 |  | 2.4 | 0 | 6 |  | 2.4
D | 70000 | 70001 |  | 8 | HE - ≤2 |  |  |  |  | 260 | LF | 52 |  | 52 | 0 | 260 |  | 52
D | 70000 | 70001 |  | 8 | V - ≤2 |  |  |  |  | 31 | EA | 15.5 |  | 15.5 | 0 | 31 |  | 15.5
D | 70000 | 70001 |  | 8 | THRD - 1 |  |  |  |  | 238 | EA | 71.4 |  | 71.4 | 0 | 238 |  | 71.4
D | 70000 | 70001 |  | 8 | CUT - ≤2 |  |  |  |  | 238 | EA | 119 |  | 119 | 0 | 238 |  | 119
D | 70000 | 70001 |  | 8 | UBOLT - ≤4 |  |  |  |  | 37 | EA | 74 |  | 74 | 0 | 37 |  | 74
P | 70000 | 70001 |  | 5 | PROCESS WATER/WC1 (CROSS CUT/SAMPLE SAW) | [6 empty] | 264.65 |  | 264.65 |  |  |  | 264.65
D | 70000 | 70001 |  | 5 | 3/4" X 50' WATER HOSE |  |  |  |  | 8 | EA | 3.2 |  | 3.2 | 0 | 8 |  | 3.2
D | 70000 | 70001 |  | 5 | FIREMAN HOSE NOZZLE |  |  |  |  | 8 | EA | 2.8 |  | 2.8 | 0 | 8 |  | 2.8
D | 70000 | 70001 |  | 5 | HE - ≤2 |  |  |  |  | 340 | LF | 68 |  | 68 | 0 | 340 |  | 68
D | 70000 | 70001 |  | 5 | V - ≤2 |  |  |  |  | 11 | EA | 5.5 |  | 5.5 | 0 | 11 |  | 5.5
D | 70000 | 70001 |  | 5 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 5 | THRD - 1 |  |  |  |  | 121 | EA | 36.3 |  | 36.3 | 0 | 121 |  | 36.3
D | 70000 | 70001 |  | 5 | CUT - ≤2 |  |  |  |  | 105 | EA | 52.5 |  | 52.5 | 0 | 105 |  | 52.5
D | 70000 | 70001 |  | 5 | UBOLT - ≤4 |  |  |  |  | 48 | EA | 96 |  | 96 | 0 | 48 |  | 96
P | 70000 | 70001 |  | 3 | PROCESS WATER/WB1 (HORIZONTAL COOLER) | [6 empty] | 227.45 |  | 227.45 |  |  |  | 227.45
D | 70000 | 70001 |  | 3 | 3/4" X 50' WATER HOSE |  |  |  |  | 5 | EA | 2 |  | 2 | 0 | 5 |  | 2
D | 70000 | 70001 |  | 3 | FIREMAN HOSE NOZZLE |  |  |  |  | 5 | EA | 1.75 |  | 1.75 | 0 | 5 |  | 1.75
D | 70000 | 70001 |  | 3 | HE - ≤2 |  |  |  |  | 300 | LF | 60 |  | 60 | 0 | 300 |  | 60
D | 70000 | 70001 |  | 3 | V - ≤2 |  |  |  |  | 10 | EA | 5 |  | 5 | 0 | 10 |  | 5
D | 70000 | 70001 |  | 3 | THRD - 1.5 |  |  |  |  | 42 | EA | 14.7 |  | 14.7 | 0 | 42 |  | 14.7
D | 70000 | 70001 |  | 3 | THRD - 1 |  |  |  |  | 60 | EA | 18 |  | 18 | 0 | 60 |  | 18
D | 70000 | 70001 |  | 3 | CUT - ≤2 |  |  |  |  | 92 | EA | 46 |  | 46 | 0 | 92 |  | 46
D | 70000 | 70001 |  | 3 | UBOLT - ≤4 |  |  |  |  | 40 | EA | 80 |  | 80 | 0 | 40 |  | 80
P | 70000 | 70001 |  | 6 | MILL AIR (SPECIALTY RIP SAW) | [6 empty] | 117.65 |  | 117.65 |  |  |  | 117.65
D | 70000 | 70001 |  | 6 | AIR WAND |  |  |  |  | 2 | EA | 0.7 |  | 0.7 | 0 | 2 |  | 0.7
D | 70000 | 70001 |  | 6 | 3/8" X 50' AIR HOSE |  |  |  |  | 2 | EA | 0.5 |  | 0.5 | 0 | 2 |  | 0.5
D | 70000 | 70001 |  | 6 | HE - ≤2 |  |  |  |  | 160 | LF | 32 |  | 32 | 0 | 160 |  | 32
D | 70000 | 70001 |  | 6 | V - ≤2 |  |  |  |  | 5 | EA | 2.5 |  | 2.5 | 0 | 5 |  | 2.5
D | 70000 | 70001 |  | 6 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 6 | THRD - 1 |  |  |  |  | 47 | EA | 14.1 |  | 14.1 | 0 | 47 |  | 14.1
D | 70000 | 70001 |  | 6 | CUT - ≤2 |  |  |  |  | 43 | EA | 21.5 |  | 21.5 | 0 | 43 |  | 21.5
D | 70000 | 70001 |  | 6 | UBOLT - ≤4 |  |  |  |  | 23 | EA | 46 |  | 46 | 0 | 23 |  | 46
P | 70000 | 70001 |  | 12 | PW/WC1 SANDER LINE CONVEYORS (BL-03, 04, 05) | [6 empty] | 279.45 |  | 279.45 |  |  |  | 279.45
D | 70000 | 70001 |  | 12 | FIREMAN HOSE NOZZLE |  |  |  |  | 12 | EA | 4.2 |  | 4.2 | 0 | 12 |  | 4.2
D | 70000 | 70001 |  | 12 | 3/4" X 50' WATER HOSE |  |  |  |  | 12 | EA | 4.8 |  | 4.8 | 0 | 12 |  | 4.8
D | 70000 | 70001 |  | 12 | HE - ≤2 |  |  |  |  | 440 | LF | 88 |  | 88 | 0 | 440 |  | 88
D | 70000 | 70001 |  | 12 | V - ≤2 |  |  |  |  | 13 | EA | 6.5 |  | 6.5 | 0 | 13 |  | 6.5
D | 70000 | 70001 |  | 12 | THRD - 2 |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 12 | THRD - 1.5 |  |  |  |  | 55 | EA | 19.25 |  | 19.25 | 0 | 55 |  | 19.25
D | 70000 | 70001 |  | 12 | THRD - 1 |  |  |  |  | 108 | EA | 32.4 |  | 32.4 | 0 | 108 |  | 32.4
D | 70000 | 70001 |  | 12 | CUT - ≤2 |  |  |  |  | 111 | EA | 55.5 |  | 55.5 | 0 | 111 |  | 55.5
D | 70000 | 70001 |  | 12 | UBOLT - ≤4 |  |  |  |  | 34 | EA | 68 |  | 68 | 0 | 34 |  | 68
P | 70000 | 70001 |  | 9 | MILL AIR (WRAPPERS/STAPLERS) | [6 empty] | 283.45 |  | 283.45 |  |  |  | 283.45
D | 70000 | 70001 |  | 9 | AIR WAND |  |  |  |  | 10 | EA | 3.5 |  | 3.5 | 0 | 10 |  | 3.5
D | 70000 | 70001 |  | 9 | 3/8" X 50' AIR HOSE |  |  |  |  | 10 | EA | 2.5 |  | 2.5 | 0 | 10 |  | 2.5
D | 70000 | 70001 |  | 9 | HE - ≤2 |  |  |  |  | 250 | LF | 50 |  | 50 | 0 | 250 |  | 50
D | 70000 | 70001 |  | 9 | V - ≤2 |  |  |  |  | 18 | EA | 9 |  | 9 | 0 | 18 |  | 9
D | 70000 | 70001 |  | 9 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 9 | THRD - 1 |  |  |  |  | 202 | EA | 60.6 |  | 60.6 | 0 | 202 |  | 60.6
D | 70000 | 70001 |  | 9 | CUT - ≤2 |  |  |  |  | 175 | EA | 87.5 |  | 87.5 | 0 | 175 |  | 87.5
D | 70000 | 70001 |  | 9 | UBOLT - ≤4 |  |  |  |  | 35 | EA | 70 |  | 70 | 0 | 35 |  | 70
P | 70000 | 70001 |  | 13 | PW/WC1 STACKER CONVEYORS (SL-07) | [6 empty] | 234.1 |  | 234.1 |  |  |  | 234.1
D | 70000 | 70001 |  | 13 | FIREMAN HOSE NOZZLE |  |  |  |  | 10 | EA | 3.5 |  | 3.5 | 0 | 10 |  | 3.5
D | 70000 | 70001 |  | 13 | 3/4" X 50' WATER HOSE |  |  |  |  | 10 | EA | 4 |  | 4 | 0 | 10 |  | 4
D | 70000 | 70001 |  | 13 | HE - ≤2 |  |  |  |  | 400 | LF | 80 |  | 80 | 0 | 400 |  | 80
D | 70000 | 70001 |  | 13 | V - ≤2 |  |  |  |  | 11 | EA | 5.5 |  | 5.5 | 0 | 11 |  | 5.5
D | 70000 | 70001 |  | 13 | THRD - 1.5 |  |  |  |  | 54 | EA | 18.9 |  | 18.9 | 0 | 54 |  | 18.9
D | 70000 | 70001 |  | 13 | THRD - 1 |  |  |  |  | 64 | EA | 19.2 |  | 19.2 | 0 | 64 |  | 19.2
D | 70000 | 70001 |  | 13 | CUT - ≤2 |  |  |  |  | 78 | EA | 39 |  | 39 | 0 | 78 |  | 39
D | 70000 | 70001 |  | 13 | UBOLT - ≤4 |  |  |  |  | 32 | EA | 64 |  | 64 | 0 | 32 |  | 64
P | 70000 | 70001 |  | 2 | PROCESS WATER/WC1 (FINISHING HOG) | [6 empty] | 197.35 |  | 197.35 |  |  |  | 197.35
D | 70000 | 70001 |  | 2 | FIREMAN HOSE NOZZLE |  |  |  |  | 2 | EA | 0.7 |  | 0.7 | 0 | 2 |  | 0.7
D | 70000 | 70001 |  | 2 | 3/4" X 50' WATER HOSE |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 2 | HE - ≤2 |  |  |  |  | 270 | LF | 54 |  | 54 | 0 | 270 |  | 54
D | 70000 | 70001 |  | 2 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 2 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 2 | THRD - 1 |  |  |  |  | 80 | EA | 24 |  | 24 | 0 | 80 |  | 24
D | 70000 | 70001 |  | 2 | CUT - ≤2 |  |  |  |  | 74 | EA | 37 |  | 37 | 0 | 74 |  | 37
D | 70000 | 70001 |  | 2 | UBOLT - ≤4 |  |  |  |  | 38 | EA | 76 |  | 76 | 0 | 38 |  | 76
P | 70000 | 70001 |  | 15 | PW/WC1 PACKAGE LINE 3 CONVEYORS (BL-08) | [6 empty] | 143.15 |  | 143.15 |  |  |  | 143.15
D | 70000 | 70001 |  | 15 | 3/4" X 50' WATER HOSE |  |  |  |  | 5 | EA | 2 |  | 2 | 0 | 5 |  | 2
D | 70000 | 70001 |  | 15 | FIREMAN HOSE NOZZLE |  |  |  |  | 5 | EA | 1.75 |  | 1.75 | 0 | 5 |  | 1.75
D | 70000 | 70001 |  | 15 | HE - ≤2 |  |  |  |  | 300 | LF | 60 |  | 60 | 0 | 300 |  | 60
D | 70000 | 70001 |  | 15 | V - ≤2 |  |  |  |  | 5 | EA | 2.5 |  | 2.5 | 0 | 5 |  | 2.5
D | 70000 | 70001 |  | 15 | THRD - 1.5 |  |  |  |  | 22 | EA | 7.7 |  | 7.7 | 0 | 22 |  | 7.7
D | 70000 | 70001 |  | 15 | THRD - 1 |  |  |  |  | 44 | EA | 13.2 |  | 13.2 | 0 | 44 |  | 13.2
D | 70000 | 70001 |  | 15 | CUT - ≤2 |  |  |  |  | 56 | EA | 28 |  | 28 | 0 | 56 |  | 28
D | 70000 | 70001 |  | 15 | UBOLT - ≤4 |  |  |  |  | 14 | EA | 28 |  | 28 | 0 | 14 |  | 28
P | 70000 | 70001 |  | 5 | MILL AIR (CROSS CUT/SAMPLE SAW) | [6 empty] | 263.45 |  | 263.45 |  |  |  | 263.45
D | 70000 | 70001 |  | 5 | 3/8" X 50' AIR HOSE |  |  |  |  | 8 | EA | 2 |  | 2 | 0 | 8 |  | 2
D | 70000 | 70001 |  | 5 | AIR WAND |  |  |  |  | 8 | EA | 2.8 |  | 2.8 | 0 | 8 |  | 2.8
D | 70000 | 70001 |  | 5 | HE - ≤2 |  |  |  |  | 340 | LF | 68 |  | 68 | 0 | 340 |  | 68
D | 70000 | 70001 |  | 5 | V - ≤2 |  |  |  |  | 11 | EA | 5.5 |  | 5.5 | 0 | 11 |  | 5.5
D | 70000 | 70001 |  | 5 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 5 | THRD - 1 |  |  |  |  | 121 | EA | 36.3 |  | 36.3 | 0 | 121 |  | 36.3
D | 70000 | 70001 |  | 5 | CUT - ≤2 |  |  |  |  | 105 | EA | 52.5 |  | 52.5 | 0 | 105 |  | 52.5
D | 70000 | 70001 |  | 5 | UBOLT - ≤4 |  |  |  |  | 48 | EA | 96 |  | 96 | 0 | 48 |  | 96
P | 70000 | 70001 |  | 8 | MILL AIR (STRAPPERS/CUT-TO-SIZE SAWS/END SEALS)) | [6 empty] | 339.1 |  | 339.1 |  |  |  | 339.1
D | 70000 | 70001 |  | 8 | AIR WAND |  |  |  |  | 6 | EA | 2.1 |  | 2.1 | 0 | 6 |  | 2.1
D | 70000 | 70001 |  | 8 | 3/8" AIR HOSE |  |  |  |  | 6 | EA | 1.5 |  | 1.5 | 0 | 6 |  | 1.5
D | 70000 | 70001 |  | 8 | HE - ≤2 |  |  |  |  | 260 | LF | 52 |  | 52 | 0 | 260 |  | 52
D | 70000 | 70001 |  | 8 | BW - 4 |  |  |  |  | 0 | EA |  |  |  | 0 | 0
D | 70000 | 70001 |  | 8 | V - ≤2 |  |  |  |  | 31 | EA | 15.5 |  | 15.5 | 0 | 31 |  | 15.5
D | 70000 | 70001 |  | 8 | THRD - 1 |  |  |  |  | 250 | EA | 75 |  | 75 | 0 | 250 |  | 75
D | 70000 | 70001 |  | 8 | CUT - ≤2 |  |  |  |  | 238 | EA | 119 |  | 119 | 0 | 238 |  | 119
D | 70000 | 70001 |  | 8 | UBOLT - ≤4 |  |  |  |  | 37 | EA | 74 |  | 74 | 0 | 37 |  | 74
P | 70000 | 70001 |  | 19 | MILL AIR (ACCESSORY EQUIPMENT STATIONS) | [6 empty] | 469.75 |  | 469.75 |  |  |  | 469.75
D | 70000 | 70001 |  | 19 | 3/8" X 50' AIR HOSE |  |  |  |  | 8 | EA | 2 |  | 2 | 0 | 8 |  | 2
D | 70000 | 70001 |  | 19 | AIR WAND |  |  |  |  | 8 | EA | 2.8 |  | 2.8 | 0 | 8 |  | 2.8
D | 70000 | 70001 |  | 19 | HE - ≤2 |  |  |  |  | 872 | LF | 174.4 |  | 174.4 | 0 | 872 |  | 174.4
D | 70000 | 70001 |  | 19 | V - ≤2 |  |  |  |  | 16 | EA | 8 |  | 8 | 0 | 16 |  | 8
D | 70000 | 70001 |  | 19 | THRD - 1.5 |  |  |  |  | 125 | EA | 43.75 |  | 43.75 | 0 | 125 |  | 43.75
D | 70000 | 70001 |  | 19 | THRD - 1 |  |  |  |  | 56 | EA | 16.8 |  | 16.8 | 0 | 56 |  | 16.8
D | 70000 | 70001 |  | 19 | CUT - ≤2 |  |  |  |  | 96 | EA | 48 |  | 48 | 0 | 96 |  | 48
D | 70000 | 70001 |  | 19 | UBOLT - ≤4 |  |  |  |  | 87 | EA | 174 |  | 174 | 0 | 87 |  | 174
P | 70000 | 70001 |  | 16 | PW/WC1 REMAN CONVEYORS (BL-01, 02) | [6 empty] | 101.25 |  | 101.25 |  |  |  | 101.25
D | 70000 | 70001 |  | 16 | FIREMAN HOSE NOZZLE |  |  |  |  | 3 | EA | 1.05 |  | 1.05 | 0 | 3 |  | 1.05
D | 70000 | 70001 |  | 16 | 3/4" X 50' WATER HOSE |  |  |  |  | 3 | EA | 1.2 |  | 1.2 | 0 | 3 |  | 1.2
D | 70000 | 70001 |  | 16 | HE - ≤2 |  |  |  |  | 160 | LF | 32 |  | 32 | 0 | 160 |  | 32
D | 70000 | 70001 |  | 16 | V - ≤2 |  |  |  |  | 4 | EA | 2 |  | 2 | 0 | 4 |  | 2
D | 70000 | 70001 |  | 16 | THRD - 1.5 |  |  |  |  | 26 | EA | 9.1 |  | 9.1 | 0 | 26 |  | 9.1
D | 70000 | 70001 |  | 16 | THRD - 1 |  |  |  |  | 28 | EA | 8.4 |  | 8.4 | 0 | 28 |  | 8.4
D | 70000 | 70001 |  | 16 | CUT - ≤2 |  |  |  |  | 43 | EA | 21.5 |  | 21.5 | 0 | 43 |  | 21.5
D | 70000 | 70001 |  | 16 | UBOLT - ≤4 |  |  |  |  | 13 | EA | 26 |  | 26 | 0 | 13 |  | 26
P | 70000 | 70001 |  | 2 | MILL AIR (FINISHING HOG) | [6 empty] | 196.45 |  | 196.45 |  |  |  | 196.45
D | 70000 | 70001 |  | 2 | 3/8" X 50' AIR HOSE |  |  |  |  | 2 | EA | 0.5 |  | 0.5 | 0 | 2 |  | 0.5
D | 70000 | 70001 |  | 2 | AIR WAND |  |  |  |  | 2 | EA | 0.7 |  | 0.7 | 0 | 2 |  | 0.7
D | 70000 | 70001 |  | 2 | HE - ≤2 |  |  |  |  | 270 | LF | 54 |  | 54 | 0 | 270 |  | 54
D | 70000 | 70001 |  | 2 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 2 | THRD - 1.5 |  |  |  |  | 1 | EA | 0.35 |  | 0.35 | 0 | 1 |  | 0.35
D | 70000 | 70001 |  | 2 | THRD - 1 |  |  |  |  | 78 | EA | 23.4 |  | 23.4 | 0 | 78 |  | 23.4
D | 70000 | 70001 |  | 2 | CUT - ≤2 |  |  |  |  | 74 | EA | 37 |  | 37 | 0 | 74 |  | 37
D | 70000 | 70001 |  | 2 | UBOLT - ≤4 |  |  |  |  | 38 | EA | 76 |  | 76 | 0 | 38 |  | 76
P | 70000 | 70001 |  | 7 | MILL AIR (REMAN SAWS/STACKERS) | [6 empty] | 125.7 |  | 125.7 |  |  |  | 125.7
D | 70000 | 70001 |  | 7 | AIR WAND |  |  |  |  | 4 | EA | 1.4 |  | 1.4 | 0 | 4 |  | 1.4
D | 70000 | 70001 |  | 7 | 3/8" X 50' AIR HOSE |  |  |  |  | 4 | EA | 1 |  | 1 | 0 | 4 |  | 1
D | 70000 | 70001 |  | 7 | HE - ≤2 |  |  |  |  | 120 | LF | 24 |  | 24 | 0 | 120 |  | 24
D | 70000 | 70001 |  | 7 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 7 | THRD - 2 |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 7 | THRD - 1 |  |  |  |  | 80 | EA | 24 |  | 24 | 0 | 80 |  | 24
D | 70000 | 70001 |  | 7 | CUT - ≤2 |  |  |  |  | 72 | EA | 36 |  | 36 | 0 | 72 |  | 36
D | 70000 | 70001 |  | 7 | UBOLT - ≤4 |  |  |  |  | 17 | EA | 34 |  | 34 | 0 | 17 |  | 34
P | 70000 | 70001 |  | 17 | PW/WC1 WASTE CONVEYORS | [6 empty] | 167.1 |  | 167.1 |  |  |  | 167.1
D | 70000 | 70001 |  | 17 | FIREMAN HOSE NOZZLE |  |  |  |  | 8 | EA | 2.8 |  | 2.8 | 0 | 8 |  | 2.8
D | 70000 | 70001 |  | 17 | 3/4" X 50' WATER HOSE |  |  |  |  | 8 | EA | 3.2 |  | 3.2 | 0 | 8 |  | 3.2
D | 70000 | 70001 |  | 17 | HE - ≤2 |  |  |  |  | 240 | LF | 48 |  | 48 | 0 | 240 |  | 48
D | 70000 | 70001 |  | 17 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 17 | THRD - 1.5 |  |  |  |  | 36 | EA | 12.6 |  | 12.6 | 0 | 36 |  | 12.6
D | 70000 | 70001 |  | 17 | THRD - 1 |  |  |  |  | 60 | EA | 18 |  | 18 | 0 | 60 |  | 18
D | 70000 | 70001 |  | 17 | CUT - ≤2 |  |  |  |  | 72 | EA | 36 |  | 36 | 0 | 72 |  | 36
D | 70000 | 70001 |  | 17 | UBOLT - ≤4 |  |  |  |  | 21 | EA | 42 |  | 42 | 0 | 21 |  | 42
P | 70000 | 70001 |  | 14 | PW/WC1 PACKAGE LINE 2 CONVEYORS (BL-07) | [6 empty] | 210.65 |  | 210.65 |  |  |  | 210.65
D | 70000 | 70001 |  | 14 | FIREMAN HOSE NOZZLE |  |  |  |  | 5 | EA | 1.75 |  | 1.75 | 0 | 5 |  | 1.75
D | 70000 | 70001 |  | 14 | 3/4" X 50' WATER HOSE |  |  |  |  | 5 | EA | 2 |  | 2 | 0 | 5 |  | 2
D | 70000 | 70001 |  | 14 | HE - ≤2 |  |  |  |  | 400 | LF | 80 |  | 80 | 0 | 400 |  | 80
D | 70000 | 70001 |  | 14 | V - ≤2 |  |  |  |  | 6 | EA | 3 |  | 3 | 0 | 6 |  | 3
D | 70000 | 70001 |  | 14 | THRD - 2 |  |  |  |  | 14 | EA | 5.6 |  | 5.6 | 0 | 14 |  | 5.6
D | 70000 | 70001 |  | 14 | THRD - 1.5 |  |  |  |  | 30 | EA | 10.5 |  | 10.5 | 0 | 30 |  | 10.5
D | 70000 | 70001 |  | 14 | THRD - 1 |  |  |  |  | 36 | EA | 10.8 |  | 10.8 | 0 | 36 |  | 10.8
D | 70000 | 70001 |  | 14 | CUT - ≤2 |  |  |  |  | 70 | EA | 35 |  | 35 | 0 | 70 |  | 35
D | 70000 | 70001 |  | 14 | UBOLT - ≤4 |  |  |  |  | 31 | EA | 62 |  | 62 | 0 | 31 |  | 62
P | 70000 | 70001 |  | 4 | MILL AIR (SANDERS) | [6 empty] | 447.4 |  | 447.4 |  |  |  | 447.4
D | 70000 | 70001 |  | 4 | AIR WAND |  |  |  |  | 12 | EA | 4.2 |  | 4.2 | 0 | 12 |  | 4.2
D | 70000 | 70001 |  | 4 | 3/8" X 50' AIR HOSE |  |  |  |  | 12 | EA | 3 |  | 3 | 0 | 12 |  | 3
D | 70000 | 70001 |  | 4 | HE - ≤2 |  |  |  |  | 448 | LF | 89.6 |  | 89.6 | 0 | 448 |  | 89.6
D | 70000 | 70001 |  | 4 | V - ≤2 |  |  |  |  | 20 | EA | 10 |  | 10 | 0 | 20 |  | 10
D | 70000 | 70001 |  | 4 | THRD - 1 |  |  |  |  | 287 | EA | 86.1 |  | 86.1 | 0 | 287 |  | 86.1
D | 70000 | 70001 |  | 4 | CUT - ≤2 |  |  |  |  | 237 | EA | 118.5 |  | 118.5 | 0 | 237 |  | 118.5
D | 70000 | 70001 |  | 4 | UBOLT - ≤4 |  |  |  |  | 68 | EA | 136 |  | 136 | 0 | 68 |  | 136
P | 70000 | 70001 |  | 11 | PW/WC1 COOLER CONVEYORS (SL-00) | [6 empty] | 190.65 |  | 190.65 |  |  |  | 190.65
D | 70000 | 70001 |  | 11 | FIREMAN HOSE NOZZLE |  |  |  |  | 5 | EA | 1.75 |  | 1.75 | 0 | 5 |  | 1.75
D | 70000 | 70001 |  | 11 | 3/4" X 50' WATER HOSE |  |  |  |  | 5 | EA | 2 |  | 2 | 0 | 5 |  | 2
D | 70000 | 70001 |  | 11 | HE - ≤2 |  |  |  |  | 360 | LF | 72 |  | 72 | 0 | 360 |  | 72
D | 70000 | 70001 |  | 11 | V - ≤2 |  |  |  |  | 6 | EA | 3 |  | 3 | 0 | 6 |  | 3
D | 70000 | 70001 |  | 11 | THRD - 2 |  |  |  |  | 2 | EA | 0.8 |  | 0.8 | 0 | 2 |  | 0.8
D | 70000 | 70001 |  | 11 | THRD - 1.5 |  |  |  |  | 46 | EA | 16.1 |  | 16.1 | 0 | 46 |  | 16.1
D | 70000 | 70001 |  | 11 | THRD - 1 |  |  |  |  | 55 | EA | 16.5 |  | 16.5 | 0 | 55 |  | 16.5
D | 70000 | 70001 |  | 11 | CUT - ≤2 |  |  |  |  | 61 | EA | 30.5 |  | 30.5 | 0 | 61 |  | 30.5
D | 70000 | 70001 |  | 11 | UBOLT - ≤4 |  |  |  |  | 24 | EA | 48 |  | 48 | 0 | 24 |  | 48
P | 70000 | 79999 |  |  | MATERIAL
P | 70000 | 70001 |  | 1 | MILL AIR (END TRIM/DUAL EDGE TRIM SAWS) | [6 empty] | 247.7 |  | 247.7 |  |  |  | 247.7
D | 70000 | 70001 |  | 1 | 3/8" X 50' AIR HOSE |  |  |  |  | 15 | EA | 3.75 |  | 3.75 | 0 | 15 |  | 3.75
D | 70000 | 70001 |  | 1 | AIR WAND |  |  |  |  | 15 | EA | 5.25 |  | 5.25 | 0 | 15 |  | 5.25
D | 70000 | 70001 |  | 1 | HE - ≤2 |  |  |  |  | 420 | LF | 84 |  | 84 | 0 | 420 |  | 84
D | 70000 | 70001 |  | 1 | V - ≤2 |  |  |  |  | 9 | EA | 4.5 |  | 4.5 | 0 | 9 |  | 4.5
D | 70000 | 70001 |  | 1 | THRD - 1.5 |  |  |  |  | 36 | EA | 12.6 |  | 12.6 | 0 | 36 |  | 12.6
D | 70000 | 70001 |  | 1 | THRD - 1 |  |  |  |  | 87 | EA | 26.1 |  | 26.1 | 0 | 87 |  | 26.1
D | 70000 | 70001 |  | 1 | CUT - ≤2 |  |  |  |  | 83 | EA | 41.5 |  | 41.5 | 0 | 83 |  | 41.5
D | 70000 | 70001 |  | 1 | UBOLT - ≤4 |  |  |  |  | 35 | EA | 70 |  | 70 | 0 | 35 |  | 70
W | 60000 |  |  |  | STRUCTURAL | [6 empty] | 8899.189 |  | 8899.189 |  |  | 0.75 | 8898.439 | [13 empty] | 3 |  | 0.75
P | 60000 | 60009 |  | 10 | TRIM SAW CONVEYORS | GROUP 2 | [5 empty] | 516.38 |  | 516.38 |  |  | 0.75 | 515.63 | [13 empty] | 3 |  | 0.75
D | 60000 | 60009 |  | 10 | OFFLOAD | GROUP 2 |  |  |  | 5.8 | TON | 8.7 |  | 8.7 | 0 | 5.8 |  | 8.7
D | 60000 | 60009 |  | 10 | SHAKEOUT | GROUP 2 |  |  |  | 5.8 | TON | 11.6 |  | 11.6 | 0 | 5.8 |  | 11.6
D | 60000 | 60009 |  | 10 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 5.8 | TON | 98.6 |  | 98.6 | 0 | 5.8 |  | 98.6
D | 60000 | 60009 |  | 10 | RACK AND RATTLE | GROUP 2 |  |  |  | 5.8 | TON | 17.4 |  | 17.4 | 0 | 5.8 |  | 17.4
D | 60000 | 60009 |  | 10 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 500 | SF | 95 |  | 95 | 0 | 500 |  | 95
D | 60000 | 60009 |  | 10 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 450 | LF | 180 |  | 180 | 0 | 450 |  | 180
D | 60000 | 60009 |  | 10 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 10 | LF | 6.5 |  | 6.5 | 0 | 10 |  | 6.5
D | 60000 | 60009 |  | 10 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 28 | EA | 70 |  | 70 | 0 | 28 |  | 70
D | 60000 | 60009 |  | 10 | INSTALL ANCHORS | GROUP 2 |  |  |  | 112 | EA | 28 |  | 28 | 3 | 109 | 0.75 | 27.25 | 3% | [12 empty] | 3 |  | 0.75
D | 60000 | 60009 |  | 10 | CLEAN UP | GROUP 2 |  |  |  | 5.8 | TON | 0.58 |  | 0.58 | 0 | 5.8 |  | 0.58
P | 60000 | 60009 |  | 13 | STACKER CONVEYORS | GROUP 2 | [5 empty] | 1164.858 |  | 1164.858 |  |  |  | 1164.858
D | 60000 | 60009 |  | 13 | OFFLOAD | GROUP 2 |  |  |  | 11.28 | TON | 16.92 |  | 16.92 | 0 | 11.28 |  | 16.92
D | 60000 | 60009 |  | 13 | SHAKEOUT | GROUP 2 |  |  |  | 11.28 | TON | 22.56 |  | 22.56 | 0 | 11.28 |  | 22.56
D | 60000 | 60009 |  | 13 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 11.28 | TON | 191.76 |  | 191.76 | 0 | 11.28 |  | 191.76
D | 60000 | 60009 |  | 13 | RACK AND RATTLE | GROUP 2 |  |  |  | 11.28 | TON | 33.84 |  | 33.84 | 0 | 11.28 |  | 33.84
D | 60000 | 60009 |  | 13 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 1625 | SF | 308.75 |  | 308.75 | 0 | 1625 |  | 308.75
D | 60000 | 60009 |  | 13 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 892 | LF | 356.8 |  | 356.8 | 0 | 892 |  | 356.8
D | 60000 | 60009 |  | 13 | LADDERS & CAGES | GROUP 2 |  |  |  | 24 | LF | 14.4 |  | 14.4 | 0 | 24 |  | 14.4
D | 60000 | 60009 |  | 13 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 78 | LF | 50.7 |  | 50.7 | 0 | 78 |  | 50.7
D | 60000 | 60009 |  | 13 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 48 | EA | 120 |  | 120 | 0 | 48 |  | 120
D | 60000 | 60009 |  | 13 | INSTALL ANCHORS | GROUP 2 |  |  |  | 192 | EA | 48 |  | 48 | 0 | 192 |  | 48
D | 60000 | 60009 |  | 13 | CLEAN UP | GROUP 2 |  |  |  | 11.28 | TON | 1.128 |  | 1.128 | 0 | 11.28 |  | 1.128
P | 60000 | 60009 |  | 8 | STRAPPERS | GROUP 2 | [5 empty] | 327.616 |  | 327.616 |  |  |  | 327.616
D | 60000 | 60009 |  | 8 | OFFLOAD | GROUP 2 |  |  |  | 3.06 | TON | 4.59 |  | 4.59 | 0 | 3.06 |  | 4.59
D | 60000 | 60009 |  | 8 | SHAKEOUT | GROUP 2 |  |  |  | 3.06 | TON | 6.12 |  | 6.12 | 0 | 3.06 |  | 6.12
D | 60000 | 60009 |  | 8 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 3.06 | TON | 52.02 |  | 52.02 | 0 | 3.06 |  | 52.02
D | 60000 | 60009 |  | 8 | RACK AND RATTLE | GROUP 2 |  |  |  | 3.06 | TON | 9.18 |  | 9.18 | 0 | 3.06 |  | 9.18
D | 60000 | 60009 |  | 8 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 400 | SF | 76 |  | 76 | 0 | 400 |  | 76
D | 60000 | 60009 |  | 8 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 250 | LF | 100 |  | 100 | 0 | 250 |  | 100
D | 60000 | 60009 |  | 8 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 36 | LF | 23.4 |  | 23.4 | 0 | 36 |  | 23.4
D | 60000 | 60009 |  | 8 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 16 | EA | 40 |  | 40 | 0 | 16 |  | 40
D | 60000 | 60009 |  | 8 | INSTALL ANCHORS | GROUP 2 |  |  |  | 64 | EA | 16 |  | 16 | 0 | 64 |  | 16
D | 60000 | 60009 |  | 8 | CLEAN UP | GROUP 2 |  |  |  | 3.06 | TON | 0.306 |  | 0.306 | 0 | 3.06 |  | 0.306
P | 60000 | 60009 |  | 7 | REMAN SAWS | GROUP 2 | [5 empty] | 442.114 |  | 442.114 |  |  |  | 442.114
D | 60000 | 60009 |  | 7 | OFFLOAD | GROUP 2 |  |  |  | 5.99 | TON | 8.985 |  | 8.985 | 0 | 5.99 |  | 8.985
D | 60000 | 60009 |  | 7 | SHAKEOUT | GROUP 2 |  |  |  | 5.99 | TON | 11.98 |  | 11.98 | 0 | 5.99 |  | 11.98
D | 60000 | 60009 |  | 7 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 5.99 | TON | 101.83 |  | 101.83 | 0 | 5.99 |  | 101.83
D | 60000 | 60009 |  | 7 | RACK AND RATTLE | GROUP 2 |  |  |  | 5.99 | TON | 17.97 |  | 17.97 | 0 | 5.99 |  | 17.97
D | 60000 | 60009 |  | 7 | FILLET WELD - 1/4 THK. | GROUP 2 |  |  |  | 0 | LF |  |  |  | 0 | 0
D | 60000 | 60009 |  | 7 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 600 | SF | 114 |  | 114 | 0 | 600 |  | 114
D | 60000 | 60009 |  | 7 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 250 | LF | 100 |  | 100 | 0 | 250 |  | 100
D | 60000 | 60009 |  | 7 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 15 | LF | 9.75 |  | 9.75 | 0 | 15 |  | 9.75
D | 60000 | 60009 |  | 7 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 22 | EA | 55 |  | 55 | 0 | 22 |  | 55
D | 60000 | 60009 |  | 7 | INSTALL ANCHORS | GROUP 2 |  |  |  | 88 | EA | 22 |  | 22 | 0 | 88 |  | 22
D | 60000 | 60009 |  | 7 | CLEAN UP | GROUP 2 |  |  |  | 5.99 | TON | 0.599 |  | 0.599 | 0 | 5.99 |  | 0.599
P | 60000 | 60009 |  | 9 | WRAPPERS | GROUP 3 | [5 empty] | 1574.521 |  | 1574.521 |  |  |  | 1574.521
D | 60000 | 60009 |  | 9 | OFFLOAD | GROUP 3 |  |  |  | 19.56 | TON | 29.34 |  | 29.34 | 0 | 19.56 |  | 29.34
D | 60000 | 60009 |  | 9 | SHAKEOUT | GROUP 3 |  |  |  | 19.56 | TON | 39.12 |  | 39.12 | 0 | 19.56 |  | 39.12
D | 60000 | 60009 |  | 9 | ERECT (0-20 LBS/FT) | GROUP 3 |  |  |  | 6.68 | TON | 113.56 |  | 113.56 | 0 | 6.68 |  | 113.56
D | 60000 | 60009 |  | 9 | ERECT (21-40 LBS/FT) | GROUP 3 |  |  |  | 12.89 | TON | 174.015 |  | 174.015 | 0 | 12.89 |  | 174.015
D | 60000 | 60009 |  | 9 | RACK AND RATTLE | GROUP 3 |  |  |  | 19.56 | TON | 58.68 |  | 58.68 | 0 | 19.56 |  | 58.68
D | 60000 | 60009 |  | 9 | GRATING - 4' X 8' SHEET | GROUP 3 |  |  |  | 2750 | SF | 522.5 |  | 522.5 | 0 | 2750 |  | 522.5
D | 60000 | 60009 |  | 9 | HANDRAIL & TOEPLATE | GROUP 3 |  |  |  | 1099 | LF | 439.6 |  | 439.6 | 0 | 1099 |  | 439.6
D | 60000 | 60009 |  | 9 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 3 |  |  |  | 75 | LF | 48.75 |  | 48.75 | 0 | 75 |  | 48.75
D | 60000 | 60009 |  | 9 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 3 |  |  |  | 42 | EA | 105 |  | 105 | 0 | 42 |  | 105
D | 60000 | 60009 |  | 9 | INSTALL ANCHORS | GROUP 3 |  |  |  | 168 | EA | 42 |  | 42 | 0 | 168 |  | 42
D | 60000 | 60009 |  | 9 | CLEAN UP | GROUP 3 |  |  |  | 19.56 | TON | 1.956 |  | 1.956 | 0 | 19.56 |  | 1.956
P | 60000 | 60009 |  | 1 | END TRIM SAW | GROUP 1 | [5 empty] | 515.176 |  | 515.176 |  |  |  | 515.176
D | 60000 | 60009 |  | 1 | OFFLOAD | GROUP 1 |  |  |  | 7.81 | TON | 11.715 |  | 11.715 | 0 | 7.81 |  | 11.715
D | 60000 | 60009 |  | 1 | SHAKEOUT | GROUP 1 |  |  |  | 7.81 | TON | 15.62 |  | 15.62 | 0 | 7.81 |  | 15.62
D | 60000 | 60009 |  | 1 | ERECT (0-20 LBS/FT) | GROUP 1 |  |  |  | 7.81 | TON | 132.77 |  | 132.77 | 0 | 7.81 |  | 132.77
D | 60000 | 60009 |  | 1 | RACK AND RATTLE | GROUP 1 |  |  |  | 7.81 | TON | 23.43 |  | 23.43 | 0 | 7.81 |  | 23.43
D | 60000 | 60009 |  | 1 | GRATING - 4' X 8' SHEET | GROUP 1 |  |  |  | 1044 | SF | 198.36 |  | 198.36 | 0 | 1044 |  | 198.36
D | 60000 | 60009 |  | 1 | HANDRAIL & TOEPLATE | GROUP 1 |  |  |  | 175 | LF | 70 |  | 70 | 0 | 175 |  | 70
D | 60000 | 60009 |  | 1 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 1 |  |  |  | 10 | LF | 6.5 |  | 6.5 | 0 | 10 |  | 6.5
D | 60000 | 60009 |  | 1 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 1 |  |  |  | 16 | EA | 40 |  | 40 | 0 | 16 |  | 40
D | 60000 | 60009 |  | 1 | INSTALL ANCHORS | GROUP 1 |  |  |  | 64 | EA | 16 |  | 16 | 0 | 64 |  | 16
D | 60000 | 60009 |  | 1 | CLEAN UP | GROUP 1 |  |  |  | 7.81 | TON | 0.781 |  | 0.781 | 0 | 7.81 |  | 0.781
P | 60000 | 60009 |  | 6 | RIP SAW | GROUP 2 | [5 empty] | 386.516 |  | 386.516 |  |  |  | 386.516
D | 60000 | 60009 |  | 6 | OFFLOAD | GROUP 2 |  |  |  | 7.81 | TON | 11.715 |  | 11.715 | 0 | 7.81 |  | 11.715
D | 60000 | 60009 |  | 6 | SHAKEOUT | GROUP 2 |  |  |  | 7.81 | TON | 15.62 |  | 15.62 | 0 | 7.81 |  | 15.62
D | 60000 | 60009 |  | 6 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 7.81 | TON | 132.77 |  | 132.77 | 0 | 7.81 |  | 132.77
D | 60000 | 60009 |  | 6 | RACK AND RATTLE | GROUP 2 |  |  |  | 7.81 | TON | 23.43 |  | 23.43 | 0 | 7.81 |  | 23.43
D | 60000 | 60009 |  | 6 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 500 | SF | 95 |  | 95 | 0 | 500 |  | 95
D | 60000 | 60009 |  | 6 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 150 | LF | 60 |  | 60 | 0 | 150 |  | 60
D | 60000 | 60009 |  | 6 | LADDERS & CAGES | GROUP 2 |  |  |  | 8 | LF | 4.8 |  | 4.8 | 0 | 8 |  | 4.8
D | 60000 | 60009 |  | 6 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 6 | LF | 3.9 |  | 3.9 | 0 | 6 |  | 3.9
D | 60000 | 60009 |  | 6 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 11 | EA | 27.5 |  | 27.5 | 0 | 11 |  | 27.5
D | 60000 | 60009 |  | 6 | INSTALL ANCHORS | GROUP 2 |  |  |  | 44 | EA | 11 |  | 11 | 0 | 44 |  | 11
D | 60000 | 60009 |  | 6 | CLEAN UP | GROUP 2 |  |  |  | 7.81 | TON | 0.781 |  | 0.781 | 0 | 7.81 |  | 0.781
P | 60000 | 60009 |  | 3 | HORIZONTAL COOLERS | GROUP 1 | [5 empty] | 2091.116 |  | 2091.116 |  |  |  | 2091.116
D | 60000 | 60009 |  | 3 | OFFLOAD | GROUP 1 |  |  |  | 23.06 | TON | 34.59 |  | 34.59 | 0 | 23.06 |  | 34.59
D | 60000 | 60009 |  | 3 | SHAKEOUT | GROUP 1 |  |  |  | 23.06 | TON | 46.12 |  | 46.12 | 0 | 23.06 |  | 46.12
D | 60000 | 60009 |  | 3 | ERECT (0-20 LBS/FT) | GROUP 1 |  |  |  | 23.06 | TON | 392.02 |  | 392.02 | 0 | 23.06 |  | 392.02
D | 60000 | 60009 |  | 3 | RACK AND RATTLE | GROUP 1 |  |  |  | 23.06 | TON | 69.18 |  | 69.18 | 0 | 23.06 |  | 69.18
D | 60000 | 60009 |  | 3 | GRATING - 4' X 8' SHEET | GROUP 1 |  |  |  | 3750 | SF | 712.5 |  | 712.5 | 0 | 3750 |  | 712.5
D | 60000 | 60009 |  | 3 | HANDRAIL & TOEPLATE | GROUP 1 |  |  |  | 1625 | LF | 650 |  | 650 | 0 | 1625 |  | 650
D | 60000 | 60009 |  | 3 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 1 |  |  |  | 36 | LF | 23.4 |  | 23.4 | 0 | 36 |  | 23.4
D | 60000 | 60009 |  | 3 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 1 |  |  |  | 46 | EA | 115 |  | 115 | 0 | 46 |  | 115
D | 60000 | 60009 |  | 3 | INSTALL ANCHORS | GROUP 1 |  |  |  | 184 | EA | 46 |  | 46 | 0 | 184 |  | 46
D | 60000 | 60009 |  | 3 | CLEAN UP | GROUP 1 |  |  |  | 23.06 | TON | 2.306 |  | 2.306 | 0 | 23.06 |  | 2.306
P | 60000 | 60009 |  | 12 | SANDER LINE CONVEYORS | GROUP 2 | [5 empty] | 1880.892 |  | 1880.892 |  |  |  | 1880.892
D | 60000 | 60009 |  | 12 | OFFLOAD | GROUP 2 |  |  |  | 20.27 | TON | 30.405 |  | 30.405 | 0 | 20.27 |  | 30.405
D | 60000 | 60009 |  | 12 | SHAKEOUT | GROUP 2 |  |  |  | 20.27 | TON | 40.54 |  | 40.54 | 0 | 20.27 |  | 40.54
D | 60000 | 60009 |  | 12 | ERECT (0-20 LBS/FT) | GROUP 2 |  |  |  | 18.29 | TON | 310.93 |  | 310.93 | 0 | 18.29 |  | 310.93
D | 60000 | 60009 |  | 12 | ERECT (21-40 LBS/FT) | GROUP 2 |  |  |  | 1.98 | TON | 26.73 |  | 26.73 | 0 | 1.98 |  | 26.73
D | 60000 | 60009 |  | 12 | RACK AND RATTLE | GROUP 2 |  |  |  | 20.27 | TON | 60.81 |  | 60.81 | 0 | 20.27 |  | 60.81
D | 60000 | 60009 |  | 12 | GRATING - 4' X 8' SHEET | GROUP 2 |  |  |  | 3075 | SF | 584.25 |  | 584.25 | 0 | 3075 |  | 584.25
D | 60000 | 60009 |  | 12 | HANDRAIL & TOEPLATE | GROUP 2 |  |  |  | 1021 | LF | 408.4 |  | 408.4 | 0 | 1021 |  | 408.4
D | 60000 | 60009 |  | 12 | STAIRS - FIELD ERECT - 3'0 WIDE | GROUP 2 |  |  |  | 92 | LF | 59.8 |  | 59.8 | 0 | 92 |  | 59.8
D | 60000 | 60009 |  | 12 | GROUTING - 12"X12" BASEPLATE - 1" THK. | GROUP 2 |  |  |  | 102 | EA | 255 |  | 255 | 0 | 102 |  | 255
D | 60000 | 60009 |  | 12 | INSTALL ANCHORS | GROUP 2 |  |  |  | 408 | EA | 102 |  | 102 | 0 | 408 |  | 102
D | 60000 | 60009 |  | 12 | CLEAN UP | GROUP 2 |  |  |  | 20.27 | TON | 2.027 |  | 2.027 | 0 | 20.27 |  | 2.027
W | 140000 |  |  |  | REFRACTORY
W | 190000 |  |  |  | DEMOBILIZE | [6 empty] | 90 |  | 90 |  |  | 34 | 56 | 38% | [13 empty] | 5 |  | 34
P | 190000 | 190002 |  |  | EQUIPMENT REMOVAL | [6 empty] | 50 |  | 50 |  |  | 24 | 26 | 48% | [13 empty] | 4 |  | 24
D | 190000 | 190002 |  |  | TOOLS |  |  |  |  | 1 | EA | 10 |  | 10 | 1 | 0 | 10 |  | 100% | [13 empty] | 1 |  | 10
D | 190000 | 190002 |  |  | EQUIPMENT |  |  |  |  | 10 | EA | 20 |  | 20 | 2 | 8 | 4 | 16 | 20% | [13 empty] | 2 |  | 4
D | 190000 | 190002 |  |  | CRANES |  |  |  |  | 2 | EA | 20 |  | 20 | 1 | 1 | 10 | 10 | 50% | [13 empty] | 1 |  | 10
P | 190000 | 190003 |  |  | TRAILER REMOVAL | [6 empty] | 20 |  | 20 |  |  | 10 | 10 | 50% | [13 empty] | 1 |  | 10
D | 190000 | 190003 |  |  | OFFICE TRAILER |  |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 190000 | 190003 |  |  | TOOL TRAILER |  |  |  |  | 1 | EA | 10 |  | 10 | 1 | 0 | 10 |  | 100% | [13 empty] | 1 |  | 10
P | 190000 | 190005 |  |  | DISCONNECT UTILITIES
P | 190000 | 190006 |  |  | FREIGHT OUT
P | 190000 | 190001 |  |  | SITE CLEAN UP | [6 empty] | 20 |  | 20 |  |  |  | 20
D | 190000 | 190001 |  |  | DURING CONSTRUCTION |  |  |  |  | 2 | DAY | 20 |  | 20 | 0 | 2 |  | 20
W | 200000 |  |  |  | SUPPORT | [6 empty] | 3800 |  | 3800 |  |  | 950 | 2850 | 25% | [13 empty] | 19 |  | 950
P | 200000 | 209980 |  |  | IT SERVICES
P | 200000 | 200100 |  |  | PROJECT MANAGER | [6 empty] | 950 |  | 950 |  |  | 350 | 600 | 37% | [13 empty] | 7 |  | 350
D | 200000 | 200100 |  |  | WEEK (50 HRS) |  |  |  |  | 19 | WEEK | 950 |  | 950 | 7 | 12 | 350 | 600 | 37% | [13 empty] | 7 |  | 350
P | 200000 | 200200 |  |  | PROJECT SUPERINTENDENT | [6 empty] | 950 |  | 950 |  |  | 600 | 350 | 63% | [13 empty] | 12 |  | 600
D | 200000 | 200200 |  |  | WEEK (50 HRS) |  |  |  |  | 19 | WEEK | 950 |  | 950 | 12 | 7 | 600 | 350 | 63% | [13 empty] | 12 |  | 600
P | 200000 | 200600 |  |  | SAFETY TECH | [6 empty] | 950 |  | 950 |  |  |  | 950
D | 200000 | 200600 |  |  | WEEK (50 HRS) |  |  |  |  | 19 | WEEK | 950 |  | 950 | 0 | 19 |  | 950
P | 200000 | 201010 |  |  | FIELD OFFICE | [6 empty] | 950 |  | 950 |  |  |  | 950
D | 200000 | 201010 |  |  | WEEK (50 HRS) |  |  |  |  | 19 | WEEK | 950 |  | 950 | 0 | 19 |  | 950
P | 200000 | 209999 |  |  | EQUIPMENT
W | 40000 |  |  |  | TOWERS/VESSELS/EQUIPMENT | [6 empty] | 17309.1825 | 2365.5 | 19674.6825 |  |  | 9.5 | 19665.1825 | [14 empty] | 5.25 |  | 9.5
P | 40000 | 40001 |  | 5 | CROSS CUT SAW | #5 | [5 empty] | 130.6875 |  | 130.6875 |  |  | 9.5 | 121.1875 | 7% | [13 empty] | 5.25 |  | 9.5
D | 40000 | 40001 |  | 5 | CRANE SETUP | #5 |  |  |  | 1 | EA | 2 |  | 2 | 1 | 0 | 2 |  | 100% | [13 empty] | 1 |  | 2
D | 40000 | 40001 |  | 5 | OFFLOAD | #5 |  |  |  | 0.25 | TON | 0.5 |  | 0.5 | 0.25 | 0 | 0.5 |  | 100% | [13 empty] | 0.25 |  | 0.5
D | 40000 | 40001 |  | 5 | LAYOUT / VERIFY | #5 |  |  |  | 1 | EA | 4 |  | 4 | 1 | 0 | 4 |  | 100% | [13 empty] | 1 |  | 4
D | 40000 | 40001 |  | 5 | INSTALL ANCHOR BOLTS | #5 |  |  |  | 8 | EA | 8 |  | 8 | 3 | 5 | 3 | 5 | 38% | [13 empty] | 3 |  | 3
D | 40000 | 40001 |  | 5 | HAUL & SET ON FOUNDATION | #5 |  |  |  | 0.25 | TON | 3 |  | 3 | 0 | 0.25 |  | 3
D | 40000 | 40001 |  | 5 | SHIM | #5 |  |  |  | 2 | EA | 3 |  | 3 | 0 | 2 |  | 3
D | 40000 | 40001 |  | 5 | SECURE | #5 |  |  |  | 8 | EA | 8 |  | 8 | 0 | 8 |  | 8
D | 40000 | 40001 |  | 5 | TRIM | #5 |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 5 | INSTALL MISC EQUIPMENT ( | #5 |  |  |  | 3 | EA | 90 |  | 90 | 0 | 3 |  | 90
D | 40000 | 40001 |  | 5 | CRANE REMOVAL | #5 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 5 | CLEAN UP | #5 |  |  |  | 0.25 | TON | 0.1875 |  | 0.1875 | 0 | 0.25 |  | 0.1875
P | 40000 | 40001 |  | 14 | PACKAGE LINE 2 CONVEYORS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  |  |  | 750.52 |  | 750.52 |  |  |  | 750.52
D | 40000 | 40001 |  | 14 | HAUL & SET ON FOUNDATION | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 12 | EA | 120 |  | 120 | 0 | 12 |  | 120
D | 40000 | 40001 |  | 14 | OFFLOAD | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 12 | EA | 120 |  | 120 | 0 | 12 |  | 120
D | 40000 | 40001 |  | 14 | OFFLOAD SHAFT | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 1 | TON | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 14 | LAYOUT / VERIFY ROLLER CONVEYORS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 12 | EA | 48 |  | 48 | 0 | 12 |  | 48
D | 40000 | 40001 |  | 14 | LAYOUT / VERIFY TRANSFER CHAIN 515 | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 7 | EA | 28 |  | 28 | 0 | 7 |  | 28
D | 40000 | 40001 |  | 14 | SET DRIVE MOTOR SUPPORT | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 5 | EA | 10 |  | 10 | 0 | 5 |  | 10
D | 40000 | 40001 |  | 14 | INSTALL DRIVE MOTORS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 5 | EA | 5 |  | 5 | 0 | 5 |  | 5
D | 40000 | 40001 |  | 14 | INSTALL DRIVE CHAINS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 12 | EA | 6.6 |  | 6.6 | 0 | 12 |  | 6.6
D | 40000 | 40001 |  | 14 | LAYOUT / VERIFY ROLLOR CONVEYOR | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 9 | EA | 36 |  | 36 | 0 | 9 |  | 36
D | 40000 | 40001 |  | 14 | SET AND SECURE ROLLER CONVEYOR | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 262 | LF | 73.36 |  | 73.36 | 0 | 262 |  | 73.36
D | 40000 | 40001 |  | 14 | INSTALL ANCHOR BOLTS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 260 | EA | 65 |  | 65 | 0 | 260 |  | 65
D | 40000 | 40001 |  | 14 | HAUL & SET ON FOUNDATION SHAFT | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 1 | TON | 6 |  | 6 | 0 | 1 |  | 6
D | 40000 | 40001 |  | 14 | HAUL & SET ON FOUNDATION TRANSFER CHAIN | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 7 | EA | 84 |  | 84 | 0 | 7 |  | 84
D | 40000 | 40001 |  | 14 | PRECISION ALIGNMENT | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 7 | EA | 21 |  | 21 | 0 | 7 |  | 21
D | 40000 | 40001 |  | 14 | GROUT FORMING | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 280 | LF | 14 |  | 14 | 0 | 280 |  | 14
D | 40000 | 40001 |  | 14 | GROUTING - CEMENTIOUTS | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 4 | CF | 8 |  | 8 | 0 | 4 |  | 8
D | 40000 | 40001 |  | 14 | BUSHHAMMERING | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 48 | SF | 9.6 |  | 9.6 | 0 | 48 |  | 9.6
D | 40000 | 40001 |  | 14 | INSTALL STRAPPER 503 | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 1 | EA | 25 |  | 25 | 0 | 1 |  | 25
D | 40000 | 40001 |  | 14 | INSTALL CUT SAW 506 | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 1 | EA | 25 |  | 25 | 0 | 1 |  | 25
D | 40000 | 40001 |  | 14 | INSTALL DRIVE MOTORS 515 | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 14 | INSTALL 515 DRIVE SHAFT | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 14 | CLEAN UP | #15 | 8504,8505,8606,8607,8508,8610,8513,8615,8514,8616,8515 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
P | 40000 | 40001 |  | 4 | SANDER | #6 | [5 empty] | 181.66 |  | 181.66 |  |  |  | 181.66
D | 40000 | 40001 |  | 4 | CRANE SETUP | #6 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 4 | OFFLOAD | #6 |  |  |  | 2 | TON | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 4 | LAYOUT / VERIFY | #6 |  |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 4 | INSTALL ANCHOR BOLTS | #6 |  |  |  | 24 | EA | 24 |  | 24 | 0 | 24 |  | 24
D | 40000 | 40001 |  | 4 | HAUL & SET ON FOUNDATION | #6 |  |  |  | 2 | TON | 12 |  | 12 | 0 | 2 |  | 12
D | 40000 | 40001 |  | 4 | SHIM | #6 |  |  |  | 8 | EA | 12 |  | 12 | 0 | 8 |  | 12
D | 40000 | 40001 |  | 4 | SECURE | #6 |  |  |  | 24 | EA | 8.4 |  | 8.4 | 0 | 24 |  | 8.4
D | 40000 | 40001 |  | 4 | INSTALL ROLLERS | #6 |  |  |  | 1 | EA | 5 |  | 5 | 0 | 1 |  | 5
D | 40000 | 40001 |  | 4 | GROUT FORMING | #6 |  |  |  | 98 | LF | 11.76 |  | 11.76 | 0 | 98 |  | 11.76
D | 40000 | 40001 |  | 4 | BUSHHAMMERING | #6 |  |  |  | 36 | SF | 9 |  | 9 | 0 | 36 |  | 9
D | 40000 | 40001 |  | 4 | GROUTING - CEMENTIOUTS | #6 |  |  |  | 3 | CF | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 4 | TRIM | #6 |  |  |  | 4 | EA | 80 |  | 80 | 0 | 4 |  | 80
D | 40000 | 40001 |  | 4 | CRANE REMOVAL | #6 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 4 | CLEAN UP | #6 |  |  |  | 2 | TON | 1.5 |  | 1.5 | 0 | 2 |  | 1.5
P | 40000 | 40001 |  | 15 | PACKAGE LINE 3 CONVEYOR | #16 | 8617 |  |  |  |  | 750.52 |  | 750.52 |  |  |  | 750.52
D | 40000 | 40001 |  | 15 | HAUL & SET ON FOUNDATION | #16 | 8617 |  |  | 12 | EA | 120 |  | 120 | 0 | 12 |  | 120
D | 40000 | 40001 |  | 15 | OFFLOAD SHAFT | #16 | 8617 |  |  | 1 | TON | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 15 | OFFLOAD | #16 | 8617 |  |  | 12 | EA | 120 |  | 120 | 0 | 12 |  | 120
D | 40000 | 40001 |  | 15 | LAYOUT / VERIFY ROLLER CONVEYORS | #16 | 8617 |  |  | 12 | EA | 48 |  | 48 | 0 | 12 |  | 48
D | 40000 | 40001 |  | 15 | LAYOUT / VERIFY TRANSFER CHAIN 617 | #16 | 8617 |  |  | 7 | EA | 28 |  | 28 | 0 | 7 |  | 28
D | 40000 | 40001 |  | 15 | SET DRIVE MOTOR SUPPORT | #16 | 8617 |  |  | 5 | EA | 10 |  | 10 | 0 | 5 |  | 10
D | 40000 | 40001 |  | 15 | INSTALL DRIVE MOTORS | #16 | 8617 |  |  | 5 | EA | 5 |  | 5 | 0 | 5 |  | 5
D | 40000 | 40001 |  | 15 | INSTALL DRIVE CHAINS | #16 | 8617 |  |  | 12 | EA | 6.6 |  | 6.6 | 0 | 12 |  | 6.6
D | 40000 | 40001 |  | 15 | LAYOUT / VERIFY ROLLOR CONVEYOR | #16 | 8617 |  |  | 9 | EA | 36 |  | 36 | 0 | 9 |  | 36
D | 40000 | 40001 |  | 15 | SET AND SECURE ROLLER CONVEYOR | #16 | 8617 |  |  | 262 | LF | 73.36 |  | 73.36 | 0 | 262 |  | 73.36
D | 40000 | 40001 |  | 15 | INSTALL ANCHOR BOLTS | #16 | 8617 |  |  | 260 | EA | 65 |  | 65 | 0 | 260 |  | 65
D | 40000 | 40001 |  | 15 | HAUL & SET ON FOUNDATION SHAFT | #16 | 8617 |  |  | 1 | TON | 6 |  | 6 | 0 | 1 |  | 6
D | 40000 | 40001 |  | 15 | HAUL & SET ON FOUNDATION TRANSFER CHAIN 617 | #16 | 8617 |  |  | 7 | EA | 84 |  | 84 | 0 | 7 |  | 84
D | 40000 | 40001 |  | 15 | PRECISION ALIGNMENT | #16 | 8617 |  |  | 7 | EA | 21 |  | 21 | 0 | 7 |  | 21
D | 40000 | 40001 |  | 15 | GROUT FORMING | #16 | 8617 |  |  | 280 | LF | 14 |  | 14 | 0 | 280 |  | 14
D | 40000 | 40001 |  | 15 | GROUTING - CEMENTIOUTS | #16 | 8617 |  |  | 4 | CF | 8 |  | 8 | 0 | 4 |  | 8
D | 40000 | 40001 |  | 15 | BUSHHAMMERING | #16 | 8617 |  |  | 48 | SF | 9.6 |  | 9.6 | 0 | 48 |  | 9.6
D | 40000 | 40001 |  | 15 | INSTALL STRAPPER 503 | #16 | 8617 |  |  | 1 | EA | 25 |  | 25 | 0 | 1 |  | 25
D | 40000 | 40001 |  | 15 | INSTALL CUT SAW 506 | #16 | 8617 |  |  | 1 | EA | 25 |  | 25 | 0 | 1 |  | 25
D | 40000 | 40001 |  | 15 | INSTALL DRIVE MOTORS 515 | #16 | 8617 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 15 | INSTALL 617 DRIVE SHAFT | #16 | 8617 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 15 | CLEAN UP | #16 | 8617 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
P | 40000 | 40001 |  | 1 | END TRIM SAW AND DUAL TRIM SAW | #1 | 8105 |  |  |  |  | 224.27 |  | 224.27 |  |  |  | 224.27
D | 40000 | 40001 |  | 1 | CRANE SETUP | #1 | 8105 |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 1 | OFFLOAD | #1 | 8105 |  |  | 8 | TON | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 1 | LAYOUT / VERIFY | #1 | 8105 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 1 | INSTALL ANCHOR BOLTS | #1 | 8105 |  |  | 16 | EA | 64 |  | 64 | 0 | 16 |  | 64
D | 40000 | 40001 |  | 1 | HAUL & SET ON FOUNDATION | #1 | 8105 |  |  | 8 | TON | 48 |  | 48 | 0 | 8 |  | 48
D | 40000 | 40001 |  | 1 | SHIM | #1 | 8105 |  |  | 8 | EA | 12 |  | 12 | 0 | 8 |  | 12
D | 40000 | 40001 |  | 1 | SECURE | #1 | 8105 |  |  | 3 | EA | 3 |  | 3 | 0 | 3 |  | 3
D | 40000 | 40001 |  | 1 | INSTALL ROLLERS | #1 | 8105 |  |  | 1 | EA | 5 |  | 5 | 0 | 1 |  | 5
D | 40000 | 40001 |  | 1 | INSTALL MOTORS | #1 | 8105 |  |  | 8 | EA | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 1 | PRECISION ALIGNMENT | #1 | 8105 |  |  | 8 | EA | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 1 | BUSHAMMERING | #1 | 8105 |  |  | 1.56 | SF | 0.39 |  | 0.39 | 0 | 1.56 |  | 0.39
D | 40000 | 40001 |  | 1 | GROUT FORMING | #1 | 8105 |  |  | 15 | LF | 0.75 |  | 0.75 | 0 | 15 |  | 0.75
D | 40000 | 40001 |  | 1 | GROUTING - CEMENTIOUTS | #1 | 8105 |  |  | 0.13 | CF | 0.13 |  | 0.13 | 0 | 0.13 |  | 0.13
D | 40000 | 40001 |  | 1 | TRIM | #1 | 8105 |  |  | 4 | EA | 32 |  | 32 | 0 | 4 |  | 32
D | 40000 | 40001 |  | 1 | CRANE REMOVAL | #1 | 8105 |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 1 | CLEAN UP | #1 | 8105 |  |  | 4 | TON | 3 |  | 3 | 0 | 4 |  | 3
P | 40000 | 40001 |  | 12 | SANDER LINE CONVEYORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  |  |  | 2784.23 |  | 2784.23 |  |  |  | 2784.23
D | 40000 | 40001 |  | 12 | CRANE SETUP | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 12 | OFFLOAD SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4.8 | TON | 9.6 |  | 9.6 | 0 | 4.8 |  | 9.6
D | 40000 | 40001 |  | 12 | OFFLOAD | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 19 | EA | 190 |  | 190 | 0 | 19 |  | 190
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY BUNK PLACER 214 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY OUTFEED CONVEYOR 212 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY CONVEYOR 202 SUPPORT STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 5 | EA | 10 |  | 10 | 0 | 5 |  | 10
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY ROLLER CONVEYOR 234,237 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY TRANSFER CONVEYOR 225 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY CONVEYOR 210 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY LIFT 224 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY ROLLER CONVEYOR 231 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY STACKER 211 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY ROLLER CONVEYOR 213 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY ROLLER CONVEYOR 220, 222 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY ROLLER CONVEYOR 215 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | LAYOUT / VERIFY TRANSFER CONVEYOR 223 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL ANCHOR BOLTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 510 | EA | 127.5 |  | 127.5 | 0 | 510 |  | 127.5
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION LIFT 224 STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 5.5 | TON | 33 |  | 33 | 0 | 5.5 |  | 33
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION ROLLER CONVEYOR 231 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 3.5 | TON | 21 |  | 21 | 0 | 3.5 |  | 21
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION LIFT 224 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 36 |  | 36 | 0 | 9 |  | 36
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION CONVEYOR 202 SUPPORT STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 14 | TON | 84 |  | 84 | 0 | 14 |  | 84
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION BUNKER PLACER 214 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | TON | 6 |  | 6 | 0 | 1 |  | 6
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION TRANSFER CONVEYOR 225 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION CONVEYOR 212 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 6 | TON | 36 |  | 36 | 0 | 6 |  | 36
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION ROLLER CONVEYOR 215 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 20 |  | 20 | 0 | 2 |  | 20
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION ROLLER CONVEYOR 213 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 20 |  | 20 | 0 | 2 |  | 20
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4.8 | TON | 28.8 |  | 28.8 | 0 | 4.8 |  | 28.8
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION ROLLER CONVEYOR 220, 222 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4 | EA | 40 |  | 40 | 0 | 4 |  | 40
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION CONVEYOR 210 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 8 | TON | 48 |  | 48 | 0 | 8 |  | 48
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION STACKER 211 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 16 | TON | 96 |  | 96 | 0 | 16 |  | 96
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION ROLLER CONVEYOR 234,237 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 12 | HAUL & SET ON FOUNDATION TRANSFER CONVEYOR 223 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 12 | SHIM | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 100 | EA | 150 |  | 150 | 0 | 100 |  | 150
D | 40000 | 40001 |  | 12 | PRECISION ALIGNMENT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 19 | EA | 57 |  | 57 | 0 | 19 |  | 57
D | 40000 | 40001 |  | 12 | BUSHHAMMERING | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 330 | SF | 66 |  | 66 | 0 | 330 |  | 66
D | 40000 | 40001 |  | 12 | GROUT FORMING | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 691 | LF | 103.65 |  | 103.65 | 0 | 691 |  | 103.65
D | 40000 | 40001 |  | 12 | GROUTING - CEMENTIOUTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 30 | CF | 60 |  | 60 | 0 | 30 |  | 60
D | 40000 | 40001 |  | 12 | CRANE REMOVAL | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 12 | CLEAN UP | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 12 | SET AND SECURE CONVEYOR SECTIONS 210 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4 | EA | 12 |  | 12 | 0 | 4 |  | 12
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 210 SUPPORT FRAMING | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 28 | EA | 23.8 |  | 23.8 | 0 | 28 |  | 23.8
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 210 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 210 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 210 DRAG CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 210 SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 12 | SET AND SECURE STACKER 211 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 12 | INSTALL STACKER LIFT TRACK | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 30 |  | 30 | 0 | 1 |  | 30
D | 40000 | 40001 |  | 12 | SET AND SECURE CONVEYOR 212 SUPPORTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 18 | EA | 54 |  | 54 | 0 | 18 |  | 54
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 212 LIFT SHAFT 6" | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 54 | LF | 22.68 |  | 22.68 | 0 | 54 |  | 22.68
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 212 CHAIN HOUSINGS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | INSTALL 212 SUPPORT BEAM | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 42 | EA | 29.4 |  | 29.4 | 0 | 42 |  | 29.4
D | 40000 | 40001 |  | 12 | INSTALL 212 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL 212 DRIVE SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 54 | LF | 28.62 |  | 28.62 | 0 | 54 |  | 28.62
D | 40000 | 40001 |  | 12 | INSTALL 212 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 12 | INSTALL 212 DRAG CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | SET AND SECURE 213 SUPPORT STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 8 | EA | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 12 | SET AND SECURE 213 ROLLER ASSEMBLY | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL 213 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL 213 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 3 | EA | 1.65 |  | 1.65 | 0 | 3 |  | 1.65
D | 40000 | 40001 |  | 12 | INSTALL ANCHORS - SECTION 202 BYPASS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 100 | EA | 25 |  | 25 | 0 | 100 |  | 25
D | 40000 | 40001 |  | 12 | SET AND SECURE CONVEYOR 202 SUPPORT STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 14 | TON | 203 |  | 203 | 0 | 14 |  | 203
D | 40000 | 40001 |  | 12 | BUSHHAMMERING - SECTION 202 BYPASS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 30 | SF | 4.5 |  | 4.5 | 0 | 30 |  | 4.5
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 202 CHAIN HOUSINGS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | CONVEYOR 202 BOLT UPS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 16 | EA | 2.4 |  | 2.4 | 0 | 16 |  | 2.4
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 202 DRAG CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 202 DRIVE SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 63 | LF | 33.39 |  | 33.39 | 0 | 63 |  | 33.39
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 202 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 202 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 12 | INSTALL BUNKER PLACER 214 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 30 |  | 30 | 0 | 1 |  | 30
D | 40000 | 40001 |  | 12 | SET AND SECURE ROLLER CONVEYOR 215 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 80 | LF | 22.4 |  | 22.4 | 0 | 80 |  | 22.4
D | 40000 | 40001 |  | 12 | INSTALL ROLLER CONVEYOR 215 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 12 | INSTALL ROLLER CONVEYOR 215 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 12 | SET AND SECURE TRANSFER 225 BEAM SUPPORTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 14 | EA | 14 |  | 14 | 0 | 14 |  | 14
D | 40000 | 40001 |  | 12 | SET AND SECURE TRANSFER 225 HOUSING SUPPORTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 27 | EA | 13.5 |  | 13.5 | 0 | 27 |  | 13.5
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 DRAG CHAIN HOUSINGS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 7 | EA | 21 |  | 21 | 0 | 7 |  | 21
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 DRIVE SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 DRAG CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 7 | EA | 10.5 |  | 10.5 | 0 | 7 |  | 10.5
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 12 | INSTALL TRANSFER 225 SUPPORT BEAMS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 12 | TRANSFER 225 BEAM BOLT UPS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 88 | EA | 13.2 |  | 13.2 | 0 | 88 |  | 13.2
D | 40000 | 40001 |  | 12 | SET AND SECURE ROLLER CONVEYOR 220, 222 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 144 | LF | 40.32 |  | 40.32 | 0 | 144 |  | 40.32
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 220, 222 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 4 | EA | 12 |  | 12 | 0 | 4 |  | 12
D | 40000 | 40001 |  | 12 | INSTALL CONVEYOR 220, 222 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 7 | EA | 3.85 |  | 3.85 | 0 | 7 |  | 3.85
D | 40000 | 40001 |  | 12 | SET AND SECURE 223 SUPPORTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 16 | EA | 16 |  | 16 | 0 | 16 |  | 16
D | 40000 | 40001 |  | 12 | INSTALL 223 SUPPORT BEAMS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 12 | INSTALL 223 DRAG CHAIN HOUSINGS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 8 | EA | 12 |  | 12 | 0 | 8 |  | 12
D | 40000 | 40001 |  | 12 | INSTALL 223 DRAG CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 8 | EA | 12 |  | 12 | 0 | 8 |  | 12
D | 40000 | 40001 |  | 12 | INSTALL 223 DRIVE SHAFT | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 57 | LF | 30.21 |  | 30.21 | 0 | 57 |  | 30.21
D | 40000 | 40001 |  | 12 | INSTALL 223 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 12 | INSTALL 223 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 12 | SET AND SECURE LIFT 224 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 9 | EA | 22.5 |  | 22.5 | 0 | 9 |  | 22.5
D | 40000 | 40001 |  | 12 | INSTALL LIFT HOUSING AND ASSEMBLE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 84 | LF | 37.8 |  | 37.8 | 0 | 84 |  | 37.8
D | 40000 | 40001 |  | 12 | INSTALL LIFT 224 CABLE GUARDS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 17 | EA | 4.25 |  | 4.25 | 0 | 17 |  | 4.25
D | 40000 | 40001 |  | 12 | ERECT LIFT 224 STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 5.5 | TON | 79.75 |  | 79.75 | 0 | 5.5 |  | 79.75
D | 40000 | 40001 |  | 12 | INSTALL LIFT 224 DRAGS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 5 | EA | 7.5 |  | 7.5 | 0 | 5 |  | 7.5
D | 40000 | 40001 |  | 12 | INSTALL 230 ROLLERS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 25 | EA | 43.75 |  | 43.75 | 0 | 25 |  | 43.75
D | 40000 | 40001 |  | 12 | INSTALL 230 ROLLER DRIVE MOTOR | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 3 |  | 3 | 0 | 1 |  | 3
D | 40000 | 40001 |  | 12 | INSTALL 230 ROLLER DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 25 | EA | 13.75 |  | 13.75 | 0 | 25 |  | 13.75
D | 40000 | 40001 |  | 12 | INSTALL 230 ROLLER SUPPORTS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 8 | EA | 6.8 |  | 6.8 | 0 | 8 |  | 6.8
D | 40000 | 40001 |  | 12 | INSTALL STATION 221 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 40 |  | 40 | 0 | 1 |  | 40
D | 40000 | 40001 |  | 12 | SET AND SECURE ROLLER CONVEYOR 231 STRUCTURE | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 3.5 | TON | 50.75 |  | 50.75 | 0 | 3.5 |  | 50.75
D | 40000 | 40001 |  | 12 | INSTALL 231 DRIVE MOTOR | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 1 | EA | 3 |  | 3 | 0 | 1 |  | 3
D | 40000 | 40001 |  | 12 | INSTALL 231 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 32 | EA | 17.6 |  | 17.6 | 0 | 32 |  | 17.6
D | 40000 | 40001 |  | 12 | INSTALL 231 ROLLERS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 31 | EA | 54.25 |  | 54.25 | 0 | 31 |  | 54.25
D | 40000 | 40001 |  | 12 | SET AND SECURE ROLLER CONVEYOR 234,237 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 138 | LF | 38.64 |  | 38.64 | 0 | 138 |  | 38.64
D | 40000 | 40001 |  | 12 | INSTALL 234,237 DRIVE MOTORS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 12 | INSTALL 234,237 DRIVE CHAINS | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 10 | EA | 5.5 |  | 5.5 | 0 | 10 |  | 5.5
D | 40000 | 40001 |  | 12 | INSTALL SMAPLE BIN 238-239 | #5 | 8210,8211,8212,8213,8202,8215,8225,8220,8222,8223,8224,8230,8231,8234,8237 |  |  | 2 | EA | 40 |  | 40 | 0 | 2 |  | 40
P | 40000 | 40001 |  | 13 | STACKER CONVEYORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  |  |  | 3175.41 |  | 3175.41 |  |  |  | 3175.41
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 7 | EA | 70 |  | 70 | 0 | 7 |  | 70
D | 40000 | 40001 |  | 13 | OFFLOAD SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 14.3 | TON | 28.6 |  | 28.6 | 0 | 14.3 |  | 28.6
D | 40000 | 40001 |  | 13 | OFFLOAD | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 21 | EA | 210 |  | 210 | 0 | 21 |  | 210
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 501 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 404 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 323 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 401 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 403 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 521 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 602 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 245 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 320 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 502 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 307 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 403 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 322 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 604 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 306,303,302 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY 520,522 ROLLER CONVEYORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 603 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | LAYOUT / VERIFY TRANSFER 601 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | INSTALL ANCHOR BOLTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 740 | EA | 185 |  | 185 | 0 | 740 |  | 185
D | 40000 | 40001 |  | 13 | SET 502 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 14 | EA | 11.9 |  | 11.9 | 0 | 14 |  | 11.9
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 603 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 13 | SET 245 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 3.4 |  | 3.4 | 0 | 4 |  | 3.4
D | 40000 | 40001 |  | 13 | INSTALL 245 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | INSTALL 502 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 14.3 | TON | 85.8 |  | 85.8 | 0 | 14.3 |  | 85.8
D | 40000 | 40001 |  | 13 | SET AND SECURE 520,522 ROLLER CONVEYORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 152 | LF | 22.8 |  | 22.8 | 0 | 152 |  | 22.8
D | 40000 | 40001 |  | 13 | INSTALL 502 ROLLER DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 13 | SET 404 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 16 | EA | 13.6 |  | 13.6 | 0 | 16 |  | 13.6
D | 40000 | 40001 |  | 13 | INSTALL 520,522 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | INSTALL 245 ROLLER DRIVE MOTOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 13 | SET 604 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 14 | EA | 11.9 |  | 11.9 | 0 | 14 |  | 11.9
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 401 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 13 | SET AND SECURE 245 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 70 | LF | 10.5 |  | 10.5 | 0 | 70 |  | 10.5
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 602 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 16 | TON | 96 |  | 96 | 0 | 16 |  | 96
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 322 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | INSTALL 307 ROLLER DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 160 | LF | 84.8 |  | 84.8 | 0 | 160 |  | 84.8
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 521 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 13 | INSTALL 307 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | SET 307 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 12 | EA | 10.2 |  | 10.2 | 0 | 12 |  | 10.2
D | 40000 | 40001 |  | 13 | INSTALL 520,522 ROLLER DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 306,303,302 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 30 |  | 30 | 0 | 3 |  | 30
D | 40000 | 40001 |  | 13 | SET AND SECURE 502 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 70 | LF | 19.6 |  | 19.6 | 0 | 70 |  | 19.6
D | 40000 | 40001 |  | 13 | SET AND SECURE 404 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 75 | LF | 21 |  | 21 | 0 | 75 |  | 21
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 403 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | INSTALL 404 ROLLER DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 13 | SET AND SECURE 604 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 70 | LF | 10.5 |  | 10.5 | 0 | 70 |  | 10.5
D | 40000 | 40001 |  | 13 | INSTALL 604 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | SET AND SECURE 307 ROLLER CONVEYOR | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 70 | LF | 19.6 |  | 19.6 | 0 | 70 |  | 19.6
D | 40000 | 40001 |  | 13 | INSTALL 404 ROLLER DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 1.65 |  | 1.65 | 0 | 3 |  | 1.65
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 403 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 501 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 320 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | INSTALL 604 ROLLER DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 323 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 13 | HAUL & SET ON FOUNDATION TRANSFER 601 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 13 | SET 520,522 ROLLER SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 28 | EA | 23.8 |  | 23.8 | 0 | 28 |  | 23.8
D | 40000 | 40001 |  | 13 | PRECISION ALIGNMENT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 32 | EA | 96 |  | 96 | 0 | 32 |  | 96
D | 40000 | 40001 |  | 13 | GROUT FORMING | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 740 | LF | 74 |  | 74 | 0 | 740 |  | 74
D | 40000 | 40001 |  | 13 | GROUTING - CEMENTIOUTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 24.98 | CF | 49.96 |  | 49.96 | 0 | 24.98 |  | 49.96
D | 40000 | 40001 |  | 13 | CLEAN UP | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 13 | BUSHHAMMERING | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 296 | SF | 59.2 |  | 59.2 | 0 | 296 |  | 59.2
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 306,303,302 SUPPORTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 52 | EA | 91 |  | 91 | 0 | 52 |  | 91
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 306,303,302 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 31 | EA | 46.5 |  | 46.5 | 0 | 31 |  | 46.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 306,303,302 DRAG TRAIN | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 31 | EA | 46.5 |  | 46.5 | 0 | 31 |  | 46.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 306,303,302 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 178 | LF | 94.34 |  | 94.34 | 0 | 178 |  | 94.34
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 306,303,302 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 306,303,302 DRIVE CHAIN | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 320 SUPPORT FRAMES | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 9 |  | 9 | 0 | 3 |  | 9
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 320 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 320 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 320 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 320 DRIVE CHAIN | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 0.55 |  | 0.55 | 0 | 1 |  | 0.55
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 320 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 401 SUPPORT FRAMING | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 36 |  | 36 | 0 | 9 |  | 36
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 22.5 |  | 22.5 | 0 | 9 |  | 22.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 DRAG CHAIN | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 8" LIFT SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 71.3 |  | 71.3 | 0 | 62 |  | 71.3
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 401 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 403 SUPPORT FRAMING | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE SHAFTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 124 | LF | 65.72 |  | 65.72 | 0 | 124 |  | 65.72
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 322 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 32 |  | 32 | 0 | 2 |  | 32
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 322 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 322 DRAG CHANIS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 22.5 |  | 22.5 | 0 | 9 |  | 22.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 322 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 322 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 322 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 403 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRAG CHAIN | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 3 | EA | 1.65 |  | 1.65 | 0 | 3 |  | 1.65
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 403 DRIVE SHAFTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 124 | LF | 65.72 |  | 65.72 | 0 | 124 |  | 65.72
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 501 SSUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 7 | EA | 28 |  | 28 | 0 | 7 |  | 28
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 501 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 22.5 |  | 22.5 | 0 | 9 |  | 22.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 501 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 501 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 501 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 501 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 50 | LF | 26.5 |  | 26.5 | 0 | 50 |  | 26.5
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 323 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 30 |  | 30 | 0 | 1 |  | 30
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 323 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 323 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 323 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 323 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 323 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 601 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 601 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 601 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 601 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 16 |  | 16 | 0 | 4 |  | 16
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 601 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 601 DRIVE SHAFTS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 124 | LF | 65.72 |  | 65.72 | 0 | 124 |  | 65.72
D | 40000 | 40001 |  | 13 | SET AND SECURE STACKER 602 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL STACKER LIFT TRACK 602 | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 1 | EA | 30 |  | 30 | 0 | 1 |  | 30
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 603 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 18 | EA | 72 |  | 72 | 0 | 18 |  | 72
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 603 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 603 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 9 | EA | 18 |  | 18 | 0 | 9 |  | 18
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 603 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 603 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 603 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 13 | SET AND SECURE TRANSFER 521 SUPPORT STRUCTURE | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 14 | EA | 42 |  | 42 | 0 | 14 |  | 42
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 521 DRAG CHAIN HOUSINGS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 10 | EA | 50 |  | 50 | 0 | 10 |  | 50
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 521 DRAG CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 10 | EA | 35 |  | 35 | 0 | 10 |  | 35
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 521 DRIVE MOTORS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 521 DRIVE CHAINS | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 13 | INSTALL TRANSFER 521 DRIVE SHAFT | #10 | 8245,8307,8404,8502,8604,8520,8522,8306,8320,8401,8403,8322,8403,8501,8323,8601,8602,8603,8521 |  |  | 60 | LF | 31.8 |  | 31.8 | 0 | 60 |  | 31.8
P | 40000 | 40001 |  | 6 | SPECIALTY RIP SAW | #7 | [5 empty] | 214.25 |  | 214.25 |  |  |  | 214.25
D | 40000 | 40001 |  | 6 | CRANE SETUP | #7 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 6 | OFFLOAD | #7 |  |  |  | 3 | TON | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 6 | LAYOUT / VERIFY | #7 |  |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 6 | INSTALL ANCHOR BOLTS | #7 |  |  |  | 36 | EA | 36 |  | 36 | 0 | 36 |  | 36
D | 40000 | 40001 |  | 6 | HAUL & SET ON FOUNDATION | #7 |  |  |  | 3 | TON | 18 |  | 18 | 0 | 3 |  | 18
D | 40000 | 40001 |  | 6 | SHIM | #7 |  |  |  | 24 | EA | 36 |  | 36 | 0 | 24 |  | 36
D | 40000 | 40001 |  | 6 | SECURE | #7 |  |  |  | 36 | EA | 12.6 |  | 12.6 | 0 | 36 |  | 12.6
D | 40000 | 40001 |  | 6 | INSTALL TRACK SYSTEM | #7 |  |  |  | 2 | EA | 30 |  | 30 | 0 | 2 |  | 30
D | 40000 | 40001 |  | 6 | PRECISION ALIGNMENT | #7 |  |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 6 | BUSHAMMERING | #7 |  |  |  | 12 | SF | 2.4 |  | 2.4 | 0 | 12 |  | 2.4
D | 40000 | 40001 |  | 6 | GROUT FORMING | #7 |  |  |  | 20 | LF | 3 |  | 3 | 0 | 20 |  | 3
D | 40000 | 40001 |  | 6 | GROUTING - CEMENTIOUTS | #7 |  |  |  | 1 | CF | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 6 | TRIM | #7 |  |  |  | 2 | EA | 40 |  | 40 | 0 | 2 |  | 40
D | 40000 | 40001 |  | 6 | CRANE REMOVAL | #7 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 6 | CLEAN UP | #7 |  |  |  | 3 | TON | 2.25 |  | 2.25 | 0 | 3 |  | 2.25
D | 40000 | 40001 |  | 6 | INSTALL DRIVE MOTOR | #7 |  |  |  | 2 | EA | 12 |  | 12 | 0 | 2 |  | 12
P | 40000 | 40002 |  | 3 | HORIZONTAL COOLER | #3 | 8109 |  |  |  |  | 2400.89 |  | 2400.89 |  |  |  | 2400.89
D | 40000 | 40002 |  | 3 | LAYOUT / VERIFY | #3 | 8109 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40002 |  | 3 | INSTALL ANCHOR BOLTS | #3 | 8109 |  |  | 144 | EA | 144 |  | 144 | 0 | 144 |  | 144
D | 40000 | 40002 |  | 3 | HAUL & SET ON FOUNDATION | #3 | 8109 |  |  | 137.5 | TON | 962.5 |  | 962.5 | 0 | 137.5 |  | 962.5
D | 40000 | 40002 |  | 3 | INSTALL CHAIN | #3 | 8109 |  |  | 1080 | LF | 32.4 |  | 32.4 | 0 | 1080 |  | 32.4
D | 40000 | 40002 |  | 3 | INSTALL SLATS | #3 | 8109 |  |  | 1220 | EA | 610 |  | 610 | 0 | 1220 |  | 610
D | 40000 | 40002 |  | 3 | SECURE | #3 | 8109 |  |  | 42 | EA | 21 |  | 21 | 0 | 42 |  | 21
D | 40000 | 40002 |  | 3 | PRECISION ALIGNMENT | #3 | 8109 |  |  | 3 | EA | 9 |  | 9 | 0 | 3 |  | 9
D | 40000 | 40002 |  | 3 | INSTALL DRIVE MOTOR | #3 | 8109 |  |  | 3 | EA | 45 |  | 45 | 0 | 3 |  | 45
D | 40000 | 40002 |  | 3 | CLEAN UP | #3 | 8109 |  |  | 137 | TON | 102.75 |  | 102.75 | 0 | 137 |  | 102.75
D | 40000 | 40002 |  | 3 | ERECT SUPPORT FRAM | #3 | 8109 |  |  | 20 | TON | 290 |  | 290 | 0 | 20 |  | 290
D | 40000 | 40002 |  | 3 | INSTALL CHAIN HOUSINGS | #3 | 8109 |  |  | 20 | EA | 60 |  | 60 | 0 | 20 |  | 60
D | 40000 | 40002 |  | 3 | INSTALL CHAIN SHAFT | #3 | 8109 |  |  | 66 | LF | 88.44 |  | 88.44 | 0 | 66 |  | 88.44
D | 40000 | 40002 |  | 3 | BUSHHAMMERING | #3 | 8109 |  |  | 36 | SF | 5.4 |  | 5.4 | 0 | 36 |  | 5.4
D | 40000 | 40002 |  | 3 | GROUT FORMING | #3 | 8109 |  |  | 144 | LF | 21.6 |  | 21.6 | 0 | 144 |  | 21.6
D | 40000 | 40002 |  | 3 | GROUTING - CEMENTIOUTS | #3 | 8109 |  |  | 2.4 | CF | 4.8 |  | 4.8 | 0 | 2.4 |  | 4.8
P | 40000 | 40001 |  | 10 | TRIM SAW CONVEYORS | #2 | 8103,8106,8120,8121,8107 |  |  |  |  | 754.64 |  | 754.64 |  |  |  | 754.64
D | 40000 | 40001 |  | 10 | NEW CUSTOM LABOR ITEM | #2 | 8103,8106,8120,8121,8107 |  |  | 0 | EA |  |  |  | 0 | 0
D | 40000 | 40001 |  | 10 | CRANE SETUP | #2 | 8103,8106,8120,8121,8107 |  |  | 3 | EA | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 10 | OFFLOAD | #2 | 8103,8106,8120,8121,8107 |  |  | 13 | EA | 130 |  | 130 | 0 | 13 |  | 130
D | 40000 | 40001 |  | 10 | OFFLOAD - SHAFT | #2 | 8103,8106,8120,8121,8107 |  |  | 1.2 | TON | 2.4 |  | 2.4 | 0 | 1.2 |  | 2.4
D | 40000 | 40001 |  | 10 | HAUL & SET ON FOUNDATION | #2 | 8103,8106,8120,8121,8107 |  |  | 13 | EA | 130 |  | 130 | 0 | 13 |  | 130
D | 40000 | 40001 |  | 10 | LAYOUT / VERIFY ROLLER CONVEYOR | #2 | 8103,8106,8120,8121,8107 |  |  | 7 | EA | 28 |  | 28 | 0 | 7 |  | 28
D | 40000 | 40001 |  | 10 | LAYOUT / VERIFY TRANSFER CONVEYOR | #2 | 8103,8106,8120,8121,8107 |  |  | 6 | EA | 24 |  | 24 | 0 | 6 |  | 24
D | 40000 | 40001 |  | 10 | INSTALL ANCHOR BOLTS | #2 | 8103,8106,8120,8121,8107 |  |  | 172 | EA | 43 |  | 43 | 0 | 172 |  | 43
D | 40000 | 40001 |  | 10 | SET ROLLER CONVEYOR SUPPORTS | #2 | 8103,8106,8120,8121,8107 |  |  | 44 | EA | 99 |  | 99 | 0 | 44 |  | 99
D | 40000 | 40001 |  | 10 | INSTALL ROLLER DRIVE CHAINS | #2 | 8103,8106,8120,8121,8107 |  |  | 6 | EA | 3.3 |  | 3.3 | 0 | 6 |  | 3.3
D | 40000 | 40001 |  | 10 | TRANSFER FRAME BOLT UPS 8" | #2 | 8103,8106,8120,8121,8107 |  |  | 16 | EA | 16.8 |  | 16.8 | 0 | 16 |  | 16.8
D | 40000 | 40001 |  | 10 | INSTALL ROLLER DRIVE MOTOR | #2 | 8103,8106,8120,8121,8107 |  |  | 3 | EA | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 10 | HAUL & SET ON FOUNDATION - SHAFT | #2 | 8103,8106,8120,8121,8107 |  |  | 1.2 | TON | 7.2 |  | 7.2 | 0 | 1.2 |  | 7.2
D | 40000 | 40001 |  | 10 | INSTALL TRANSFER DRIVE MOTOR | #2 | 8103,8106,8120,8121,8107 |  |  | 4 | EA | 8 |  | 8 | 0 | 4 |  | 8
D | 40000 | 40001 |  | 10 | INSTALL TRANSFER DRIVE CHAINS | #2 | 8103,8106,8120,8121,8107 |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40001 |  | 10 | SET AND SECURE ROLLER CONVEYOR | #2 | 8103,8106,8120,8121,8107 |  |  | 240 | LF | 84 |  | 84 | 0 | 240 |  | 84
D | 40000 | 40001 |  | 10 | PRECISION ALIGNMENT | #2 | 8103,8106,8120,8121,8107 |  |  | 7 | EA | 21 |  | 21 | 0 | 7 |  | 21
D | 40000 | 40001 |  | 10 | BUSHHAMMERING | #2 | 8103,8106,8120,8121,8107 |  |  | 32.4 | SF | 8.1 |  | 8.1 | 0 | 32.4 |  | 8.1
D | 40000 | 40001 |  | 10 | GROUT FORMING | #2 | 8103,8106,8120,8121,8107 |  |  | 180 | LF | 9 |  | 9 | 0 | 180 |  | 9
D | 40000 | 40001 |  | 10 | GROUTING - CEMENTIOUTS | #2 | 8103,8106,8120,8121,8107 |  |  | 2.7 | CF | 5.4 |  | 5.4 | 0 | 2.7 |  | 5.4
D | 40000 | 40001 |  | 10 | INSTALL DRAG CHAIN HOUSINGS | #2 | 8103,8106,8120,8121,8107 |  |  | 8 | EA | 32 |  | 32 | 0 | 8 |  | 32
D | 40000 | 40001 |  | 10 | INSTALL DRAG CHAIN IN HOUSING | #2 | 8103,8106,8120,8121,8107 |  |  | 8 | EA | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 10 | INSTALL DRAG CHAIN SHAFT | #2 | 8103,8106,8120,8121,8107 |  |  | 108 | LF | 57.24 |  | 57.24 | 0 | 108 |  | 57.24
D | 40000 | 40001 |  | 10 | INSTALL DRIVE MOTOR GUARDS | #2 | 8103,8106,8120,8121,8107 |  |  | 4 | EA | 4 |  | 4 | 0 | 4 |  | 4
D | 40000 | 40001 |  | 10 | INSTALL LIFT CYLINDERS | #2 | 8103,8106,8120,8121,8107 |  |  | 4 | EA | 6 |  | 6 | 0 | 4 |  | 6
D | 40000 | 40001 |  | 10 | CRANE REMOVAL | #2 | 8103,8106,8120,8121,8107 |  |  | 3 | EA | 6 |  | 6 | 0 | 3 |  | 6
P | 40000 | 40001 |  | 2 | FINISHING HOG | #8 | [5 empty] | 763.975 | 55.5 | 819.475 |  |  |  | 819.475
D | 40000 | 40001 |  | 2 | CRANE SETUP | #8 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 2 | OFFLOAD - CONVEYORS | #8 |  |  |  | 2 | EA | 10 |  | 10 | 0 | 2 |  | 10
D | 40000 | 40001 |  | 2 | OFFLOAD | #8 |  |  |  | 6.5 | TON | 13 |  | 13 | 0 | 6.5 |  | 13
D | 40000 | 40001 |  | 2 | LAYOUT / VERIFY - HOG | #8 |  |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 2 | INSTALL ANCHOR BOLTS | #8 |  |  |  | 28 | EA | 112 |  | 112 | 0 | 28 |  | 112
D | 40000 | 40001 |  | 2 | HAUL & SET ON FOUNDATION | #8 |  |  |  | 6.5 | TON | 39 |  | 39 | 0 | 6.5 |  | 39
D | 40000 | 40001 |  | 2 | SHIM | #8 |  |  |  | 10 | EA | 15 |  | 15 | 0 | 10 |  | 15
D | 40000 | 40001 |  | 2 | SECURE | #8 |  |  |  | 3 | EA | 3 |  | 3 | 0 | 3 |  | 3
D | 40000 | 40001 |  | 2 | INSTALL BASE | #8 |  |  |  | 1 | EA | 5 |  | 5 | 0 | 1 |  | 5
D | 40000 | 40001 |  | 2 | PRECISION ALIGNMENT | #8 |  |  |  | 1 | EA | 3 |  | 3 | 0 | 1 |  | 3
D | 40000 | 40001 |  | 2 | BUSHHAMMERING | #8 |  |  |  | 54 | SF | 8.1 |  | 8.1 | 0 | 54 |  | 8.1
D | 40000 | 40001 |  | 2 | GROUT FORMING | #8 |  |  |  | 80 | EA | 12 |  | 12 | 0 | 80 |  | 12
D | 40000 | 40001 |  | 2 | GROUTING - CEMENTIOUTS | #8 |  |  |  | 4.5 | CF | 9 |  | 9 | 0 | 4.5 |  | 9
D | 40000 | 40001 |  | 2 | CRANE REMOVAL | #8 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 2 | CLEAN UP | #8 |  |  |  | 6.5 | TON | 4.875 |  | 4.875 | 0 | 6.5 |  | 4.875
D | 40000 | 40001 |  | 2 | WELDOUT W6 TO COLUMN SUPPORTS | #8 |  |  |  | 360 | L IN |  | 18 | 18 | 0 | 360 |  | 18
D | 40000 | 40001 |  | 2 | INSTALL TENSIONER ROLLER | #8 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 2 | INSTALL DRIVE MOTOR | #8 |  |  |  | 1 | EA | 1 |  | 1 | 0 | 1 |  | 1
D | 40000 | 40001 |  | 2 | INSTALL CONVEYOR BELT | #8 |  |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 2 | LAYOUT INFEED CONVEYOR | #8 |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 2 | LAYOUT OUTFEED CONVEYOR | #8 |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 2 | INSTALL INFEED CONVEYOR | #8 |  |  |  | 60 | LF | 330 |  | 330 | 0 | 60 |  | 330
D | 40000 | 40001 |  | 2 | INSTALL OUTFEED CONVEYOR | #8 |  |  |  | 30 | LF | 165 | 37.5 | 202.5 | 0 | 30 |  | 202.5
P | 40000 | 40002 |  | 9 | WRAPPERS AND STAPLERS | #14 | [5 empty] | 1784.7 |  | 1784.7 |  |  |  | 1784.7
D | 40000 | 40002 |  | 9 | ASSEMBLE AND ERECT PLATFORMS | #14 |  |  |  | 2 | EA | 200 |  | 200 | 0 | 2 |  | 200
D | 40000 | 40002 |  | 9 | INSTALL SPRING CANS | #14 |  |  |  | 20 | EA | 80 |  | 80 | 0 | 20 |  | 80
D | 40000 | 40002 |  | 9 | INSTALL WASTE CONVEYOR BELT | #14 |  |  |  | 62 | LF | 155 |  | 155 | 0 | 62 |  | 155
D | 40000 | 40002 |  | 9 | CRANE SETUP | #14 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40002 |  | 9 | OFFLOAD | #14 |  |  |  | 30 | TON | 60 |  | 60 | 0 | 30 |  | 60
D | 40000 | 40002 |  | 9 | LAYOUT / VERIFY INFEED CONVEYORS | #14 |  |  |  | 6 | EA | 36 |  | 36 | 0 | 6 |  | 36
D | 40000 | 40002 |  | 9 | LAYOUT / VERIFY WRAPPERS | #14 |  |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40002 |  | 9 | LAYOUT / VERIFY SPRING CANS | #14 |  |  |  | 20 | EA | 120 |  | 120 | 0 | 20 |  | 120
D | 40000 | 40002 |  | 9 | LAYOUT / VERIFY - WASTE CONVEYOR | #14 |  |  |  | 1 | EA | 6 |  | 6 | 0 | 1 |  | 6
D | 40000 | 40002 |  | 9 | LAYOUT / VERIFY OUTFEED CONVEYORS | #14 |  |  |  | 8 | EA | 48 |  | 48 | 0 | 8 |  | 48
D | 40000 | 40002 |  | 9 | INSTALL ANCHOR BOLTS | #14 |  |  |  | 408 | EA | 102 |  | 102 | 0 | 408 |  | 102
D | 40000 | 40002 |  | 9 | HAUL & SET ON FOUNDATION WASTE CONVEYOR | #14 |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40002 |  | 9 | HAUL & SET ON FOUNDATION OUTFEED CONVEYORS | #14 |  |  |  | 8 | EA | 36 |  | 36 | 0 | 8 |  | 36
D | 40000 | 40002 |  | 9 | HAUL & SET ON FOUNDATION INFEED CONVEYORS | #14 |  |  |  | 6 | EA | 27 |  | 27 | 0 | 6 |  | 27
D | 40000 | 40002 |  | 9 | HAUL & SET ON FOUNDATION WRAPPERS | #14 |  |  |  | 10 | TON | 60 |  | 60 | 0 | 10 |  | 60
D | 40000 | 40002 |  | 9 | SHIM | #14 |  |  |  | 4 | EA | 6 |  | 6 | 0 | 4 |  | 6
D | 40000 | 40002 |  | 9 | SECURE | #14 |  |  |  | 408 | EA | 142.8 |  | 142.8 | 0 | 408 |  | 142.8
D | 40000 | 40002 |  | 9 | INSTALL ROLLERS | #14 |  |  |  | 4 | EA | 20 |  | 20 | 0 | 4 |  | 20
D | 40000 | 40002 |  | 9 | BUSHHAMMERING | #14 |  |  |  | 120 | SF | 24 |  | 24 | 0 | 120 |  | 24
D | 40000 | 40002 |  | 9 | PRECISION ALIGNMENT | #14 |  |  |  | 8 | EA | 24 |  | 24 | 0 | 8 |  | 24
D | 40000 | 40002 |  | 9 | GROUT FORMING | #14 |  |  |  | 400 | LF | 32 |  | 32 | 0 | 400 |  | 32
D | 40000 | 40002 |  | 9 | GROUTING - CEMENTIOUTS | #14 |  |  |  | 10 | CF | 20 |  | 20 | 0 | 10 |  | 20
D | 40000 | 40002 |  | 9 | TRIM | #14 |  |  |  | 2 | EA | 240 |  | 240 | 0 | 2 |  | 240
D | 40000 | 40002 |  | 9 | CRANE REMOVAL | #14 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40002 |  | 9 | CLEAN UP | #14 |  |  |  | 10 | TON | 7.5 |  | 7.5 | 0 | 10 |  | 7.5
D | 40000 | 40002 |  | 9 | SET AND SECURE INFEED CNVEYORS | #14 |  |  |  | 6 | EA | 60 |  | 60 | 0 | 6 |  | 60
D | 40000 | 40002 |  | 9 | INSTALL INFEED CONVEYOR DRIVE MOTORS | #14 |  |  |  | 4 | EA | 12 |  | 12 | 0 | 4 |  | 12
D | 40000 | 40002 |  | 9 | INSTALL INFEED CONVEYOR DRIVE CHAINS | #14 |  |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40002 |  | 9 | SET AND SECURE OUTFEED CONVEYOR SUPPORT STRUCTURE | #14 |  |  |  | 8 | EA | 64 |  | 64 | 0 | 8 |  | 64
D | 40000 | 40002 |  | 9 | INSTALL OUTFEED CONVEYOR DRIVE MOTORS | #14 |  |  |  | 4 | EA | 16 |  | 16 | 0 | 4 |  | 16
D | 40000 | 40002 |  | 9 | INSTALL OUTFEED CONVEYOR DRIVE CHAINS | #14 |  |  |  | 4 | EA | 2.2 |  | 2.2 | 0 | 4 |  | 2.2
D | 40000 | 40002 |  | 9 | ASSEMBLE AND TRIM OUTFEED CONVEYORTS | #14 |  |  |  | 8 | EA | 160 |  | 160 | 0 | 8 |  | 160
P | 40000 | 40001 |  | 8 | STRAPPERS | #13 | [5 empty] | 78.6 |  | 78.6 |  |  |  | 78.6
D | 40000 | 40001 |  | 8 | CRANE SETUP | #13 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 8 | OFFLOAD | #13 |  |  |  | 2 | TON | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 8 | LAYOUT / VERIFY | #13 |  |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 8 | INSTALL ANCHOR BOLTS | #13 |  |  |  | 16 | EA | 16 |  | 16 | 0 | 16 |  | 16
D | 40000 | 40001 |  | 8 | HAUL & SET ON FOUNDATION | #13 |  |  |  | 2 | TON | 12 |  | 12 | 0 | 2 |  | 12
D | 40000 | 40001 |  | 8 | SHIM | #13 |  |  |  | 8 | EA | 12 |  | 12 | 0 | 8 |  | 12
D | 40000 | 40001 |  | 8 | SECURE | #13 |  |  |  | 16 | EA | 5.6 |  | 5.6 | 0 | 16 |  | 5.6
D | 40000 | 40001 |  | 8 | GROUT FORMING | #13 |  |  |  | 40 | LF | 4 |  | 4 | 0 | 40 |  | 4
D | 40000 | 40001 |  | 8 | BUSHHAMMERING | #13 |  |  |  | 18 | SF | 4.5 |  | 4.5 | 0 | 18 |  | 4.5
D | 40000 | 40001 |  | 8 | GROUTING - CEMENTIOUTS | #13 |  |  |  | 1.5 | CF | 3 |  | 3 | 0 | 1.5 |  | 3
D | 40000 | 40001 |  | 8 | TRIM | #13 |  |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 8 | CRANE REMOVAL | #13 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 8 | CLEAN UP | #13 |  |  |  | 2 | TON | 1.5 |  | 1.5 | 0 | 2 |  | 1.5
P | 40000 | 40001 |  |  | WELDER ADJUSTMENT | [7 empty] | 2250 | 2250 |  |  |  | 2250
D | 40000 | 40001 |  |  | 3 WELDER 50HR WEEK 15 WEEKS |  |  |  |  | 150 | HOURS |  | 2250 | 2250 | 0 | 150 |  | 2250
P | 40000 | 40001 |  | 11 | COOLER CONVEYORS | #4 | 8108,8201 |  |  |  |  | 528.04 |  | 528.04 |  |  |  | 528.04
D | 40000 | 40001 |  | 11 | CRANE SETUP | #4 | 8108,8201 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 11 | OFFLOAD | #4 | 8108,8201 |  |  | 6 | EA | 60 |  | 60 | 0 | 6 |  | 60
D | 40000 | 40001 |  | 11 | OFFLOAD SHAFT | #4 | 8108,8201 |  |  | 2.2 | TON | 4.4 |  | 4.4 | 0 | 2.2 |  | 4.4
D | 40000 | 40001 |  | 11 | HAUL & SET ON FOUNDATION | #4 | 8108,8201 |  |  | 6 | EA | 60 |  | 60 | 0 | 6 |  | 60
D | 40000 | 40001 |  | 11 | LAYOUT / VERIFY OUTFEED TRANSFER CONVEYOR | #4 | 8108,8201 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 11 | LAYOUT / VERIFY INFEED TRANSFER CONVEYOR | #4 | 8108,8201 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 11 | INSTALL ANCHOR BOLTS | #4 | 8108,8201 |  |  | 182 | EA | 45.5 |  | 45.5 | 0 | 182 |  | 45.5
D | 40000 | 40001 |  | 11 | SET AND SECURE INFEED CHAIN HOUSINGS | #4 | 8108,8201 |  |  | 9 | EA | 9 |  | 9 | 0 | 9 |  | 9
D | 40000 | 40001 |  | 11 | SET AND SECURE OUTFEED CHAIN HOUSINGS | #4 | 8108,8201 |  |  | 9 | EA | 9 |  | 9 | 0 | 9 |  | 9
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED DRIVE CHAIN | #4 | 8108,8201 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 11 | INSTALL INFEED DRIVE MOTOR | #4 | 8108,8201 |  |  | 2 | EA | 6 |  | 6 | 0 | 2 |  | 6
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED DRIVE MOTOR | #4 | 8108,8201 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 11 | HAUL & SET ON FOUNDATION SHAFT | #4 | 8108,8201 |  |  | 2.2 | TON | 13.2 |  | 13.2 | 0 | 2.2 |  | 13.2
D | 40000 | 40001 |  | 11 | INSTALL INFEED DRIVE CHAIN | #4 | 8108,8201 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 11 | SECURE | #4 | 8108,8201 |  |  | 182 | EA | 45.5 |  | 45.5 | 0 | 182 |  | 45.5
D | 40000 | 40001 |  | 11 | PRECISION ALIGNMENT | #4 | 8108,8201 |  |  | 4 | EA | 12 |  | 12 | 0 | 4 |  | 12
D | 40000 | 40001 |  | 11 | GROUT FORMING | #4 | 8108,8201 |  |  | 85 | LF | 5.1 |  | 5.1 | 0 | 85 |  | 5.1
D | 40000 | 40001 |  | 11 | BUSHHAMMERING | #4 | 8108,8201 |  |  | 14.4 | SF | 3.6 |  | 3.6 | 0 | 14.4 |  | 3.6
D | 40000 | 40001 |  | 11 | GROUTING - CEMENTIOUTS | #4 | 8108,8201 |  |  | 1.2 | CF | 2.4 |  | 2.4 | 0 | 1.2 |  | 2.4
D | 40000 | 40001 |  | 11 | CRANE REMOVAL | #4 | 8108,8201 |  |  | 2 | EA | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 11 | CLEAN UP | #4 | 8108,8201 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 11 | INSTALL INFEED SUPPORT FRAMING | #4 | 8108,8201 |  |  | 36 | EA | 30.6 |  | 30.6 | 0 | 36 |  | 30.6
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED SUPPORT FRAMING | #4 | 8108,8201 |  |  | 36 | EA | 30.6 |  | 30.6 | 0 | 36 |  | 30.6
D | 40000 | 40001 |  | 11 | INSTALL INFEED DRAG CHAIN SHAFT | #4 | 8108,8201 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 11 | INSTALL INFEED DRAG CHAINS | #4 | 8108,8201 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED DRAG CHAIN SHAFT | #4 | 8108,8201 |  |  | 62 | LF | 32.86 |  | 32.86 | 0 | 62 |  | 32.86
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED DRAG CHAIN | #4 | 8108,8201 |  |  | 9 | EA | 13.5 |  | 13.5 | 0 | 9 |  | 13.5
D | 40000 | 40001 |  | 11 | INSTALL OUTFEED 8" LIFT SHAFT | #4 | 8108,8201 |  |  | 62 | LF | 50.22 |  | 50.22 | 0 | 62 |  | 50.22
P | 40000 | 40001 |  | 17 | WASTE CONVEYORS | #9 | [5 empty] | 1544.56 | 60 | 1604.56 |  |  |  | 1604.56
D | 40000 | 40001 |  | 17 | OFFLOAD | #9 |  |  |  | 24 | EA | 240 |  | 240 | 0 | 24 |  | 240
D | 40000 | 40001 |  | 17 | INSTALL WASTE CONVEYOR 40' SECTIONS | #9 |  |  |  | 484 | LF | 726 |  | 726 | 0 | 484 |  | 726
D | 40000 | 40001 |  | 17 | LAYOUT / VERIFY | #9 |  |  |  | 24 | EA | 96 |  | 96 | 0 | 24 |  | 96
D | 40000 | 40001 |  | 17 | INSTALL ANCHOR BOLTS | #9 |  |  |  | 320 | EA | 80 |  | 80 | 0 | 320 |  | 80
D | 40000 | 40001 |  | 17 | HAUL & SET ON FOUNDATION | #9 |  |  |  | 24 | EA | 240 |  | 240 | 0 | 24 |  | 240
D | 40000 | 40001 |  | 17 | INSTALL DRIVE MOTORS | #9 |  |  |  | 3 | EA | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 17 | INSTALL DRIVE CHAINS | #9 |  |  |  | 3 | EA | 6 |  | 6 | 0 | 3 |  | 6
D | 40000 | 40001 |  | 17 | INSTALL TENSIONER ROLLERS | #9 |  |  |  | 8 | EA | 40 |  | 40 | 0 | 8 |  | 40
D | 40000 | 40001 |  | 17 | PRECISION ALIGNMENT | #9 |  |  |  | 3 | EA | 9 |  | 9 | 0 | 3 |  | 9
D | 40000 | 40001 |  | 17 | GROUT FORMING | #9 |  |  |  | 352 | LF | 10.56 |  | 10.56 | 0 | 352 |  | 10.56
D | 40000 | 40001 |  | 17 | BUSHHAMMERING | #9 |  |  |  | 30 | SF | 6 |  | 6 | 0 | 30 |  | 6
D | 40000 | 40001 |  | 17 | GROUTING - CEMENTIOUTS | #9 |  |  |  | 2.5 | CF | 5 |  | 5 | 0 | 2.5 |  | 5
D | 40000 | 40001 |  | 17 | INSTALL WASTE CHUTE | #9 |  |  |  | 70 | LF | 70 |  | 70 | 0 | 70 |  | 70
D | 40000 | 40001 |  | 17 | CEAN UP | #9 |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 17 | WELD CONNECTON POINTS | #9 |  |  |  | 60 | LF |  | 60 | 60 | 0 | 60 |  | 60
P | 40000 | 40001 |  | 16 | REMAN CONVEYORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  |  |  | 1088.23 |  | 1088.23 |  |  |  | 1088.23
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 14 | EA | 140 |  | 140 | 0 | 14 |  | 140
D | 40000 | 40001 |  | 16 | LAYOUT ROLLER CONVEYORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 8 | EA | 16 |  | 16 | 0 | 8 |  | 16
D | 40000 | 40001 |  | 16 | OFFLOAD SHAFT | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1.5 | TON | 3 |  | 3 | 0 | 1.5 |  | 3
D | 40000 | 40001 |  | 16 | OFFLOAD | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 18 | EA | 180 |  | 180 | 0 | 18 |  | 180
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY TRANSFER 317 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY TRANSFER 310 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 16 | INSTALL ROLLER CONVEYORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 261 | LF | 73.08 |  | 73.08 | 0 | 261 |  | 73.08
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY TRANSFER 316 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY PACKERS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY TRANSFER 249/250 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 16 | LAYOUT / VERIFY STACKER 251/252 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 16 | INSTALL CUT SAWS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 40 |  | 40 | 0 | 2 |  | 40
D | 40000 | 40001 |  | 16 | INSTALL ANCHOR BOLTS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 222 | EA | 55.5 |  | 55.5 | 0 | 222 |  | 55.5
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION TRANSFER 316 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION STACKER 251/252 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 12 |  | 12 | 0 | 2 |  | 12
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION PACKERS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 3 | EA | 15 |  | 15 | 0 | 3 |  | 15
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION SHAFT | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1.5 | TON | 9 |  | 9 | 0 | 1.5 |  | 9
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION TRANSFER 317 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 12 |  | 12 | 0 | 1 |  | 12
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION TRANSFER 249/250 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 20 |  | 20 | 0 | 2 |  | 20
D | 40000 | 40001 |  | 16 | HAUL & SET ON FOUNDATION TRANSFER 310 | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 20 |  | 20 | 0 | 1 |  | 20
D | 40000 | 40001 |  | 16 | SET AND SECURE TRANSFER 310 SUPPORT STRUCTURE | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 3 | EA | 45 |  | 45 | 0 | 3 |  | 45
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 310 DRAG CHAIN HOUSINGS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 9 | EA | 45 |  | 45 | 0 | 9 |  | 45
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 310 DRAG CHAINS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 9 | EA | 27 |  | 27 | 0 | 9 |  | 27
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 310 DRIVE MOTORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 310 DRIVE CHAINS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 310 DRIVE SHAFT | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 70 | LF | 37.1 |  | 37.1 | 0 | 70 |  | 37.1
D | 40000 | 40001 |  | 16 | SET AND SECURE TRANSFER 316 SUPPORT STRUCTURE | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 6 | EA | 36 |  | 36 | 0 | 6 |  | 36
D | 40000 | 40001 |  | 16 | SET AND SECURE TRANSFER 317 SUPPORT STRUCTURE | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 3 | EA | 12 |  | 12 | 0 | 3 |  | 12
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 317 DRAG CHAIN HOUSINGS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 5 | EA | 15 |  | 15 | 0 | 5 |  | 15
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 317 DRAG CHAIN | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 5 | EA | 10 |  | 10 | 0 | 5 |  | 10
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 317 DRIVE MOTORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 4 |  | 4 | 0 | 1 |  | 4
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 317 DRIVE CHAINS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 0.55 |  | 0.55 | 0 | 1 |  | 0.55
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 317 DRIVE SHAFT | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 20 | LF | 10.6 |  | 10.6 | 0 | 20 |  | 10.6
D | 40000 | 40001 |  | 16 | INSTALL PACKERS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 3 | EA | 30 |  | 30 | 0 | 3 |  | 30
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 249/250 DRAG CHAIN HOUSINGS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 4 | EA | 16 |  | 16 | 0 | 4 |  | 16
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 249/250 DRAG CHAINS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 4 | EA | 8 |  | 8 | 0 | 4 |  | 8
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 249/250 DRIVE MOTORS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 249/250 DRIVE CHAINS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 2 | EA | 1.1 |  | 1.1 | 0 | 2 |  | 1.1
D | 40000 | 40001 |  | 16 | INSTALL TRANSFER 249/250 DRIVE SHAFT | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 20 | LF | 10.6 |  | 10.6 | 0 | 20 |  | 10.6
D | 40000 | 40001 |  | 16 | SET AND SECURE STACKER 251/252 SUPPORT STRUCTURE | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 4 | EA | 24 |  | 24 | 0 | 4 |  | 24
D | 40000 | 40001 |  | 16 | INSTALL STACKER 251/252 LIFT BEAM | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 20 | LF | 40 |  | 40 | 0 | 20 |  | 40
D | 40000 | 40001 |  | 16 | CLEAN UP | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 40000 | 40001 |  | 16 | GROUT FORMING | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 259 | LF | 20.72 |  | 20.72 | 0 | 259 |  | 20.72
D | 40000 | 40001 |  | 16 | GROUTING - CEMENTIOUTS | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 5.2 | CF | 10.4 |  | 10.4 | 0 | 5.2 |  | 10.4
D | 40000 | 40001 |  | 16 | BUSHHAMMERING | #12 | 8310,8316,8317,8249,8250,8251,8252 |  |  | 62.4 | SF | 12.48 |  | 12.48 | 0 | 62.4 |  | 12.48
P | 40000 | 40001 |  | 7 | REMAN SAWS AND REMAN STACKERS | #11 | [5 empty] | 154 |  | 154 |  |  |  | 154
D | 40000 | 40001 |  | 7 | CRANE SETUP | #11 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 7 | OFFLOAD | #11 |  |  |  | 2 | TON | 4 |  | 4 | 0 | 2 |  | 4
D | 40000 | 40001 |  | 7 | LAYOUT / VERIFY | #11 |  |  |  | 2 | EA | 8 |  | 8 | 0 | 2 |  | 8
D | 40000 | 40001 |  | 7 | INSTALL ANCHOR BOLTS | #11 |  |  |  | 40 | EA | 14 |  | 14 | 0 | 40 |  | 14
D | 40000 | 40001 |  | 7 | HAUL & SET ON FOUNDATION | #11 |  |  |  | 2 | TON | 12 |  | 12 | 0 | 2 |  | 12
D | 40000 | 40001 |  | 7 | SHIM | #11 |  |  |  | 20 | EA | 30 |  | 30 | 0 | 20 |  | 30
D | 40000 | 40001 |  | 7 | SECURE | #11 |  |  |  | 40 | EA | 10 |  | 10 | 0 | 40 |  | 10
D | 40000 | 40001 |  | 7 | GROUT FORMING | #11 |  |  |  | 70 | LF | 10.5 |  | 10.5 | 0 | 70 |  | 10.5
D | 40000 | 40001 |  | 7 | BUSHHAMMERING | #11 |  |  |  | 48 | SF | 12 |  | 12 | 0 | 48 |  | 12
D | 40000 | 40001 |  | 7 | GROUTING - CEMENTIOUTS | #11 |  |  |  | 4 | CF | 8 |  | 8 | 0 | 4 |  | 8
D | 40000 | 40001 |  | 7 | TRIM | #11 |  |  |  | 2 | EA | 40 |  | 40 | 0 | 2 |  | 40
D | 40000 | 40001 |  | 7 | CRANE REMOVAL | #11 |  |  |  | 1 | EA | 2 |  | 2 | 0 | 1 |  | 2
D | 40000 | 40001 |  | 7 | CLEAN UP | #11 |  |  |  | 2 | TON | 1.5 |  | 1.5 | 0 | 2 |  | 1.5
W | 10000 |  |  |  | MOBILIZE | [6 empty] | 480 | 30 | 510 |  |  | 15.1 | 494.9 | 3% | [13 empty] | 1.51 |  | 15.1
P | 10000 | 10005 |  |  | WELDER TEST / QUALIFICATION | [7 empty] | 30 | 30 |  |  | 10 | 20 | 33% | [13 empty] | 1 |  | 10
D | 10000 | 10005 |  |  | TEST |  |  |  |  | 3 | CRAFT |  | 30 | 30 | 1 | 2 | 10 | 20 | 33% | [13 empty] | 1 |  | 10
P | 10000 | 10007 |  |  | CONNECT UTILITIES
P | 10000 | 10001 |  |  | EQUIPMENT SETUP | [6 empty] | 50 |  | 50 |  |  | 5.1 | 44.9 | 10% | [13 empty] | 0.51 |  | 5.1
D | 10000 | 10001 |  |  | TOOLS |  |  |  |  | 1 | EA | 10 |  | 10 | 0.51 | 0.49 | 5.1 | 4.9 | 51% | [13 empty] | 0.51 |  | 5.1
D | 10000 | 10001 |  |  | EQUIPMENT |  |  |  |  | 10 | EA | 20 |  | 20 | 0 | 10 |  | 20
D | 10000 | 10001 |  |  | CRANES |  |  |  |  | 2 | EA | 20 |  | 20 | 0 | 2 |  | 20
P | 10000 | 10008 |  |  | FREIGHT IN
P | 10000 | 10002 |  |  | TRAILER SETUP | [6 empty] | 20 |  | 20 |  |  |  | 20
D | 10000 | 10002 |  |  | OFFICE TRAILER |  |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
D | 10000 | 10002 |  |  | TOOL TRAILER |  |  |  |  | 1 | EA | 10 |  | 10 | 0 | 1 |  | 10
P | 10000 | 10004 |  |  | SAFETY ORIENTATION | [6 empty] | 410 |  | 410 |  |  |  | 410
D | 10000 | 10004 |  |  | CUSTOMER SAFETY ORIENTATION |  |  |  |  | 41 | CRAFT | 82 |  | 82 | 0 | 41 |  | 82
D | 10000 | 10004 |  |  | INDEMAND SAFETY ORIENTATION |  |  |  |  | 41 | CRAFT | 328 |  | 328 | 0 | 41 |  | 328
W | 30000 |  |  |  | CONCRETE
P | 30000 | 39998 |  |  | SURVEY
[5 empty] | TOTAL | [6 empty] | 37786.0715 | 2395.5 | 40181.5715 |  |  | 1011 | 39170.5715 | 2.516% | [12 empty] | 3 | 34.76 | 0.75 | 1010.25